灯光检讨报告2004

| Task / Problems encountered | Potential solutions / Tips |
| --- | --- |
| 十月 |  |
| 了解剧本 discuss 剧情 with导演 n SM Come out with a general idea for each 剧 | - Must be familiar with script so as to portray the correct 感觉 with ur lx and to facilitate discussions. - Light are hard to visualize but just try ur best. |
| 十一月/ 寒假 |  |
| - Read up on different types of lx stuff - Go to library to read up as much as possible. Find enough bks to equip urself with knowledge - Make full use of 协调 to discuss lx. | - Must be clear on the different types of lights available. Be clear of the features of each type of light. eg. How it is used and what are the effects it can/cannot achieve - Go watch drama shows if possible, esp the renowned productions. - 导演can be too idealized or vague when they talk abt lx. Make sure you explain clearly what CAN be done and what CANNOT be done. And if you think certain effects are good or bad, bring it up! - IMPORTANT!! Explain to them that “ lx spot” doesn't mean a lx circle hitting on the ground with the actor standing on it! Most likely you have more than 1 lx hitting the actor’s face n it’s the face n body that matter the most, not the size of the lx spot on the ground!! (but of coz don't spill the lx too much) - MUST!! keep reminding your 导演 that no actors should stand closer than 0.5 m from the edge of VT stage. Other wise they have no face lx AT ALL!! They are advisable to stand behind the 1st lx truss. Remember to keep reminding 导演 and SM about this fact as they will certainly forget. - Feel free to ask seniors if you have problems. |
| Draw out a good timetable | Make a timetable and STICK TO IT as far as possible. Remember to leave enough blank slots to complete uncompleted work due to holidays etc |
| Prepare for own 灯光课 for J1s | Source for useful materials to conduct the lessons. Use this chance to revise ur 灯光knowledge also, and add in whatever info you think is useful. |
| Budget | List out all materials needed and get good quotes for them. Try to save $$$ where ever possible. Although they will be subjected to changes, but u should have a general idea of budget. |
| Buying of materials | Get extra materials to experiment with and to use as backup. eg extra batteries and wires. Go to neighbourhood or cheaper shops to buy materials as it is cheaper. A second trip to obtain more materials is usually unavoidable |
| 十二月 |  |
| Try to recce VT at least once | - Get to know the technicians. Familiarize yourself with the lights’ positions. Ask questions when needed - Obtain latest versions of lighting rig plan, equipment list etc |
| Professional灯光课 from 老师 | - Take notes and ask questions - This is the time where there will be hand-ons so once again familiarize yourself with the different types of lights - Absorb as much as possible, clarify any doubts and uncertainties - Listen carefully to老师 and do not be complacent. They are very experienced and understand your lx constraints. |
| Preliminary version of cue sheet | - Must have made a beta version of cue sheet for each剧 and make sure the SMs and 导演s understand it. Subject to many many changes but die die must 出 a cue sheet! - Go through scene to scene analysis with SMs and 导演 |
| Contact seniors to borrow equipment or ask questions | With the right contacts the smoke machine can be borrowed for free. Daily rent for one smoke machine in VT is $50, which is very expensive. |
| Confirm the gobos that are needed early | If gobos can be bought, then buy it as it is more durable and reliable. Order as early as possible, as minimum delivery time is about 3 weeks. If not then have to cut gobo yourself. Check out the correct size of gobo used in VT! |
| Get receipts for purchases! | Very important to get receipts! No receipt = no claiming of money, and have to 自掏腰包 |
| Establish good relations with 黄城ppl, especially 总监, SMs ,导演s 音响and 道具ppl | Very important as u will be working with these ppl for the next 3 months, a happy working relationship makes things much much easier!! And you will need their help! |
| Dare to say “no” if demands are too excessive | Do not let SMs and导演s climb over ur head. Let them know ur stand and work out a compromise. Remember, You have the final say in things regarding lx! |
| Attachment | - Last year Yong Liang went overseas n I was sick for 4 days, so we didn't make much use of the attachment  - But it can be a very fruitful experience! Try to get VT attachment if possible. You can watch how professionals work and learn techniques in focusing n plotting. - Ask questions whenever possible. |
| 一月 |  |
| Choose juniors for 灯光 carefully. | - Try to get enthu and lively J1s as this will make 灯光more fun. Experience is recommended but not required - .Recruit about 9 members with a good gender ratio. Girls are preferred as they tend to be less playful. But guys can do more manual work. No PRCs or foreign scholars who cannot be devoted to 灯光. Remember, 宁缺毋滥. |
| 灯光课 | - Must be clear and precise on what u are teaching, and pass on the confidence to them. Test them when needed. If possible have a practical session with actual lights brought in. Can borrow lights from PA/AVA if contacts are available. - Try not to make lessons too long or boring. But having lesson is still necessary. |
| Prepare allocation of people for each 剧 | Some 剧s may need more people eg. Smoke machine, followspot etc. but can use members from other剧s also. |
| Obtain smoke machine | Very expensive to rent. Borrowed from Doreen for free. Received the smoke machine at the end of February. |
| Making of 阴阳测度器 decided after budget day | Had to overshoot budget to obtain materials. Next time must finalise budget before budget day. Gobos take up a huge part of your budget. |
| Decided to make gobos ourselves | Gobo might be flimsy and not durable. Luckily homemade gobos managed to hold. Try to order gobos if possible and do it early. |
| Begin to 跟戏 | 跟戏 is very important! Make sure J1s don't just stone n rot. They must be really familiar with the entire script to help you in VT. |
| Revision of cue sheets | There will be lots of changes n updates. But make sure all updates should be done before 总彩。 You should discuss lx with both the SM n 导演, it is easier to clarify any doubts and stage concepts. |
| Floor plans / Set diagrams | - Get floor plans from 道具asap. Must standardize types of floor plans among SMs to prevent confusion. 半杯 had a different type of floor plan from 闹鬼. - 道具 diagrams can give accurate measurements but they are not drawn to scale on a whole. So better draw out your own set diagram with lx grid to facilitate your planning. ( Refer to Appendix A and diskette) |
| Some floor plans not finalized | No finalized floor plans means which light to use for set cannot be confirmed. At least get good estimates of positions of sets. |
| Recce VT | Were lucky this year to enable J1s to recce VT before move-in. Get SMs to go also to explain certain concepts. |
| Colour of lights | - Try to finalise which colours to use ASAP. Then can confirm if VT has that colour during subsequent recce of VT. If recce not possible then call up VT and ask. - Use the Lee filter book to help you to decide on which colour to use. You should take note of the mood, colour match with costumes, character highlight etc. |
| Allocation of lights | Allocation of lights must be clear and finalized at least 2 weeks before move-in. Be very sure about y u are using that particular light for that area. Try not to share lights whenever possible. Rigging of extra lights is possible, but generally limited to a maximum of 2 per truss. |
| 二月 |  |
| Lights Floor Plan | - You should have 1 lx plan from VT and then make your own lx plan based on your allocation of lx. - Once your lx are finalized, draw out your lx on the A3 size lx grid line. This is drawn to scale and can clearly help you to see which type of lx is allocated to which 剧 and what are the colours and gobos used. |
| Analyse light path, angle etc. | - Use the VT’s cross sectional scale diagram to draw out the light path and angle you have in mind. This can show where you lx will hit n which area they light up. - VT profiles have diff zoom angles and power rating. So they produce diff sharpness and lx spot size. You may use iris or diffuser to achieve the effect you want - If you are lighting up a set or person using only main truss lx. Then they should position far enough fr that truss to get at least 45-60 degree lx angle. Stress this point to SM, other wise there’s no face lx. |
| Scrollers | Dont use the scrolling function of scrollers if possible cos of unreliability. They an be used for lighting soft edged areas. Scrollers do not have barn doors! Can only change size and colours are limited to those in the colour reel. |
| Fresnels | Scrollers without the scroller. Are fixed with barn doors. Thus are more flexible that scrollers because of colour, barn door and size change. |
| PCs | Used for general lighting. Must check and refocus if necessary. Do not take their word that it is already focused. Beware of dark areas and curtain spill |
| Profiles | Mainly used for sharp edges spotlx and gobos. Can rig extra profiles from rear trusses. Extreme truss end profiles can be used also for gobos or colours. |
| Side FOH | Mainly used for facelx at DS. Must focus carefully and check check check for dark areas. Beware of spill onto side, house curtains and the speakers. |
| Top FOH | Very far and thus weak. Usually have to use at >80% intensity to have effect. Might have to use iris to reduce size. Should reserve at least 8/12 for emcees, but they can accommodate to ur needs. |
| 三月 | MOVE IN !! |
| Focus chart | Before you move in, should have made a focus chart indicating all lx that need to be focused. ( refer to appendix B) |
| Magic Sheet ( Appendix C ) | Get your magic sheets ready! - It gives a comprehensive idea of GL. ie which PC is used to lx up which area. - Use the same format for scroller. It shows which scroller is used to lx up which area, useful if u are using a scroller wash. We didn’t use scroler wash this year so it is not included in magic sheet. - Side lx table shows which side lx has been used - Front FOH n side FOH are very important for your face lx. Get to know how they have been prefocused by technicians in ur recce. The lx areas shown are quite fool proof from our experience n they will lx up the face evenly. - The little squares are for u to note spot lx or any specials. - Cyc table are for you to note down the cyc channel no. |
| Rigging of lights | - Can be done in advance if possible. Send in rig plan to technicians directly not thru VT office. Best to do it at least 1 week before move in. Rigging should be done only if there is no other light available. - Rigging can be done during hanging of backdrop. Could not be done in advance this year due to time constrains. Best to limit the extra rigging per truss to 2 lights. - But be prepared to spend more time if the previous drama grp changed your house rig. So u have to rig them back. - Insert colour gels during rigging. |
| Focusing of lx - Centre hotspot on head “hotspot on my head” - Once satisfied, lock the instrument “Lock it” - Increase or decrease the beam size (for profiles) “Open up” or “Close” - Focus the beam (for profiles) “shaper” or “softer” - Shape the beam “barn door in here” (for PC / fresnel scrollers) “shutter in to here” (for profiles) - Compare with other beam if necessary 道具may eat into your time, and there is a limit you can compromise. 导演keep making noise. | - Try to do all the GL first. Then do the rest of the truss lights by channel number or by 剧 or by sets, which ever is easier. Must think on behalf of 道具also. Work along with them not manipulate them. - Can do side lx and cyc lights together. Or cyc lights with FOH also. Try to do things simultaneously to save time. Focus all lights related to a particular set together, instead of moving the set in and out. - We focus FOH with working lx on this year, the result is disastrous! A more sensible way is to let J1s learn to plot first if you can’t do the focusing. - Had to do refocusing a lot of times this year due to insufficient face lx and colour changes. - Make it a clear point to 总监 that focusing is OUR time and all 导演should not speak if we do not ask them. If they interfere with your work, tell them to shut up! - No SM should ask 导演to clarify positions. SM should know better where are the sets and 演员！ - In case the lx can’t achieve the effect you want, talk to SM to move the set! It’s faster and easier. |
| Plotting of lx An ideal way of plotting is to let 组长sit in audience seats and talk to J1s thru intercom to do the plot. It’s the only way you can see the effects of you lighting. But your J1s wont achieve that standard for the 1st day and you will definitely run out of time You are NOT advisable to do life plot during full run, as full run is for you to feel the flow of the show. You should have enough time next year as you have 3 days to prepare. | - Make a plotting list b4 your move in. - Let the juniors plot lights after the technician teaches them how to do it. Try not to rush them as it will be their first time doing it. Preferably abt 45 mins for each剧. Must keep strictly to the time limit! - So Just do all the plots you have in mind 1st with your J1s in the control room and come out with a complete cue run for 1st day. Do amendments later on. - Changes to the cues are unavoidable, best is to plan ahead what cues to alter after each full run/tech run/show so that it can be done once there is time. You have to sit in audi seats during tech run to do the amendments and discuss with 导演。 - Group a few lx that are used to lx up the same set. So u can save time. - Check thru n run all the cues before every show carefully!! This is IMPORTANT to avoid cue jumps in 七彩 this year. Do it even if you have to delay house open time. - Remember that the control room will be locked during the technicians’ break so u wont be able to plot lights during that time. - If you are programming scrollers, program the colour scroll in the previous cue, so the next cue would lx up the colour you want. |
| Technicians | - Do not offend or irritate any technicians. U depend on them for survival even if they irritate you. So get in their good books and show that u are enjoyable to work with. - Instructions should be clear and precise with minimum hesitation. Visualize every lx b4 you move in. - Scaffold is not a good place to stay up in, so invite them down when not needed. Top FOH lights are a LONG way up in VT and hard to focus, so get it done in a single trip. Thank them when u have finished. Respect them and listen to their advice. |
| Conflict among lights | - Must try to work out a good solution to “fighting” of lights. If needed get the SMs together to tell them your problem/s and see if a compromise is possible. Of coz they will say “can not”, but in the end it’s too late when they see the problem. - Rig extra lights only as a last resort. Die die also must have face lx!! It should be your top most priority for most shows. - Recycle lights whenever possible. Recycle is different from sharing. U recycle that lx to 补any dark spot or add face lx etc. |
| Go-ing of Cues | Let everyone in that 剧have a chance to run the cues, no matter it is during a full run or the actual show. If the 组长has to be at the SM table downstairs during a tech run/full run, leave a member who is competent enough to operate the light board in the control room. Must leave a person in the control room for 谢幕to operate the 司仪cues. |
| Cue sheets | Very hard to finalise due to many changes whether from allocation of lights or demands from 导演s. try to think out a comprehensive version early to prevent too many changes. Cue sheets usually change after a rehearsal. But they MUST be finallised after 总彩二 . Get juniors to make one themselves also so that they can familiarize themselves with the剧’s lights. |
| Timetable | Hard to draw up a good timetable and stick to it strictly due to many unforeseen circumstances. Refer to timetable often and make changes if needed. Also plan a timetable for urself for move-in. |
| Junior灯光-ians | Recruit only those that are enthusiastic. Experience is not needed. Check out their schedules and make sure they can commit to 灯光. Try to keep them enthu and interested. If got time to spare give them some time to interact among themselves to get to know each other. |
| 灯光课 | Must have the relevant course materials to teach. Be clear as to what u are teaching to instill confidence in ur students. Could have practical lesson cos of contacts with PA/AVA and could borrow their lights. |
| 半杯stairs | Lights to use for the stairs could not be changed due to truss constrains and thus stairs positions had to be changed. Check markings during rehearsals in hall and correct mistakes early. Due to height difference(eg closer to light) the intensity had to be lowered to prevent overexposure(actors appear too bright). There was also insufficient face lx, which was eventually solved by using side lx to hit the actor from the front. This unexpectedly created a shadow on the cyc which turned out to be very impressive =D |
| Sharing of lights | Had problems in coordinating 半杯desk and 七彩bubble chair. Try not to share lights if possible. Remember that higher up side FOH lx (eg 19 & 31) can be used as DS sptlx too. |
| Smoke machine | Get to know the machine inside out. Tends to spout smoke even when uncalled for. Must know how to use this to ur advantage or know how to remove this problem. Warm up time is quite long. Give sufficient time to warm up and use extensions if necessary. |
| 地道灯 | Everything was theoretical since we had not tried this before. The markings of the地道灯had to be marked only after the effects of the lx were set. Had to be familiar with operating the地道灯. |
| Cyc lights / Shadow play | The final approach to making the clock tower shadow was to use a backlight to light up the area. The blue cyc effect was sacrificed to make the clock tower shadow sharp. The fighting scene used a single cyc lx to create a sharp image of the fighting. A group of cyc lights was unused even after the colour gels were slotted in. This was because the effect was wrong and to save time the colour gels were just left there. A similar colour from another剧was used instead. |
| 闹鬼backdrop | Planned to use 4 lights to light up the backdrop but this was insufficient due to the size of backdrop. In the end used 8 lx to light up the backdrop, the extra lx also used to light up the creases and make the folds less obvious. |
| Face lx | - Many positions of 半杯actors and sets do not have enough face lx. Stress once again that they cant stand too close to stage edge! - Must think thru thoroughly about usage of lx. Die die must have face lx. |
| Side lx | - Must plan before hand how the sidelx should be used. Eg sidelx to show motion should not hit the floor. However sidelx to light up an area and create mood should hit on something on stage like set or the floor. - Plan the allocation of sidelx for each side boom carefully. Some sidelx were not used and not focused at the last min even though the colour gels had been slotted in. This was due to the lack of time for focusing. Eg for the green ghostly lx in 闹鬼the number of side lx used was reduced from 6 to 3. |
| A few final words. | - You will be very stressed on the whole. But just know what u are doing and maintain a good pace of focusing n plotting. Be creative and keep an optimistic mind. - Be ready for on the spot and last minute changes. Must learn to 随机应变! GOOD LUCK! |

APPENDIX A          七彩 ACT 1

APPENDIX B    sample page of focus chart

| # Channel # | Type | ## Special | Gobo / colour gel | Focused? |
| --- | --- | --- | --- | --- |
| ### TRUSS 1 |  |  |  |  |
| 43 | profile |  | L117/ Iris |  |
| 44 | PC |  |  |  |
| 45 | scroller |  | L102 |  |
| 46 | fresnel |  |  |  |
|  | profile |  |  |  |
| 47 | profile |  | L117 |  |
| 48 | PC |  |  |  |
| 49 | scroller |  | L151 |  |
| 50 | PC |  |  |  |
| 51 | profile |  |  |  |
| 52 | PC |  |  |  |
| 53 | fresnel |  |  |  |
| 54 | PC |  |  |  |
| 55 | profile |  | L117 |  |
|  | profile |  |  |  |
| 56 | scroller |  | L102 |  |
| 57 | fresnel |  |  |  |
| 58 | PC |  |  |  |
| 59 | profile |  | L117/ Iris |  |
| TRUSS 2 |  |  |  |  |
| 77 | profile |  |  |  |
| 76 | PC |  |  |  |
| 75 | fresnel |  |  |  |
| 74 | Scroller |  | L102 |  |
| 73 | profile |  | L151 |  |
| 72 | PC |  |  |  |
| 71 | fresnel |  |  |  |
| 70 | PC |  |  |  |
| 69 | profile |  |  |  |
| 68 | PC |  |  |  |
| 67 | scroller |  | L102 |  |
| 66 | PC |  |  |  |
| 65 | profile |  |  |  |
| 64 | fresnel |  |  |  |

| MAGIC SHEET 2004 |  |  |  |
| --- | --- | --- | --- |

CYC   TOP

APPENDIX C

| 88 94 | 84 90 | 80 86. CYC Ground Row |
| --- | --- | --- |
| 70 76 | 66 72 | 62 68 163; 162; 161; 160; 159; 158; 157. Rear Projection |
| 52 58 | 48 54 | 44 50 |

# General lighting

| 12 9 | 8 5 | 4 1 |
| --- | --- | --- |

# General  FOH

半杯

| 31 21 | 32 20 | 33 19 |
| --- | --- | --- |

# FOH  Side

| 210 | 209 | 208 | 207 | 206 | 205 |
| --- | --- | --- | --- | --- | --- |
| 198 | 197 | 196 | 195 | 194 | 193 |
| 186 | 185 | 184 | 183 | 182 | 181 |
| 174 | 173 | 172 | 171 | 170 | 169 |

| 211 | 212 | 213 | 214 | 215 | 216 |
| --- | --- | --- | --- | --- | --- |
| 199 | 200 | 201 | 202 | 203 | 204 七彩 |
| 187 | 188 | 189 | 190 | 191 | 192 |
| 175 SR side boom | 176 | 177 | 178 | 179 | 180 SL side boom |

半杯

七彩

闹鬼

闹鬼

APPENDIX D    Useful Contacts

| Psyche Chui Lighting designer (HK) psyche@hkapa.edu | Victoria Theatre (call them up to book time for recce) 63388283 |
| --- | --- |
| Wong May Lan Teacher Adviser 98798101 | Chinese High (Joseph Tan) 96820725 |
| Doreen ( get your smoke machine) Technical adviser 96868793 | The Theatre Practice 63372529 |
| Zamri bin Ismail VT senior technician 96795191 | Te Deum Eng (get your gobos here!) 67420181 |