## Slide 1: Chapter 5: Project Time Management

## Slide 2: Importance of Project Schedules
Managers often cite delivering projects on time as one of their biggest challenges
Average time overrun from 1995 CHAOS report was 222%
Time has the least amount of flexibility; it passes no matter what
Schedule issues are the main reason for conflicts on projects, especially during the second half of projects

## Slide 3: Figure 5-1. Conflict Intensity Over the Life of a Project

## Slide 4: Project Time Management Processes
Project time management involves the processes required to ensure timely completion of a project. Processes include:
  Activity definition
  Activity sequencing
  Activity duration estimating
  Schedule development
  Schedule control

## Slide 5: Where Do Schedules Come From? Defining Activities
Project schedules grow out of the basic document that initiate a project
  Project charter includes start and end dates and budget information
  Scope statement and WBS help define what will be done
Activity definition involves developing a more detailed WBS and supporting explanations to understand all the work to be done

## Slide 6: Activity Sequencing
Involves reviewing activities and determining dependencies
  Mandatory dependencies: inherent in the nature of the work; hard logic
  Discretionary dependencies: defined by the project team; soft logic
  External dependencies: involve relationships between project and non-project activities
You must determine dependencies in order to use critical path analysis

## Slide 7: Project Network Diagrams
Project network diagrams are the preferred technique for showing activity sequencing
A project network diagram is a schematic display of the logical relationships among, or sequencing of, project activities

## Slide 8: Figure 5-2. Sample Activity-on-Arrow (AOA) Network Diagram for Project X

## Slide 9: Arrow Diagramming Method (ADM)
Also called activity-on-arrow (AOA) project network diagrams
Activities are represented by arrows
Nodes or circles are the starting and ending points of activities
Can only show finish-to-start dependencies

## Slide 10: Process for Creating AOA Diagrams
1. Find all of the activities that start at node 1. Draw their finish nodes and draw arrows between node 1 and those finish nodes. Put the activity letter or name and duration estimate on the associated arrow
2. Continuing drawing the network diagram, working from left to right. Look for bursts and merges. Bursts occur when a single node is followed by two or more activities. A merge occurs when two or more nodes precede a single node
3. Continue drawing the project network diagram until all activities are included on the diagram that have dependencies
4. As a rule of thumb, all arrowheads should face toward the right, and no arrows should cross on an AOA network diagram

## Slide 11: Precedence Diagramming Method (PDM)
Activities are represented by boxes
Arrows show relationships between activities
More popular than ADM method and used by project management software
Better at showing different types of dependencies

## Slide 12: Figure 5-3. Task Dependency Types

## Slide 13: Figure 5-4. Sample Precedence Diagramming Method (PDM) Network Diagram for Project X
Project 98 file

## Slide 14: Activity Duration Estimating
After defining activities and determining their sequence, the next step in time management is duration estimating
Duration includes the actual amount of time worked on an activity plus elapsed time
People doing the work should help create estimates, and an expert should review them

## Slide 15: Schedule Development
Schedule development uses results of the other time management processes to determine the start and end date of the project and its activities
Ultimate goal is to create a realistic project schedule that provides a basis for monitoring project progress for the time dimension of the project
Important tools and techniques include Gantt charts, PERT analysis, and critical path analysis

## Slide 16: Gantt Charts
Gantt charts provide a standard format for displaying project schedule information by listing project activities and their corresponding start and finish dates in a calendar format
Symbols include:
  A black diamond: milestones or significant events on a project with zero duration
  Thick black bars: summary tasks
  Lighter horizontal bars: tasks
  Arrows: dependencies between tasks

## Slide 17: Figure 5-5. Gantt Chart for Project X
Project 98 file

## Slide 18: Figure 5-6. Gantt Chart for Software Launch Project
Project 98 file

## Slide 19: Figure 5-7. Sample Tracking Gantt Chart
Project 98 file
white diamond: slipped milestone
two bars: planned and actual times

## Slide 20: Critical Path Method (CPM)
CPM is a project network analysis technique used to predict total project duration
A critical path for a project is the series of activities that determines the earliest time by which the project can be completed
The critical path is the longest path through the network diagram and has the least amount of slack or float

## Slide 21: Finding the Critical Path
First develop a good project network diagram
Add the durations for all activities on each path through the project network diagram
The longest path is the critical path

## Slide 22: Simple Example of Determining the Critical Path
Consider the following project network diagram. Assume all times are in days.
a. How many paths are on this network diagram?
b. How long is each path?
c. Which is the critical path?
d. What is the shortest amount of time needed to complete this project?

## Slide 23: Figure 5-8. Determining the Critical Path for Project X

## Slide 24: Class Activity
Get a partner
Do Exercise 2, p. 136

## Slide 25: More on the Critical Path
If one of more activities on the critical path takes longer than planned, the whole project schedule will slip unless corrective action is taken
Misconceptions:
  The critical path is not the one with all the critical activities; it only accounts for time
  There can be more than one critical path if the lengths of two or more paths are the same
  The critical path can change as the project progresses

## Slide 26: Using Critical Path Analysis to Make Schedule Trade-offs
Knowing the critical path helps you make schedule trade-offs
Free slack or free float is the amount of time an activity can be delayed without delaying the early start of any immediately following activities
Total slack or total float is the amount of time an activity may be delayed from its early start without delaying the planned project finish date

## Slide 27: Table 5-1. Free and Total Float or Slack for Project X

## Slide 28: Techniques for Shortening a Project Schedule
Shortening durations of critical tasks for adding more resources or changing their scope
Crashing tasks by obtaining the greatest amount of schedule compression for the least incremental cost
Fast tracking tasks by doing them in parallel or overlapping them

## Slide 29: Shortening Project Schedules
Overlapped
tasks
Shortened duration
Original
schedule

## Slide 30: Many Horror Stories Related to Project Schedules
See “What Went Wrong?” example about the National Insurance Recording System
Creating realistic schedules and sticking to them is a key challenge of project management

## Slide 31: Importance of Updating Critical Path Data
It is important to update project schedule information
The critical path may change as you enter actual start and finish dates
If you know the project completion date will slip, negotiate with the project sponsor

## Slide 32: Program Evaluation and Review Technique (PERT)
PERT is a network analysis technique used to estimate project duration when there is a high degree of uncertainty about the individual activity duration estimates
PERT uses probabilistic time estimates based on using optimistic, most likely, and pessimistic estimates of activity durations

## Slide 33: PERT Formula and Example
PERT weighted average formula:
optimistic time + 4X most likely time + pessimistic time
6
Example:
PERT weighted average =
8 workdays + 4 X 10 workdays + 24 workdays = 12 days 6
where 8 = optimistic time, 10 = most likely time, and 24 = pessimistic time

## Slide 34: Controlling Changes to the Project Schedule
Perform reality checks on schedules
Allow for contingencies
Don’t plan for everyone to work at 100% capacity all the time
Hold progress meetings with stakeholders and be clear and honest in communicating schedule issues

## Slide 35: Working with People Issues
Strong leadership helps projects succeed more than good PERT charts
Project managers should use
  empowerment
  incentives
  discipline
  negotiation

## Slide 36: What Went Right?
Chris Higgins used the discipline he learned in the Army to transform project management into a cultural force at Bank of America. Higgins learned that taking time on the front end of a project can save significant time and money on the back end. As a quartermaster in the Army, when Higgins' people had to pack tents, he devised a contest to find the best way to fold a tent and determine the precise spots to place the pegs and equipment for the quickest possible assembly. Higgins used the same approach when he led an interstate banking initiative to integrate incompatible check processing, checking account, and savings account platforms in various states.
Law mandated that the banks solve the problem in one year or less. Higgins' project team was pushing to get to the coding phase of the project quickly, but Higgins held them back. He made the team members analyze, plan, and document requirements for the system in such detail that it took six months just to complete that phase. But the discipline up front enabled the software developers on the team to do all of the coding in only three months, and the project was completed on time.

## Slide 37: Using Software to Assist in Time Management
Software for facilitating communications helps people exchange schedule-related information
Decision support models help analyze trade-offs that can be made
Project management software can help in various time management areas

## Slide 38: Table 5-2. Project 98 Features Related to Project Time Management

## Slide 39: Words of Caution on Using Project Management Software
Many people misuse project management software because they don’t understand important concepts and have not had good training
You must enter dependencies to have dates adjust automatically and to determine the critical path
You must enter actual schedule information to compare planned and actual progress

## Slide 40: Discussion Questions
Why do you think schedule issues often cause the most conflicts on projects?
Explain as clearly as possible what a critical path is and why a project manager should be concerned about it.
What skills of a project manager described earlier do you think are most important for time management?