## Slide 1: Chapter 1: Introduction to Project Management

## Slide 2: Motivation for Studying Information Technology (IT) Project Management
IT Projects have a terrible track record
  A 1995 Standish Group study found that only 16.2% of IT projects were successful
  Over 31% of IT projects were canceled before completion, costing over $81 B in the U.S. alone
A 1999 ComputerWorld article listed project manager as the #1 position IT managers say they need most for contract help
The need for IT projects keeps increasing
Companies in general are emphasizing projects

## Slide 3: What Is a Project?
A project is a temporary endeavor undertaken to accomplish a unique purpose
Attributes of projects
  unique purpose
  temporary
  require resources, often from various areas
  should have a primary sponsor and/or customer
  involve uncertainty

## Slide 4: Samples of Projects
Northwest Airlines developed a new reservation system called ResNet (see chapters 11-16)
Bank of America created a system to integrate check processing, checking accounts, and savings accounts in various states (p. 130)
Kodak created the Advantix Advanced Photo System in one of their most ambitious projects ever (p. 302)

## Slide 5: Projects I’ve Worked On
Writing this book!
Writing a web-based CBT course
Starting a new academic program
Purchasing a risk management system for an oil company
Starting a new internal consulting group
Managing a beta test for new software
The National Aerospace Plane Project
The High Reliability Fighter Project
The Local Online Network System Project
etc., etc., etc.

## Slide 6: The Triple Constraint
Every project is constrained in different ways by its
  Scope goals
  Time goals
  Cost goals
It is the project manager’s duty to balance these three often competing goals

## Slide 7: Figure 1-1. The Triple Constraint of Project Management

## Slide 8: Exercise on the Triple Constraint
Pair up and instructor assign roles
“Player” describe in your own words what the triple constraint really means, then give an example of it on a real project you’re familiar with
“Coach” listen and ask questions, then be ready to share what your partner said
Was the project “successful?” Why or why not?

## Slide 9: What is Project Management?
Project management is “the application of knowledge, skills, tools, and techniques to project activities in order to meet or exceed stakeholder needs and expectations from a project” (PMI*, Project Management Body of Knowledge (PMBOK Guide), 1996, p. 6)
*The Project Management Institute (PMI) is an international professional society. Their web site is www.pmi.org. Over 315,000 copies of the PMBOK Guide were in circulation by June 1999.

## Slide 10: Figure 1-2. Project Management Framework
T
T

## Slide 11: Project Stakeholders
Stakeholders are the people involved in or affected by project activities
Stakeholders include
  the project sponsor and project team
  support staff
  customers
  users
  suppliers
  opponents to the project

## Slide 12: 9 Project Management Knowledge Areas
Knowledge areas describe the key competencies that project managers must develop
  4 core knowledge areas lead to specific project objectives (scope, time, cost, and quality)
  4 facilitating knowledge areas are the means through which the project objectives are achieved (human resources, communication, risk, and procurement management)
  1 knowledge area (project integration management) affects and is affected by all of the other knowledge areas

## Slide 13: Project Management Tools and Techniques
Project management tools and techniques assist project managers and their teams in various aspects of project management
Some specific ones include
  Project Charter and WBS (scope)
  Gantt charts, PERT charts, critical path analysis (time)
  Cost estimates and Earned Value Analysis (cost)

## Slide 14: Sample WBS for Intranet Project in Chart Form

## Slide 15: Figure 1-4. Sample Gantt Chart*
*This template file comes with Project 98
WBS
Gantt Chart

## Slide 16: Figure 1-5. Sample PERT Chart
Each box is a project task from the WBS. Arrows show dependencies
between tasks. The tasks in red are on the critical path. If any tasks on the
critical path take longer than planned, the whole project will slip
unless something is done.

## Slide 17
Sample Earned Value Chart

## Slide 18: Advantages of Project Management*
Bosses, customers, and other stakeholders do not like surprises
Good project management (PM) provides assurance and reduces risk
PM provides the tools and environment to plan, monitor, track, and manage schedules, resources, costs, and quality
PM provides a history or metrics base for future planning as well as good documentation
Project members learn and grow by working in a cross-functional team environment
*Source: Knutson, Joan, PM Network, December 1997, p. 13

## Slide 19: How Project Management (PM) Relates to Other Disciplines
Much of the knowledge needed to manage projects is unique to PM
However, project managers must also have knowledge and experience in
  general management
  the application area of the project
Project managers must focus on meeting specific project objectives

## Slide 20: Figure 1-3. Project Management and Other Disciplines

## Slide 21: History of Project Management*
Modern project management began with the Manhattan Project, which the U.S. military led to develop the atomic bomb
In 1917 Henry Gantt developed the Gantt chart as a tool for scheduling work in job shops
In 1958, the Navy developed PERT charts
In the 1970s, the military began using project management software, as did the construction industry
By the 1990s, virtually every industry was using some form of project management
* August 1999 PM Network has good articles on history of PM

## Slide 22: The Project Management Profession
A 1996 Fortune article called project management the “number one career choice”
Other authors like Tom Peters and Thomas Stewart stress that projects are what add value to organizations
Professional societies like the Project Management Institute have grown tremendously

## Slide 23: Project Management Certification
PMI provides certification as a Project Management Professional (PMP)
A PMP has documented sufficient project experience, agreed to follow a code of ethics, and passed the PMP exam
The number of people earning PMP certification is increasing quickly
Other groups, like the Gartner Group and the Singapore Computer Society, have their own IT PM Certification programs

## Slide 24: Figure 1-6. Growth in PMP Certification, 1993-1998
Over 12,500
by May 1999

## Slide 25: Code of Ethics
PMI developed a project management code of ethics that all PMPs must agree to abide by
Conducting work in an ethical manner helps the profession earn confidence
Ethics are on the web at www.pmi.org/certification/code.htm

## Slide 26: Discussion Questions
Give three examples of activities that are projects and three examples of activities that are not projects
How is project management different from general management?
Why do you think so many projects are unsuccessful?
Is a high failure rate unique to certain types of projects, like IT projects?