## Slide 1: Chapter 6: Project Cost Management

## Slide 2: The Importance of Project Cost Management
IT projects have a poor track record for meeting cost goals
Average cost overrun was 189% of the original estimates
In 1995, cancelled IT projects cost the U.S. over $81 billion

## Slide 3: What Went Wrong?
According to the San Francisco Chronicle front-page story, "Computer Bumbling Costs the State $1 Billion," the state of California had a series of expensive IT project failures in the late 1990s, costing taxpayers nearly $1 billion. Some of the poorly managed projects included the Department of Motor Vehicles vehicle registration and driver's license databases, a statewide child support database, the State Automated Welfare System, and a Department of Corrections system for tracking inmates. Senator John Vasconcellos thought it was ironic that the state which leads in creation of computers is the state most behind in using computer technology to improve state services.
Also consider the Internal Revenue Service's expensive reengineering and IT project failures. The Internal Revenue Service (IRS) managed a series of project failures that cost taxpayers over $50 billion a year—roughly as much money as the annual net profit of the entire computer industry.

## Slide 4: What is Cost and Project Cost Management?
Cost is a resource sacrificed or fore-gone to achieve a specific objective or something given up in exchange
Costs are usually measured in monetary units like dollars
Project cost management includes the processes required to ensure that the project is completed within an approved budget

## Slide 5: Project Cost Management Processes
Resource planning: determining what resources and quantities of them should be used
Cost estimating: developing an estimate of the costs and resources needed to complete a project
Cost budgeting: allocating the overall cost estimate to individual work items to establish a baseline for measuring performance
Cost control: controlling changes to the project budget

## Slide 6: Quick Quiz on Cost Concepts
Suppose you sell 10 widgets per day on average, and the average cost per widget is $10. If you sold 11 widgets on day, what would the affect on profits be?
Suppose you were buying 10 PCs for your new business. What would some of the life cycle costs be?
Give examples of “tangible” vs. “intangible” benefits of a new project

## Slide 7: Basic Principles of Cost Management
Most CEOs and boards know a lot more about finance than IT, IT project managers must speak their language
  Profits are revenues minus expenses
  Life cycle costing is estimating the cost of a project over its entire life
  Cash flow analysis is determining the estimated annual costs and benefits for a project
  Benefits and costs can be tangible or intangible, direct or indirect
  Sunk cost should not be a criteria in project selection

## Slide 8: Table 6-1. Cost of Software Defects
It is important to spend money up-front on IT
projects to avoid spending a lot more later.

## Slide 9: What Went Right?
Ford Motor Company had great success with its Taurus/Sable project. Ford excels in team product development and seeks to remove barriers among design, engineering, production, marketing, sales, and purchasing. However, the Taurus team went far beyond that by creating a car that excelled in design and quality at half the typical development cost. They brought together all the relevant disciplines as a team and took the various steps in designing, producing, marketing, and selling the cars simultaneously as well as sequentially. Ford even included people outside the company for advice—car dealerships, insurance companies, and suppliers. One supplier even offered the services of its own drafting department to prepare initial designs for Ford's approval. Bringing together all the key players provided extremely valuable ideas at the conceptual stage, when changes can be made without much extra cost. "Not only were there substantial savings in cost and design time, but major production contracts were being negotiated and set up some three years ahead of production, with the duration of the contract some five years. This also led to cost economies."

## Slide 10: Resource Planning
The nature of the project and the organization will affect resource planning
Some questions to consider:
  How difficult will it be to do specific tasks on the project?
  Is there anything unique in this project’s scope statement that will affect resources?
  What is the organization’s history in doing similar tasks?
  Does the organization have or can they acquire the people, equipment, and materials that are capable and available for performing the work?

## Slide 11: Cost Estimating
An important output of project cost management is a cost estimate
There are several types of cost estimates and tools and techniques to help create them
It is also important to develop a cost management plan that describes how cost variances will be managed on the project

## Slide 12: Table 6-2. Types of Cost Estimates

## Slide 13: Cost Estimation Tools and Techniques
4 basic tools and techniques for cost estimates:
  analogous or top-down: use the actual cost of a previous, similar project as the basis for the new estimate
  bottom-up: estimate individual work items and sum them to get a total estimate
  parametric: use project characteristics in a mathematical model to estimate costs
  computerized tools: use spreadsheets, project management software, or other software to help estimate costs

## Slide 14: Constructive Cost Model (COCOMO)
Barry Boehm helped develop the COCOMO models for estimating software development costs
Parameters include source lines of code or function points
COCOMO II is a computerized model available on the web
Boehm suggest that only parametric models do not suffer from the limits of human decision-making

## Slide 15: Typical Problems with IT Cost Estimates
Developing an estimate for a large software project is a complex task requiring a significant amount of effort. Remember that estimates are done at various stages of the project
Many people doing estimates have little experience doing them. Try to provide training and mentoring
People have a bias toward underestimation. Review estimates and ask important questions to make sure estimates are not biased
Management wants a number for a bid, not a real estimate. Project managers must negotiate with project sponsors to create realistic cost estimates

## Slide 16: Table 6-3. Business Systems Replacement Project Cost Estimate Overview

## Slide 17: Table 6-4. Business Systems Replacement Project Cash Flow Analysis

## Slide 18: Cost Budgeting
Cost budget involves allocating the project cost estimate to individual work items and providing a cost baseline
For example, in the Business Systems Replacement project, there was a total purchased costs estimate for FY97 of $600,000 and another $1.2 million for Information Services and Technology
These amounts were allocated to appropriate budgets as shown in Table 6-5

## Slide 19: Table 6-5. Business Systems Replacement Project Budget Estimates for FY97 and Explanations

## Slide 20: Cost Control
Project cost control includes
  monitoring cost performance
  ensuring that only appropriate project changes are included in a revised cost baseline
  informing project stakeholders of authorized changes to the project that will affect costs
Earned value analysis is an important tool for cost control

## Slide 21: Earned Value Analysis (EVA)
EVA is a project performance measurement technique that integrates scope, time, and cost data
Given a baseline (original plan plus approved changes), you can determine how well the project is meeting its goals
You must enter actual information periodically to use EVA. Figure 6-1 shows a sample form for collecting information

## Slide 22: Figure 6-1. Cost Control Input Form for Business Systems Replacement Project

## Slide 23: Earned Value Analysis Terms
Budgeted cost of work scheduled (BCWS), also called the budget, is that portion of the approved total cost estimate planned to be spent on an activity during a given period
Actual cost of work performed (ACWP), also called actual cost, are the total direct and indirect costs incurred in accomplishing work on an activity during a given period
Budgeted cost of work performed (BCWP), also called earned value, is the percentage of work actually completed multiplied by the planned cost (or BCWS)

## Slide 24: Table 6-6. Earned Value Calculations for One Activity After Week One

## Slide 25: Table 6-7. Earned Value Formulas

## Slide 26: Rules of Thumb for EVA Numbers
Negative numbers for cost and schedule variance indicate problems in those areas. The project is costing more than planned or taking longer than planned
CPI and SPI less than 100% indicate problems

## Slide 27: Class Activity
Get a partner
Do Exercise 1, p. 169

## Slide 28: Figure 6-2. Earned Value Calculations for a One-Year Project After Five Months
Excel file

## Slide 29: Figure 6-3. Earned Value Chart for Project After Five Months
Excel file
EAC

## Slide 30: Using Software to Assist in Cost Management
Spreadsheets are a common tool for resource planning, cost estimating, cost budgeting, and cost control
Many companies use more sophisticated and centralized financial applications software for cost information
Project management software has many cost-related features

## Slide 31: Discussion Questions
Do most colleges and companies provide adequate education and training in cost management for IT project managers? Give examples to support your answer.
Give an example of using the following techniques for creating a cost estimate: analogous, parametric, bottom-up, and computerized tools.
What is earned value analysis? Why is it the preferred method for measuring project performance? Why isn't it used more often?