## Slide 1: Chapter 3: Project Integration Management

## Slide 2: Opening Case
Nick Carson was recently made project manager of a critical biotech project for his company in Silicon Valley. This project involved creating the hardware and software for a DNA sequencing instrument used in assembling the human genome. Each instrument sold for approximately $200,000, and various sites would purchase several instruments. One hundred instruments running 24 hours per day could decipher the entire human genome in less than two years. The biotech project was the company's largest project, and it had tremendous potential for future growth and revenues. Unfortunately, there were problems managing this large project. It had been underway for three years and had already gone through three different project managers. Nick had been the lead software developer on the project before senior management made him project manager. Senior management told him to do whatever it took to deliver the first version of the software for the DNA sequencing instrument in four months and a production version in nine months. Their urgency in getting the project out was influenced by negotiations for a potential corporate buy-out with a larger company.

## Slide 3: Opening Case (cont’d)
Nick was highly energetic and intelligent and had the technical background to make the project a success. He delved into the technical problems and found some critical flaws that were key in getting the DNA sequencing instrument to work. He was having difficulty, however, in his new role as project manager. Although Nick and his team got the product out on time, senior management was upset because Nick did not focus on managing. He never provided management with accurate schedules or detailed task lists of what was happening on the project. Instead of performing the work of project manager, Nick had taken on the role of software integrator and troubleshooter. Nick, however, did not understand senior management’s problem—he delivered the product, didn’t he? Didn't they realize how valuable he was?

## Slide 4: Discussion Questions
What do you think was the real problem in this case?
Was Nick a good project manager? Why or why not?
What could Nick have done to be a better project manager?
What should senior management have done to help Nick?

## Slide 5: The Key to Overall Project Success: Good Project Integration Management
Project managers must coordinate all of the other knowledge areas throughout a project’s life cycle
Many new project managers have trouble looking at the “big picture” and want to focus on too many details

## Slide 6: Project Integration Management Processes
Project Plan Development: taking the results of other planning processes and putting them into a consistent, coherent document—the project plan
Project Plan Execution: carrying out the project plan
Overall Change Control: coordinating changes across the entire project

## Slide 7: Figure 3-1. Framework for Project Integration Management

## Slide 8: Interface Management
Interface management involves identifying and managing the points of interaction between various elements of the project
Project managers must establish and maintain good communication and relationships across organizational interfaces

## Slide 9: Project Plan Development
A project plan is a document used to coordinate all project planning documents
Its main purpose is to guide project execution
Project plans assist the project manager in leading the project team and assessing project status

## Slide 10: Attributes of Project Plans
Just as projects are unique, so are project plans
Plans should be dynamic
Plans should be flexible
Plans should be updated as changes occur
Plans should first and foremost guide project execution

## Slide 11: Common Elements of a Project Plan
Introduction or overview of the project
Description of how the project is organized
Management and technical processes used on the project
Work to be done, schedule, and budget information

## Slide 12: Table 3-1. Sample Outline for a Software Project Management Plan (SPMP)

## Slide 13: Stakeholder Analysis
A stakeholder analysis documents important (often sensitive) information about stakeholders such as
  stakeholders’ names and organizations
  roles on the project
  unique facts about stakeholders
  level of influence and interest in the project
  suggestions for managing relationships

## Slide 14: Table 3-2. Sample Stakeholder Analysis

## Slide 15: Project Plan Execution
Project plan execution involves managing and performing the work described in the project plan
The majority of time and money is usually spent on execution
The application area or the project directly affects project execution because the products of the project are produced during execution

## Slide 16: What Went Wrong?
Many people have a poor view of plans based on past experiences. Senior managers often require a plan, but then no one follows up on whether the plan was followed.
For example, one project manager said he would meet with each project team leader within two months to review their plans. The project manager created a detailed schedule for these reviews. He cancelled the first meeting due to another business commitment. He rescheduled the next meeting for unexplained personal reasons. Two months later, the project manager had still not met with over half of the project team leaders.
Why should project members feel obligated to follow their own plans when the project manager obviously did not follow his?

## Slide 17: Important Skills for Project Execution
General management skills like leadership, communication, and political skills
Product skills and knowledge (see example of “What Went Right?”)
Use of specialized tools and techniques

## Slide 18: Tools and Techniques for Project Execution
Work Authorization System: provides a method for ensuring that qualified people do work at the right time and in the proper sequence
Status Review Meetings: regularly scheduled meetings used to exchange project information
Project Management Software: special software to assist in managing projects

## Slide 19: Overall Change Control
Overall change control involves identifying, evaluating, and managing changes throughout the project life cycle
Three main objectives of change control:
  Influence the factors that create changes to ensure they are beneficial
  Determine that a change has occurred
  Manage actual changes when and as they occur

## Slide 20: Figure 3-2. Overall Change Control Process

## Slide 21: Change Control on Information Technology Projects
Former view: The project team should strive to do exactly what was planned on time and within budget
Problem: Stakeholders rarely agreed up-front on the project scope, and time and cost estimates were inaccurate
Modern view: Project management is a process of constant communication and negotiation
Solution: Changes are often beneficial, and the project team should plan for them

## Slide 22: Change Control System
A formal, documented process that describes when and how official project documents and work may be changed
Describes who is authorized to make changes and how to make them
Often includes a change control board (CCB), configuration management, and a process for communicating changes

## Slide 23: Change Control Boards (CCBs)
A formal group of people responsible for approving or rejecting changes on a project
Provides guidelines for preparing change requests, evaluates them, and manages the implementation of approved changes
Includes stakeholders from the entire organization

## Slide 24: Making Timely Changes
Some CCBs only meet occasionally, so it may take too long for changes to occur
Some organizations have policies in place for time-sensitive changes
  “48 hour policy” allowed project team members to make decisions, then they had 48 hours reverse the decision pending senior management approval

## Slide 25: Configuration Management
Ensures that the products and their descriptions are correct and complete
Concentrates on the management of technology by identifying and controlling the functional and physical design characteristics of products
Configuration management specialists identify and document configuration requirements, control changes, record and report changes, and audit the products to verify conformance to requirements

## Slide 26: Table 3-3. Suggestions for Managing Overall Change Control
    View project management as a process of constant communications and negotiations
    Plan for change
    Establish a formal change control system, including a Change Control Board (CCB)
    Use good configuration management
    Define procedures for making timely decisions on smaller changes
    Use written and oral performance reports to help identify and manage change
    Use project management and other software to help manage and communicate changes

## Slide 27: Need for Top Management Commitment
Several studies cite top management commitment as one of the key factors associated with project success
Top management can help project managers secure adequate resources, get approval for unique project needs in a timely manner, receive cooperation from people throughout the organization, and learn how to be better leaders

## Slide 28: Table 3-4. What Helps Projects Succeed?
1987 Pinto and Slevin
Clear project mission
Top management support
Good project schedule/plan
Good client consultation
1995 Standish Group
User involvement
Executive management support
Clear statement of requirements
Proper planning

## Slide 29: Need for Organizational Commitment to Information Technology (IT)
If the organization has a negative attitude toward IT, it will be difficult for an IT project to succeed
Having a Chief Information Officer (CIO) at a high level in the organization helps IT projects
Assigning non-IT people to IT projects also encourage more commitment

## Slide 30: Need for Organizational Standards
Standards and guidelines help project managers be more effective
Senior management can encourage
  the use of standard forms and software for project management
  the development and use of guidelines for writing project plans or providing status information
  the creation of a project management office or center of excellence

## Slide 31: Discussion Questions
What are crucial elements of successful project plan execution? Describe a well-executed project you are familiar with. Describe a disaster. What were some of the main differences between these projects?
Discuss the importance of top management commitment and the development of standards for successful project management. Give examples of projects that failed due to a lack of top management commitment and a lack of organizational standards.