## Slide 1: Standard Work Breakdown Structure
Legend
= Decomposes to lower level WBS elements
4.0
Implementation
3.0
Solution Development
1.0
Mission Analysis
2.0
Investment Analysis
6.0
Disposition
5.0
In-Service Management
Project Specific Activities
Pre-Project Activities
Standard Work Breakdown Structure (WBS)

## Slide 2: WBS Element 1.0 Mission Analysis
1.0
Mission Analysis
1.1
Identify Projected Demand for Services
1.2
Identify Technological Opportunities
1.3
Identify Projected Supply of Services
1.4
Mission Needs Analysis and Assessment

## Slide 3: WBS Element 2.0 Investment Analysis
2.0
Investment Analysis
2.1
Requirements Definition
2.1.1
Initial Requirements Definition
2.1.2
Finalize Requirements
2.2
Alternatives Identification and Analysis
2.2.1
Alternatives Identification
2.2.2
Alternatives Analysis

## Slide 4: WBS Element 3.0 Solution Development
3.0
Solution Development
3.1
Program Management
3.2
System Engineering
3.3
HW / SW Design, Development and Production
3.5
Test and Evaluation
3.6
Documentation
Legend
= Decomposes to lower level WBS elements
3.7
Support
3.4
Facilities and Physical Infrastructure Design and Development

## Slide 5: WBS Element 3.1 Program Management
3.1
Program Management
3.1.1
Work Planning, Authorization and Management
3.1.2
Program Control
3.1.3
Contract Management

## Slide 6: WBS Element 3.2 System Engineering
3.2
System Engineering
3.2.1
System Requirements and Definition
3.2.2
Analysis, Design, and Integration
3.2.3
Value Engineering
3.2.4
Supportability, Maintainability, and Reliability Engineering
3.2.5
Quality Assurance Program
3.2.6
Configuration Management
3.2.7
Human Factors
3.2.8
Security

## Slide 7: WBS Element 3.3 HW/SW Design, Development and Production
3.3
HW/SW Design, Development and Production
3.3.1
Hardware
Design and Development
3.3.2
Software Design and Development
3.3.3
HW/SW Integration, Assembly, Test and Checkout
3.3.5
Production
3.3.4
Production Engineering

## Slide 8: WBS Element 3.4 Facilities and Physical Infrastructure Design and Development
3.4
Facilities and Physical Infrastructure Design and Development
3.4.1
Facility Planning and Design
3.4.2
Real Estate
3.4.3
Physical Infrastructure

## Slide 9: WBS Element 3.5 Test and Evaluation
3.5
Test and Evaluation
3.5.1
System Development Test and Evaluation
3.5.2
System Operational Test and Evaluation
3.5.3
System Independent Software Verification and Validation
3.5.5
Independent Operational Test and Evaluation
3.5.4
Site Acceptance Testing

## Slide 10: WBS Element 3.7 Support
3.7
Support
3.7.2
Test and Measurement Equipment Acquisition
3.7.3
Support and Handling Equipment Acquisition
3.7.4
Support
Facilities Construction / Conversion / Expansion
3.7.5
Support Equipment Acquisition / Modification
3.7.6
Support Facilities and Equipment Maintenance
3.7.7
Initial Spares and Repair Parts Acquisition
3.7.8
Initial Training
3.7.1
Logistics Support Planning

## Slide 11: WBS Element 4.0 Implementation
4.0
Implementation
Legend
= Decomposes to lower level WBS elements
4.1
Program Management
4.6
Installation and Checkout
4.7
Commissioning / Closeout
4.8
Telecommunications
4.9
Implementation Training
4.2
Engineering
4.3
Environmental and Occupational Safety and Health Compliance
4.4
Site Selection and Acquisition
4.5
Construction

## Slide 12: WBS Element 4.1 Program Management
4.1
Program Management
4.1.1
Work Planning, Authorization and Management
4.1.2
Program Control
4.1.3
Contract Management

## Slide 13: WBS Element 5.0 In-Service Management
5.0
In-Service Management
5.3
Modifications
5.5
Technical Teaming
5.2
Corrective Maintenance
5.1
Preventive Maintenance / Certification
5.4
Maintenance Control
5.6
Shift Augmentation
5.8
Logistics
5.7
Program Support
5.9
In-Service Training
Legend
= Decomposes to lower level WBS elements
5.10
Second Level Engineering
5.11
Infrastructure Support
5.12
Flight Inspections and SIAP Development
5.13
System Performance Assessment
5.14
System Operations

## Slide 14: WBS Element 5.7 Program Support
5.7
Program Support
5.7.1
Work Planning, Authorization and Management
5.7.2
Program Control
5.7.3
Contract Management

## Slide 15: WBS Element 5.8 Logistics
5.8
Logistics
5.8.1
Supply Support
5.8.2
Repair
5.8.3
Support Equipment Maintenance
5.8.4
Warranty Tracking

## Slide 16: WBS Element 5.11 Infrastructure Support
5.11
Infrastructure Support
5.11.1
Hazardous Materials Handling
5.11.2
Utilities, Building and Grounds Upkeep and Maintenance
5.11.4
Building and Infrastructure Improvements
5.11.3
Telecommunications
5.11.5
Real Estate Acquisition and Management

## Slide 17: WBS Element 6.0 Disposition
6.0
Disposition
6.1
Program Management
6.2
Decommissioning
6.3
Engineering
6.4
Environmental
6.5
Dismantle / Removal
6.6
Site Restoration / Closeout