## Slide 1
Earned Value Management Systems (EVMS)
Project Management Institute Washington, DC Chapter
Presented By
Sean Alexander
(703) 503-5000 or (888) 860-0700
salex@meridianet.com
Basic Concepts

## Slide 2
Wisdom of the Ages
“It must be remembered that there is nothing more difficult to plan, more doubtful of success, more dangerous to manage, than the creation of a new system. For the initiator has the enmity of all who would profit by the preservation of the old institutions and merely lukewarm defenders in those who would gain by the new ones.
— Niccolo Machiavelli

## Slide 3
EVMS Objectives
Plan all work prior to beginning it;
Measure performance based on an objective set of technical criteria;
Analyze schedule status and projections using a time phased CPM network;
Analyze the expenditure of funds in light of the work accomplished (not work scheduled);

## Slide 4
EVMS Objectives [continued]
Isolate problems:
  Quantify technical problems within the context of cost and schedule parameters;
  Not aimed at replacing or changing the process for technical problem detection;
Forecast completion date and final cost;
Take corrective action;
Maintain disciplined control of the performance measurement baseline.

## Slide 5
Earned Value Management: How Did It Come About?
1959 PERT and PERT/Cost — Milestone Charts And Rate-of Expenditure Curves — Dollars Spent Vs Estimates Of Percent Complete (DD 1097)
1963 Earned Value Concept (MINUTEMAN)
1964 Cost Accomplishment Concept (TITAN III)
1966 AF—Cost/schedule Planning And Control Specification (C/SPCS)
1967 DOD—Cost/Schedule Control Systems Criteria (C/SCSC) (DODI 7000.2)
1972 DOD—-Revised DODI 7000.2 and Issued the Joint Implementation Guide (JIG)
1972 NASA Marshall Space Flight Center—C/SPC
1975 DOE—Performance Measurement System (PMS)
1976 DOD—Revised the C/SCSC JIG
1980 DOD—Revised the C/SCSC JIG
1982 National Security Agency—Earned Value
1983 NASA—Goddard Space Flight Center—PMS
1984 FAA & NASA Lewis Research Center—PMS
1985 NASA Johnson Space Flight Center—PMS
1987 DOD—Revised DOD C/SCSC JIG
1988 NASA Marshall SFC—Revised PMS (MMI 8020.7C, 44 Criteria)
1989 Australian DOD—DODI 7000.2
1990 Canadian DOD—PMS
1991 DODI 5000.2 replaces DODI 7000.2
1992 National Oceanic And Atmospheric Administration (NOAA)—PMS
1993 Swedish FMV—C/SCSC
1994 Internal Revenue Service (IRS)—C/SCSC
1994 Federal Bureau Of Investigation (FBI) —C/SCSC
1996 DODR 5000.2-R replaces DODI 5000.2 C/SCSC revised from 35 to 32 criteria
1996 Revised JIG—Renamed Earned Value Management Implementation Guide (EVMIG)
1997 EVMIG Revised
1998 MIL-STD 881B replaced by MIL HDBK 881

## Slide 6
The Eight Subsystems of EVMS
Organization
Scheduling
Budgeting
Work Authorization
Data Accumulation and Reporting
Variance Analysis
Estimate At Completion
Baseline Maintenance and Control

## Slide 7
Budget Structure
Negotiated Changes
Written Change Authorization, Not Negotiated
Profit/Fee
Contract Cost
Authorized, Unpriced Work
Distributed Budget
[S of all CAs]
Undistributed Budget
Management Reserve
Performance Measurement Baseline (PMB)
Contract Budget Base
(CBB)
Contract

## Slide 8
Earned Value Terminology
Data Element
Term
Acronym
Scheduled Work
Budgeted Cost for Work Scheduled
BCWS
Earned Value
Budgeted Cost for Work Performed
BCWP
Actuals
Actual Cost of Work Performed
ACWP
Authorized Work
Budget At Completion
BAC
Forecasted Cost
Estimate At Completion
EAC
Work Variance
Schedule Variance
SV
Cost Variance
Cost Variance
CV
Completion Variance
Variance At Completion
VAC

## Slide 9
Earned Value Data Elements
T/N
Cost Variance
Schedule Variance
Projected
Program
Delay
VAC
EAC
BAC (PMB)
CBB
MR
ACWP
BCWP
BCWS
ETC
Schedule Slip

## Slide 10
Where Are We Going?
"Cheshire-Puss," she began, rather timidly, "Would you tell me, please, which way I ought to go from here?"
"That depends a great deal on where you want to get to," said the cat.
"I don't much care where -," said Alice.
"Then it doesn't matter which way you go," said the cat.
- Lewis Carroll
Alice in Wonderland

## Slide 11
Control Account
Software Engineering
CWBS/OBS Integration
Work
Packages
Planning
Packages
OBS DATA SUMMARIZATION
SOFTWARE
INTEGRATION
PROGRAM
Product Development
Master Planning
Ada
Products
Software Tools
Standards
CPCI #1
MOS
CPCI #2
MOLE
CPCI #3
MAC
Ada
Study
Ada
Conversion
Ada
Approach
Ada
Applications
Secure Systems
LAN Applications
Marketing
BCWS BCWP
ACWP BAC EAC
FUNCTIONAL
ORGANIZATION
CWBS
EXTENSION
SELECTED
REPORTING
ELEMENTS
SELECTED
PSWBS
ELEMENTS
Hardware Engineering
Engineering
Operations
WBS
DATA
SUMMAR
I
ZAT
I
ON
VP/GM
Control Account
Control Account
Control Account
Control Account
Control Account

## Slide 12
Control Account Elements
Work Packages
Detailed, short-span tasks, or material items, required to accomplish the CA objectives, typically in the near term
Task 1
Task 2
Task 4
Task 5
Task 3
Work Packages
Planning Packages
Planning Packages
Future work that has not been detail planned as work packages. They are always scheduled to occur in the future.

## Slide 13
Earned Value Techniques
A predetermined amount of value, i.e., budget, that is claimed, or earned, when the corre-sponding work is accomplished. The budget value is earned in one of the following ways:
0/100
X/Y Percent
  25/75
  40/60
  50/50
Milestone Weights
Milestone Weights with Percent Complete
% Complete
  Subjective Estimate
  Objective Indicators
Apportioned Effort
Level of Effort

## Slide 14
Budgets v. Funds

## Slide 15
BCWS v. ETC
Budgeted Cost for Work Scheduled (BCWS)
  Time phased budget spread of required resources for the entire task.
  Forms the Performance Measurement Baseline (PMB).
Estimate To Complete (ETC)
  Funding required to complete remaining work.
  When added to ACWP, it results in the EAC.

## Slide 16
EAC
The Plan (BCWS) and the ETC
BCWS
ETC
BAC/
The BCWS & BAC represent the work. The ETC & EAC represent the funds (i.e., money) required for that work.

## Slide 17
BAC v. EAC
Budget At Completion (BAC)
  Budgetary number representing ALL authorized work (i.e., the SOW).
  Cannot change without a change to the SOW, or appropriate approval.
Estimate At Completion (EAC)
  Funding number representing ALL the money that will be spent.
  Can change without a commensurate change to the SOW.

## Slide 18
Budget v. Funds
Budget
A number written on a piece of paper
Cannot be spent
BCWS
BCWP
BAC
Funds
Actuals
Expenditures & estimates of future spending
ETC
ACWP
EAC

## Slide 19
P
CUM
Data Analysis Relationships
Term
Formula
Percent Complete
Cost Performance Index
or Performance Factor
Checklist Actions
Ratio of work accomplished in terms of the total amount of work to do.
Symbol
% Done
CPI or PF
TCPI or VF
BCWP
BAC
Average Performance
BCWPcum
Duration (wks or mos)
Since ACWP Began
BCWPcum
Duration (wks or mos)
From Time Now to
Manager's
Stated
Completion Date
SC or S/C
Schedule Correlation
BCWP
ACWP
Ratio of work accomplished against money spent (an efficiency rating: Work
Done for Resources Expended)
To Complete
Performance Index
or Verification Factor
BAC - BCWP
EAC - ACWP
Ratio of work remaining against money remaining (Efficiency which must be
achieved to complete the remaining work with the expected remaining money)
Schedule Performance Index
SPI
Ratio of work accomplished against what should have been done (Efficiency
Rating: Work done as compared to what should have been done)
BCWP
BCWS
SV
Ratio of Schedule Variance (SV) in terms of average amount of work
accomplished (in weeks or months). It indicates a correlation to program true
schedule condition
IEAC
Independent Estimate
At Completion
BAC
PF
Calculation of a projected Estimate At Completion to compare with the CAM's
Estimate At Completion:
1) Ration of total work to be done against experienced cost efficiency
2) Sunk costs added to a ratio of remaining work against weighted cost and
schedule efficiencies
1)
2)
BAC - BCWP
.8CPI + .2SPI
ACWP +
Average Expected
Performance To Finish
Average rate at which work has been accomplished since work began
Average rate at which work must be accomplished in the future to finish on the
date the CAM has forecasted for completion of the work.
P
TO GO
P
CUM

## Slide 20
Benefits of EVMS
Clear definition of work prior to beginning that work
  Helps the line manager credibly request appropriate resources
  Provides the basis for a realistic plan against which to measure performance

## Slide 21
Benefits of EVMS [continued]
Objective measurement of work accomplishment
  Helps the line manager develop plans that are rooted in reality
    If the task can be done within scope, schedule, budget; confidence in a successful outcome is increased
    If the task cannot be done within scope, schedule, budget; that problem can be defined and resolved at a time when the resolution will be reasonably inexpensive

## Slide 22
Benefits of EVMS [continued]
Objective measurement of work accomplishment [continued]
  Assists the line manager to request needed help
  Assists program and functional management to identify areas requiring additional management attention
Provides true cost condition
  Side-steps false cost variances
  Encourages realistic projections of final cost
  Enhances accuracy of funding forecasts

## Slide 23
Benefits of EVMS [continued]
Reduces propensity of customer/boss to add work without adding budget
  Ties budget directly to work
  Requires all work transfers to include associated budget
  Requires all budget transfers to include associated work
Fosters management decisions within a framework of reality, rather than latent unease

## Slide 24
Any Questions?
Sean Alexander
Summary/Wrap-up

## Slide 25
EVMS Resources
Books
  Earned Value Quentin W. Fleming & Joel M. Koppleman
  Cost/Schedule Control Systems Criteria Quentin W. Fleming
  Project Performance Measurement Robert R. Kemps
  Visualizing Project Management Kevin Forsberg, Ph.D., Hal Mooz and Howard Cotterman
Software
  Artemis Views Artemis Management Systems Contact: Patrick Perugini (303) 581-3102 Web: http://www.artemispm.com
  Cobra Welcom Software Contact: Diana Melton (281) 558-0514 Web: http://www.wst.com
Software [continued]
  Dekker TRAKKER Dekker Ltd. Contact: Ron Barry (909) 384-9000 Web: http://www.dtrakker.com
  MicroFrame Project Manager (MPM) MicroFrame Technologies, Inc. Contact: Carl Amacker (415) 616-4000 Web: http://www.microframe.com
Internet
  Project Management Institute http://www.pmi.org
  US DoD Earned Value http://www.acq.osd.mil/pm
  Earned Value Bibliography http://www.uwf.edu/~dchriste/ev-bib.html
  Amazon.com http://www.amazon.com
Sean Alexander
(703) 503-5000 or (888) 860-0700
salex@meridianet.com

## Slide 26
Earned Value Data Elements
Time Now
Cost Variance
Schedule Variance
Projected
Project
Delay
Variance at
Completion
(VAC)
Estimate at Completion
(EAC)
Budget at Completion (BAC)
Project Budget Base
Management
Reserve
ACWP
BCWP
BCWS
ETC
Schedule Slip

## Slide 27
Earned Value Terminology
Data Element
Term
Acronym
Scheduled Work
Budgeted Cost for Work Scheduled
BCWS
Earned Value
Budgeted Cost for Work Performed
BCWP
Actuals
Actual Cost of Work Performed
ACWP
Authorized Work
Budget At Completion
BAC
Forecasted Cost
Estimate At Completion
EAC
Work Variance
Schedule Variance
SV
Cost Variance
Cost Variance
CV
Completion Variance
Variance At Completion
VAC