## Slide 1: Cost Estimation
The Basics

## Slide 2: Sources
Barry Boehm et al., Software cost estimation with COCOMO II, Prentice-Hall: New Jersey, 2000.
Walker Royce, Software project management – a unified framework, Addison Wesley Longman: Reading, MA, 1998.
Some slides from Yancey Bond and Dmitriy Shaltayev, University of Alabama

## Slide 3: Background
COCOMO: Constructive Cost Modeling
  Barry Boehm, Software Engineering Economics, 1981
  Provided an “engineering” basis for reasoning about cost and schedule for software-based solutions
Ada COCOMO
  Barry Boehm and Walker Royce, 1989
Based on waterfall process model

## Slide 4: Problems
Standish Group 1995: 53% of software projects were overrun by more than 50% on both budget and schedule
Numerous large-scale failures
  London Stock Exchange
    $1.5M --> $6+M; 7 mos. --> 17+ mos.
      cancelled after 17 months
  FAA Advanced Automation System
    $3.7B --> $7.0B; 48 mos. --> 96 mos.
      cancelled after 70 months
  Master Net (banking)
    $22M --> $80+M; 9 mos. --> 48+ mos.
      cancelled after 48 months

## Slide 5: COCOMO
Effort = C1 * EAF * (Size)P1
Time = C2 * (Effort)P2
Where
  C1 = constant scaling coefficient for effort
  EAF = effort adjustment factor that characterizes domain, personnel, environment, tools
  Size = size of the end product measured in number of delivered source instructions
  P1 = exponent characterizing economies of scale (especially non-value-add: rework, bureaucracy, communications overhead
  Time = total number of months
  C2 = constant scaling coefficient for schedule
  P2 = exponent characterizing inertia and parallelism

## Slide 6: Original Empirical Models Based on 56 Projects
Organic (all done in-house)
  Effort = 3.2 * EAF * (Size)1.05
  Time = 2.5 * (Effort)0.38
Semidetached (middle-ground)
  Effort = 3.0 * EAF * (Size)1.12
  Time = 2.5 * (Effort)0.35
Embedded (custom, external customer)
  Effort = 2.8 * EAF * (Size)1.2
  Time = 2.5 * (Effort)0.32
(See handout for effort adjustment factors)

## Slide 7: Since COCOMO …
Software an essential part of most businesses
Improved quality and reduced cost, risk, cycle time
  Evolutionary, risk-driven, collaborative development
  Fourth-generation languages and application generators
  Commercial off-the-shelf (COTS) and reuse-driven software approaches
  Fast-track development approaches
  Software process maturity initiatives

## Slide 8: Model Clashes
Typical Cause: incompatibilities among the primary models being used to define and manage the project
  product models: requirements, architecture, design, etc.
  process models: waterfall, spiral, maturity models, etc.
  property models: cost, schedule, performance, etc.
  success models: business case, stake-holder win-win, “I’ll know it when I see it” (IKIWISI), etc.

## Slide 9: MBASE
Model-Based (System) Architecting and Software Engineering
  Provide consistent, mutually supportive product, process, property and success models
    http://sunset.usc.edu/research/MBASE
  Stakeholder success models are primary drivers
  Win-Win Spiral Model
  Architecture-first development, RUP, incremental
  Integrated system/software engineering
    Move toward Integrated Capability Maturity Model (CMM-I)

## Slide 10: COCOMO II
Barry Boehm et al., Software cost estimation with COCOMO II, Prentice-Hall: New Jersey, 2000.
Two underlying models
  Framework for describing software project
    Effort ~ (Environment) x (Size)Process
    Schedule ~ (Effort) Process
    Addresses process models, culture, stakeholders, methods, tools, teams and the size/complexity of product
  Experience base used to estimate the likely resources (effort, time) of a project from historical precedents
    calibration data

## Slide 11: Related Models
COCOTS: cost of COTS integration
COPSEMO: phase distribution of schedule and effort
CORADMO: rapid application development
COQUALMO: quality in terms of delivered defect density
COPROMO: effects of software productivity strategies

## Slide 12: COCOMO II User Objectives
Reason about cost and schedule implications of software decisions
  investment or other financial decisions involving software development effort
  project budgets and schedules as a basis for planning and control
  tradeoffs among cost, schedule, functionality, performance or quality
  cost and schedule risk management
  build vs. buy: develop, reuse, lease, purchase
  legacy software: modify, phase out, outsource
  invest in organization capabilities: tools, process maturity, reuse, outsourcing, etc.
  process improvement strategies

## Slide 13: COCOMO II Model Objectives
Provide accurate cost and schedule estimates for current and likely software projects
Enable organizations to easily recalibrate, tailor or extend COCOMO II
Provide careful, easy-to-understand definitions of the model’s inputs, outputs and assumptions
Provide a constructive model
Provide a normative model
Provide an evolving model

## Slide 14: Tailorable Mix of Three Models
Application Composition: Any prototyping
  2 environment drivers, 0 process drivers
  Sizing in Object Points
Early Design Model: Exploring architecture, development options, Design
  7 environment drivers, 5 process drivers
  Sizing in Function Points or SLOC
Post Architecture Model: Ready to Develop, has a lifecycle architecture
  17 environment drivers, 5 process drivers
  Sizing in Function Points or SLOC
(Comparison: COCOMO 81)
  15 environment drivers, 1 process driver
  Sizing in SLOC (Function Point Extensions)

## Slide 15: Marketplace Model
End-User Programming
(55M performers in U.S. in 2005)
Application Generators
And Composition Aids
(0.6M performers)
Application
Composition
(0.7M)
System
Integration
(0.7M)
Infrastructure
(0.75M)
Does not need COCOMO II
COCOMO II Application Composition Model
Mix of 3 COCOMO II Models

## Slide 16: Tailorable Mix of Three Models Why?
Tailorable processes, not waterfall
Granularity of cost model must be consistent with granularity of information available at given phase of project
  Cost ranges, not cost points
  Coarse-grained in early phases
  Increasingly fine-grained in later phases

## Slide 17: Process Models
Inception Elaboration Construction Transition
Plans and Preliminary Detailed Code and Integration
Requirements Design Design Unit Test and Test
Inception
Readiness
Review
Life-
Cycle
Objectives
Life-
Cycle
Architecture
Initial
Operational
Capability
Product
Release
Review
Life-Cycle
Concept
Review
Software
Requirements
Review
Product
Design
Review
Unit
Test
Accept.
Critical
Design
Review
Software
Acceptance
Review
MBASE/
RUP
Waterfall
COCOMO II Estimation Endpoints
Early Design Model
Post-Architecture Model

## Slide 18: Nominal-Schedule Estimation Equations (Early Design and Post-Arch Models)
where
Effort in Person-Months (Nominal Sched)
Development Calendar Time (NS)
where
Effort Multipliers
for Cost Drivers
n=6 in ED
n=16 in PA
Exponential
Scale Factors
COCOMO II.2000 Calibration:

## Slide 19: Example
Average large project
  100 KSLOC
  EMi = 1.0
  E = 1.15

## Slide 20: Cost Drivers
Cost Driver rating (as an EM) is based on a strong rationale that they would independently explain
  a significant source of project effort
  productivity variation
Early Design model: 7 cost drivers
Post-Architecture model: 17 cost drivers
Size is the primary cost driver
  Exponential effect – five scale factors

## Slide 21: Scale Factors
E = exponent of Size cost driver
  E < 1.0  economies of scale
    double project size, less then double effort
    Achieved via shared simulations, testbeds, project infrastructure (tools, standards, reporting, etc.)
  E = 1.0  balanced economies of scale
    Typical for small projects
  E > 1.0  diseconomies of scale
    Interpersonal communication overhead
    Large system integration overhead

## Slide 22: Modeling Question
Why do the equations take this form?
  Especially for the exponents?
  Staffing level is computed, not fixed input, to development time?
  Relative quantitative values for qualitative cost drivers

## Slide 23: Size Calculation for New Code
Measure the amount of intellectual work put into program development
Two types of code
  New Code
  Reused and Adapted Code
Measures
  Source Lines of Code (SLOC)
  Unadjusted Function Points (UFP)
  Object Points
  Others…

## Slide 24: Counting Source Lines of Code
Logical Source statement is standard line of code
  See SEI checklist definition
  Exclude COTS, GFS, other products, libraries, operating systems
  Count operator directives to code generators
Measure in thousand source lines of code
  KSLOC

## Slide 25: Counting Unadjusted Function Points (UFP)
External Input (EI)
  Count each unique user data or user control input type that enters system boundary
External Output (EO)
  Count each unique user data or user control input type that leaves system boundary
Internal Logical File (ILF)
  Count each major logical group of user data or control information in the software system as a logical internal file type. Include each logical file (e.g., each logical group of data) that is generated, used, or maintained by the software system.
External Interface Files (EIF)
  Files passed or shared between software systems (counted within each system)
External Inquiry (EQ)
  Count each unique input-output combination, where input causes and generates an immediate output
5 User Function Types

## Slide 26: UFP Counting Process
Count the number of each of the five user function types
Determine complexity levels (low, avg., high) depending on the number of data element types and the number of file types referenced
Apply complexity weights (using calibrated tables)
Compute UFP: add all the weighted function counts
Convert UFP Count to SLOC in the implementation language
  COCOMO II uses backfining (?) tables, see handout

## Slide 27: Reused Code
Terms
  Reused Code: “Black Box”
  Adapted Code: “White Box”
  ESLOC: Equivalent Source lines of Code
Effects
  ~5% cost to assess, select, assimilate
  Adaptation Adjustment Modifier (AAM)
    Cost of understanding software and checking module interfaces

## Slide 28: Reuse Factors
DM = % of design modified
CM = % of code modified
IM = % of integration effort is to integrate reused software
AT = % of code automatically translated
SU = Software understanding increment
  Structure, Application Clarity, Self-Descriptiveness
  Very low  very high; 10%  50% penalty
AA = assessment and assimilation increment
  None  extensive test, evaluation and documentation
  rating 0 8
UNFM = programmer’s relative unfamiliarity with the software
  0.0 (very familiar)  1.0 (never seen it)

## Slide 29: Size Calculation for Reused Code
Terms:
  Reused Code: “Black Box”
  Adapted Code: “White Box”
  ESLOC: Equivalent Source lines of Code
Equation:
  EKSLOC = Adapted KSLOC * (1 – AT/100) * AAM
  AAF = (0.4 * DM) + (0.3 * CM) + (0.3 * IM)
  [AA + AAF(1+ (0.02 * SU * UNFM))]/100
  for AAF<=50
AAM=
[AA + AAF + (SU * UNFM)]/100
        for AAF>50
{

## Slide 30: Observations
Adaptation Adjustment Modifier (AAM)
  Best case: 1-1 with building from scratch
  Worst case: 2x the effort to modify than to develop as new
Reuse (black box, COTS) may require glue code
Integration and test is not free
  Reduce with well-architected product lines
  IM > 100 is possible for integration into complex applications

## Slide 31: Size Adjustment for Requirements Evolution
Requirements Evolution and Volatility (REVL)
  e.g., user interface evolution, technology upgrades, COTS volatility
  Percentage of code discarded due to requirements evolution
    A relative adder to size of delivered code
Calculation:
  Size = (1 + REVL/100) x SizeD
  SizeD is the reuse-equivalent of the delivered software

## Slide 32: Automatically Translated Code
Cost of software re-engineering and conversion
  AT = % code re-engineered by automatic translation
The term (1-AT/100) in the Equivalent SLOC equation represents automatically translated code
Automated Translation Productivity (ATPROD)
  Default ATPROD = 2400 source statements per person-month

## Slide 33: Software Maintenance
Add new capabilities; fix or adapt existing capabilities
  Adjusted by understanding and familiarity factors
  Excludes major rebuild (>50%) or large (>20%) interface changes
If know Base Code Size and Maintenance Change Factor
  MCF in % = (Sizeadded + Sizemodified)/Base Code Size
  SizeM = [(Base Code Size) x MCF ] x MAF
    MAF = Maintenance Adjustment Factor
    = 1 + (SU/100 x UNFM)

## Slide 34: Effort Estimation
Early Design and Post-Architecture Models use the same functional form
Effort is expressed in Person-Months (PM)
  the amount of time one person spends working on the software project in one month
  ~152 hours/PM
PM = A x SizeE x EMi
  A = 2.94 for COCOMO II.2000

## Slide 35: Economies of Scale Factors
Precedentedness (PREC): if a product is similar to several previously developed projects, the prec. is high
Development Flexibility (FLEX)
Architecture/Risk Resolution (RESL)
Team Cohesion (TEAM)
Process Maturity (PMAT) : Key Process Questionnaire
    18 Key Process Areas from SEI CMM
    Equivalent Process Maturity Level (EPML)
      EPML = 5 * (KPA % / 100) *1/ # of KPAs

## Slide 36: Effort Multipliers
Each rating level of the cost drivers has a value associated with it that translates the qualitative rating of the cost driver into a quantitative one.
  Nominal Level always has an effort multiplier value of 1.00.
  EMi > 1.00 more effort required
  EMi < 1.00 less effort required
Post-Architecture Model has 17 cost drivers
Early Design has 7 cost drivers (combinations of the Post-Architecture Model’s 17 drivers)
Post-Architecture Drivers can be divided into Product, Platform, Personnel, and Project Factors

## Slide 37: Product Factors
Required Software Reliability (RELY) : the measure of the extent to which the software must perform its intended function over a period of time
Database Size (DATA): captures the effect large test data requirements have on product development. Determined by the ratio D/P ratio of bytes in the testing database to SLOC in the program

## Slide 38: Product Factors (continued)
Product Complexity (CPLX): Divided into 5 areas
  Control operations
  Computational operations
  Device-dependent operations
  Data management operations
  User interface management operations
Developed for Reusability (RUSE): Accounts for additional effort needed to construct components intended for reuse
  Across Project
  Across Program
  Across Product line
  Across multiple product lines

## Slide 39: Product Factors (continued)
5. Documentation Match to Life-Cycle Needs (DOCU): evaluated in terms of the suitability of the project’s documentation to its life cycle needs

## Slide 40: Platform Factors
6. Execution Time Constraint (TIME): measure of the execution time constraint imposed upon a software system. Based on the percentage of available execution time to be used by the system
7. Main Storage Constraint (STOR): represents the degree of main storage constraint imposed on a software system.

## Slide 41: Platform Factors (continued)
8. Platform Volatility (PVOL): referring to the hardware and software the software product calls on to perform its tasks.
  Major change every two weeks =>very high
  Major change every 12 months =>low

## Slide 42: Personnel Factors
9. Analyst Capability (ACAP): Analysis and design ability examined
10. Programmer Capability (PCAP): evaluate on team basis not individual
11. Personnel Continuity (PCON): in terms of the project’s annual personnel turnover
12. Applications Experience (APEX): based on the level of applications experience of the project team
  Less than 2 months =>very low
  6 years=>very high

## Slide 43: Personnel Factors (continued)
13. Platform Experience (PLEX): level of experience with more powerful platforms, networking, database, user interface
14. Language and Tool Experience (LTEX): measure of the level of programming language and software tool experience of the project team

## Slide 44: Project Factors
15. Use of Software Tools (TOOL): amount of involvement of software tools
  Simple edit and code =>very low
  Integrated life cycle management =>very high
16. Multi-site Development (SITE): involves assessing and judgment-based averaging of 2 factors:
  Site collocation
  Communication support
17. Required Development Schedule (SCED): measures the schedule constraint imposed on the project team. Stretch out or acceleration

## Slide 45: Early Design Model Drivers
Early Design Cost Driver
Combined Post-Arch. Cost Drivers
Product Reliability/Complexity - RCPX
RELY, DATA, CPLX, DOCU
Developed for Reusability RUSE
RUSE
Platform Difficulty - PDIF
TIME, STOR, PVOL
Personnel Capability - PERS
ACAP, PCAP, PCON
Personnel Experience - PREX
APEX, PLEX, LTEX
Facilities - FCIL
TOOL, SITE
Required Development Schedule SCED
SCED

## Slide 46: Effort Estimation for Multiple Modules
Apply project-level drivers, scale factors and the SCED cost driver to the aggregated size
Apportion effort by component size as a % of whole
Apply component-level drivers, scale factors (excluding SCED) to each component
Repeat without applying SCED at project-level
Resulting in

## Slide 47: Schedule (Time to Develop) Estimation
TDEV = [C * (PMNS)F] * SCED% / 100
  C = 3.67
  F = (D + 0.2 * [E – B])
    D = 0.28
    B = 0.91

## Slide 48: Using COCOMO II as a justifiable analysis model for business decisions
Investment decisions; Business-Case analysis
Setting project budgets and schedules
Performing tradeoff analyses
  e.g., vary RELY effort multiplier and see how cost shifts from development to maintenance in total life-cycle cost
Cost/schedule risk management
  Perform computations with and without the risk being realized and see the size of the impact  best/worst case estimates
Development vs. COTS reuse decisions
Legacy software phase-out decisions
Software reuse and product line decisions
Process improvement decisions

## Slide 49: More?
Business decision examples
Application examples
Calibration
Extensions (COPSEMO, COCOTS, etc.)
Phase/Activity distributions
Use for incremental development
Future trends
Industry assessment and use