## Slide 1: COCOTS
The Basics

## Slide 2: Risks specific to COCOTS
No access to the source code
The COTS product evolution and development is out of control

## Slide 3: The determinants of the feasible COTS solution
Strategic
Technical
Economic
Feasible
COTS
solution

## Slide 4: Relation of the COCOTS to the COCOMO suite
COCOMO models the of system component built from scratch, new code
COCOMO II allows to model the use of the system components built from the preexisting source code that is reused, I.I modified or adapted for current purposes
COCOTS models the use of the preexisting software components the access to the source code of which is rectricted

## Slide 5: COCOTS overview
COCOTS consists of 4 related sub models :
Candidate COTS component assessment
COTS component tailoring
Integration, development of the “glue code” needed to plug the COTS components into the larger system
Increased system level volatility due to the incorporated COTS components

## Slide 6
TIME
STAFFING
New System development
Not Involving COTS Components
COCOMO II Efforts

## Slide 7
TIME
STAFFING
New System development
Not Involving COTS Components
COCOTS Efforts
System Efforts due to COTS Volatility
1. COTS Assessment
3. Glue Code Development
2. COTS Tailoring

## Slide 8: COTS Component Assessment
Basis for the COTS assessment
  Functional Requirements – capability offered
  Performance Requirements – timing and sizing constraints
  Nonfunctional Requirements – cost, training, installation, maintenance, reliability
Has 2 stages
  Initial Filtering
  Detailed assessment

## Slide 9: Formulas :
Initial Filtering Efforts (IFE) =  (# of COTS candidates in class) * (average initial filtering effort for class) over all classes
Detailed Assessment Effort (DAE) =  (# of COTS candidates in the class) * (average detailed assessment effort for class) over all classes, by project domain
Final Project Assessment Effort = IFE + DAE

## Slide 10: COTS Assessment Attributes
CORRECTNESS
AVAILABILITY / ROBUSTNESS
SECURITY
PRODUCT PERFORMANCE
UNDERSTANDABILITY
EASE OF USE
VERSION COMPATIBILITY
INTERCOMPONENT COMPATIBILITY
FLEXIBILITY
INSTALLATION / UPGRADE EASE
PORTABILITY
FUCTIONALITY
PRICE
MATURITY
VENDOR SUPPORT
TRAINING

## Slide 11: COTS Tailoring
Activities to configure COTS
  Parameters Initialization
  Input / GUI screen and output report layout
  Security protocols set-up
  Script Writing
  NOT modification / expansion of COTS functionality

## Slide 12: Formulas :
  Project Tailoring Effort =  (# of COTS tailored in the class) * (average tailoring effort for class and complexity) over all classes, by project domain,
  where the average tailoring effort for a given class is qualified by the complexity of the overall tailoring task usually associated with class, rated over 5 levels from Very Low to Very High (from 1 to 5)

## Slide 13: Glue Code
New Code needed to get COTS product integrated into a larger system.
Can be the code to connect COTS to other COTS and NDI or the code to connect COTS to the higher level system code

## Slide 14
In-house built software composed of :
  Code needed to facilitate the data/information exchange between COTS and other COTS/NDI or between COTS and the system
  Code needed to connect COTS to the system and/or other COTS/NDI but does not necessarily to enable data/information exchange
  Code needed to provide the required functionality missing in the COTS component which depends upon or interacts with the COTS component

## Slide 15
interfaces
interfaces
Glue Code
COTS
Components
Application
Components
or other
COTS
Components
The Scope of the Glue Code:
Data transfer, interface connection, needed functionality

## Slide 16: Glue Code Sub model
  Glue Code Effort =
  A * [(size) * (1 + CREVOL)]B *
   (effort multipliers)
  where
  A – linear scaling factor
  Size = of glue code in source-lines of code or function points
  CREVOL = % of rework of the glue code due to the COTS volatility or requirements change
  B = architectural nonlinear scaling factor
  Effort multipliers = 13 multiplicative adjustment factors

## Slide 17: Effort Multipliers
Personnel Drivers
ACIEP – COTS Integrator Experience with Product
ACIPC – COTS Integrator Personnel Capability
AXCIP – Integrator Experience with COTS Integration Process
APCON – Integrator Personnel Continuity

## Slide 18: Effort Multipliers (Contd.)
COTS Components Drivers
ACPMT – COTS Product Maturity
ACSEW – COTS Supplier Product Extension Willingness
APCPX –COTS Product Interface Complexity
ACPPS – COTS Supplier Product Support
ACPTD – COTS Supplier Provided Training and Documentation

## Slide 19: Effort Multipliers (Contd.)
Application/System Drivers
ACREL – Constraints on Application System/Subsystem Reliability
AACPX – Application Interface Complexity
ACREP –Constraints on COTS Technical Performance
ASPRT – Application System Portability

## Slide 20: System Volatility
The effort that results from the on the larger system of the effects of swapping COTS components out of the system with newer versions of those components that have been released by the COTS vendor.
Once the project has moved to the long-term maintenance phase these impacts will be significant and may dominate the system maintenance process depending upon the # and nature of the COTS components used.

## Slide 21
System Volatility Effort = (application effort) * {[1 + (SCREVOL/1+REVL)] E - 1}* (COTS effort multipliers)
where
Application effort = new coding effort separate from COTS integration effects
SCREVOL = % rework in the system due to the COTS volatility and requirements change
REVL = % of rework in the system independent of COTS effects due to the requirements change
System Volatility Effort