## Slide 1: The Personal Software Process (PSP)
CMU/SEI-2000-TR-022, ESC-TR-2000-022
By Watts S. Humphrey
Also used
A Personal Commitment
to Software Quality
By Watts Humphrey
Presented By Vikas Bhatia
Referenced site
http://wwwipd.ira.uka.de/~gramberg/PSP/#forms

## Slide 2: What is PSP
Provides engineers with a disciplined personal framework for doing software work
Provides a set of methods, forms, and scripts that show how to plan, measure, and manage the work
Designed for use with any programming language or design methodology
Can be used for any aspect of software development
Goal – produce zero defect products on schedule and within planned costs
Recommended use with TSP

## Slide 3: The Umbrella Strikes Back
CMM – focus on management system and support provided to development engineers
TSP – extend the PSP concept to the team
PSP – extended to people “who actually do the work” – the engineers

## Slide 4: Principles of PSP
Every engineer is different; to be most effective, engineers must plan their work and they must base their plans on their own personal data
To consistently improve their performance, engineers must personally use well-defined and measured processes
To produce quality products, engineers must feel personally responsible for the quality of their products. Superior products are not produced by mistake; engineers must strive to do quality work
It costs less to find and fix defects earlier in a process than later
It is more efficient to prevent defects than to find and fix them
The right way is always the fastest and cheapest way to do a job
IMPROVE

## Slide 5: PSP Process Structure
See PSP1 Project Plan Summary Handout

## Slide 6: PSP Process Elements
Since the PSP process has a number of methods that are not generally practiced by engineers, the PSP methods are introduced in a series of seven process versions. These versions are labeled PSP0 through PSP3, and each version has a similar set of logs, forms, scripts, and standards
The process scripts define the steps for each part of the process, the logs and forms provide templates for recording and storing data, and the standards guide the engineers as they do the work
PSP scripts also called operational process
PSP Forms

## Slide 7: Process Elements

## Slide 8: PSP Introduction Structure
Students write 10 programs and complete 5 data analysis reports
Start with the PSP0 process, record the time spent in each process phase, and log all the defects found
One or two programs with each PSP version

## Slide 9
http://interactive.sei.cmu.edu/Features/1999/June/Background/
Background.jun99.htm

## Slide 10: PSP1 Process Script

## Slide 11: PSP Planning

## Slide 12: PSP Process
Requirements - Engineers start planning by defining the work that needs to be done in as much detail as possible
Conceptual Design - This is a first, rough guess at what the product would look like if the engineers had to build it based on what they currently know
Estimate Product Size and Resources – Use PROBE

## Slide 13: PROBE
PROxy Based Estimation – uses proxies or objects as the basis for estimating the likely size of the product
Determine the objects required to build the product described by the conceptual design
Determine the likely type and number of methods for each object
Refer to historical data on the sizes of similar objects previously developed and use linear regression to determine the likely overall size of the finished product
To use linear regression, must have historical data on estimated versus actual program size for at least three prior programs
Result – Estimate for size of program, total development time, and the time required for each development phase

## Slide 14: PSP Process (contd)
Produce the Schedule – Based on the time time required for each process step, engineers estimate the time they will spend on the job each day or week. With that information, they spread the task time over the available scheduled hours to produce the planned time for completing each task.
Develop Product
Analyze the Process – Postmortem, update the project plan summary with actual data, calculate any required quality or other performance data, and review how well they performed against the plan

## Slide 15: PSP Data Gathering
Time Measures
Size Measures
  LOC
  Size Categories
  Size Accounting
Quality Measures
  - Defect Density - Review Rate
  - Development Time Ratios - Defect Ratios
  - Defect Removal Leverage - Yield
  - Defects Per Hour - A/FR

## Slide 16: PSP Discipline
Engineers normally do not follow procedures…?
In PSP these procedures are: follow a defined process, plan the work, gather data, and use this data to analyze and improve the process
Not easy in practice
Solution TSP – to provide the disciplined environment that engineers need to consistently use the PSP methods in practice

## Slide 17: PSP Results
Claims that PSP “substantially improves engineering performance in estimating accuracy and early defect removal while not significantly affecting productivity”
Provided charts to prove that as PSP exposure continues results, quality of work improves

## Slide 18: CMM, TSP and PSP are designed such that…
CMM - To produce superior products, management must obtain superior performance from their engineers. This requires that they hire capable people and provide them with suitable leadership, processes, and support
TSP - The engineers must be able to work together effectively in a team environment and know how to consistently produce quality products
PSP - The engineering teams must be properly trained and capable of doing disciplined engineering work
Finally, without proper management and executive leadership, organizations cannot succeed, regardless of their other capabilities