GHS Class of 1993 – 10 Year Reunion

August 2, 2003

Planning Notes

Updated July 30, 2003

Committees:

- Venue & Food Committee – Chair Brandi Dennis Young

- Entertainment & Activity Committee – Chair Angie Moody Jones

- Publicity Committee (Liase w/newspapers and radio stations) – Chair Sydney Gohring Hofer

- Communication [with Classmates] Committee – Chair Becky Sliva-Callahan

- Web Presence Committee – Chair Jeremy Moats

- Finance Committee – Chair Mick White

Reunion Volunteers: Chris McLean, Keri Laduke, Amy Gengenbacher and staff at Mick White’s office

Friday night plans (August 1, 2003):

- Nothing official planned

- Informal gathering at Cherry Street

Saturday night (August 2, 2003):

Reunion Logistics

- Location: Knox College, Lincoln Room

- Time: 6:00 – 11:00 pm

- Payment: $25 for singles or $45 per couples; make checks payable to “GHS Class of 1993” and send to Mick White at 415 N. Henderson Street, Galesburg IL 61401.  Payment deadline: Wednesday, July 30.  Headcount to Knox due same day by Noon.

- Food: Buffet will include vegetarian pasta shells, chicken, sweet corn, broccoli/cauliflower mix, mashed potatoes, roasted baby red potatoes, three choices of salad (garden, fresh fruit and pasta) and three choices of dessert (cheesecake, German chocolate cake and apple pie)

- Alcohol: Cash bar until 10:30

- Entertainment: DJ, slide show, web site images and a handful of small, interactive games

- Recommended attire: business casual

Planning Timeline:

February 2003: Date set for reunion and committee established

February 2003: Secured Knox College as the location, deposit provided ($200)

February 2003: Yahoo group created

March 2003: 1993 graduating class list obtained from Steve Eisemann at GHS

March 2003: Class web site created

March – June 2003: Communication with classmates; updated addresses and started collecting RSVPs (Also, utilized large public sites such as classmates.com and reunion.com to find classmates via e-mail. On classmates.com, the GHS Class of 1993 has over 160 registered members.)

April 13, 2003: Committee Conference Call to finalize plan

April – June 2003: Sent out press releases to local community papers and stations

May 2003: DJ booked and deposit provided ($50)

June 14, 2003: E-mail postcard to all classmates with confirmed e-mail address

June 16, 2003: Post card mailing to all classmates without confirmed e-mail address

July 3, 2003: Opened class bank account (Joint account: Mick White & Kristin Gunther Michalczyk) and reviewed the location and ‘house’ decorations

July 15, 2003: Reminder post card mailing

July 25, 2003: 98 confirmed RSVPs

July 29, 2003: 104 confirmed RSVPs

July 30, 2003: Final headcount to Knox

Note: Committee heads need to meet briefly at 5:30 pm on August 2, just before the doors open at the reunion to discuss the following items: reunion agenda, expectations for future reunions, updating addresses, and a quick run through last minute details.