## Slide 1: Using Microsoft Project 98 to Assist in Managing Information Technology (IT) Projects
Kathy Schwalbe, Ph.D., PMP
Associate Professor, Business/MIS
Augsburg College, Minneapolis, MN
Presented 3/26/99 at CTI Conference
schwalbe@augsburg.edu
www.augsburg.edu/ppages/schwalbe

## Slide 2: Overview of Presentation
Audience background and interest in this topic
Personal background on IT projects and using Microsoft Project
Introduction to project management
Overview of Project 98
Step-by-step example using Project 98
Where to get sample files

## Slide 3: Introduction to Project Management (PM)
Project management is “the application of knowledge, skills, tools, and techniques to project activities in order to meet or exceed stakeholder needs and expectations from a project” (PMI*, PM Body of Knowledge (PMBOK), 1996, p. 6)
*The Project Management Institute (PMI) is an international
professional society. Their web site is www.pmi.org

## Slide 4: Project Management Framework
Project Management Integration
Project
Success
Scope
Mgt.
Time
Mgt.
Cost
Mgt.
Quality
Mgt.
HR
Mgt.
Comm.
Mgt.
Risk
Mgt.
Procure.
Mgt.
9 Knowledge Areas Core Functions
Facilitating Functions
Stakeholder
needs and expectations
Tools and
techniques

## Slide 5: IT Projects Have a Terrible Track Record
Project “success” is often defined as meeting project scope on time and within budget
The Standish Group’s famous “CHAOS” reports* document the horrible IT track record
  Only 16% of IT projects were successful from 1995 CHAOS survey (up to 26% in 1998 study)
  31% of IT projects were cancelled in 1995, costing the U.S. over $81 billion
* 1995 report available at www.standishgroup.com

## Slide 6: Time, Cost, and Scope Problems of IT Projects*
Average schedule overrun for IT projects was 222%
Average cost overrun was 189%
Large companies’ IT projects have 42% of the originally-proposed features and functions
* 1995 report available at www.standishgroup.com

## Slide 7: Project Management Can Help Improve Success If Used Well
Positive leadership is the most significant factor associated with successful project managers
Using software is just one tool of project management. You must understand several PM concepts before using PM software

## Slide 8: Benefits of Using PM Software
Software alone can not improve projects, but it can help
  define and manage the scope of projects
  create and manage project schedules
  manage resources and costs
  facilitate communications

## Slide 9: Key PM Concepts Needed Before Using Project 98
A Work Breakdown Structure (WBS) is an outcome-oriented structure that defines the total scope of the project
A Gantt chart is a tool for communicating project schedules using a calendar format

## Slide 10: More Key PM Concepts
A network diagram (also referred to as a PERT chart) shows the sequence in which tasks must be performed
A critical path is the longest path through a network diagram that determines the earliest completion of a project. It has no slack time
A baseline is a project plan that serves as the basis for measuring performance

## Slide 11: WBS for Intranet Project in Chart Form

## Slide 12: Sample Intranet WBS and Gantt Chart*
*This template file comes with Project 98
WBS
Gantt Chart

## Slide 13: WBS and Gantt Chart for Software Launch*
*This template file comes with Project 98.
WBS
Gantt Chart

## Slide 14: Sample Network Diagram or PERT Chart
The tasks in red are on the critical path. If any of them
take longer than planned, the whole project will slip
unless something is done.
Each box is a project task from
the WBS. Arrows show
dependencies between tasks

## Slide 15: Overview of Microsoft Project 98
Project 98 is the clear leader in the desktop market for PM software
  The Gartner Group estimates it accounts for 2/3 of sales
  A recent survey of 1,000 PMs found it was used by 48% of the respondents. Next listed tool only used by 13.8% of respondents*
  PC Magazine gave it the Editor’s Choice award in 6/30/98 issue
*Fox, Terry L. and Spence, J. Wayne, "Tools of the Trade:
A Survey of Project Management Tools," Project Management
Journal, September 1998

## Slide 16: Common Errors in Using Project 98 or other PM Software
People do not understand
what a WBS is, and they are hard to create
the need to link tasks or know what a critical path is
the need to set a baseline in order to track progress
that Project 98 is a powerful and complicated tool, and training is needed

## Slide 17: Step-By-Step Example Using Project 98
First I’ll show help information and basics about the software
Then I’ll create a new file for a project to create a project tracking database

## Slide 18: Where to Get Sample Files
Microsoft Project 98 comes with sample files that should be loaded in Program Files/Microsoft Office, Templates, Microsoft Project. The Intranet and Software Launch files are sample files
Several vendors provide sample files, and many companies keep a repository of files
Microsoft provides links to Y2K and IT template files (next slide)

## Slide 19: www.microsoft.com/products/msoffice/project/download/template.htm