## Slide 1: Chapter 12: Initiating

## Slide 2: Opening Case
Chapters 12-15 are all based on a real case study
Fay Beauchine, VP of Reservations at Northwest Airlines (NWA), sponsored the ResNet projects
Peeter Kivestu, a marketing director, was the project manager for ResNet
ResNet was the first information technology project led by non-technical managers at NWA

## Slide 3: What Is Involved in Project Initiation?
Initiating is the process of recognizing and starting a new project or project phase
It is critical to ensure that the right kinds of projects are being initiated for the right reasons
It is better to have moderate or een a small amount of success on an important project than huge success on an unimportant one

## Slide 4: Supporting Explicit Business Objectives
The most important reason for initiating IT projects is to support explicit business objectives
NWA was having financial difficulties in the early 1990s, so reducing costs was a key business objective
ResNet would help stop the financial drain caused by the reservation call centers

## Slide 5: Table 12-1. Initiating Processes and Outputs

## Slide 6: Background on Northwest Airlines (NWA)
Northwest Airlines (www.nwa.com) is the world’s fourth largest airline and America’s oldest carrier
In 1998, NWA had over 50,000 employees worldwide
The reservation system used 3,000 dumb terminals in the early 1990s
The reservation process was becoming more complex, and the call centers were losing money

## Slide 7: Background on ResNet
The reservation system before ResNet was PARS
Reservation agents had to use cryptic commands to use the old system
All information was on one character-based screen
Deregulation and new marketing initiatives complicated the reservation process
Call times were increasing

## Slide 8: Figure 12-1. Sample Reservation Screen Before ResNet

## Slide 9: Focus on Making Direct Sales
Fay Beauchines’ vision was to change the focus of the call centers from just information and service to sales
Making a direct sale saved NWA commission fees of 13% plus 18% in overhead cost savings
A new reservation system was needed to help agents make direct sales

## Slide 10: Staffing a New Project
Fay selected Peeter Kivestu, a marketing director at NWA, as the ResNet project manager
Peeter’s strategy was to prove the concept of ResNet first with a prototype
Peeter asked Arvid Lee, a senior member of the IS department, to lead the IS team on the ResNet projects
Kathy (Krammer) Christenson, a marketing analyst, become the ResNet application development manager

## Slide 11: Table 12-2. Three Main ResNet Projects

## Slide 12: What Went Wrong?
After finishing the ResNet beta project, Peeter and his team saw the rest of ResNet as one large project to implement the new reservation system in all of the call centers. Senior management, however, broke the rest of ResNet into two separate projects, ResNet 1995 and ResNet 1996. Their goals were to avoid a huge investment commitment and to provide further incentives for the ResNet team to produce successful results. If the 1995 ResNet project was not successful, senior management could decide not to fund the 1996 project. Although this strategy reduced financial risk, Peeter and his team did not like the decision. If ResNet 1996 were not approved for some reason, they would be stuck with two totally different reservations systems in different sales offices. This situation would cause huge management, technical, and support problems. The ResNet 1995 team was under a lot of pressure to do a good job or the ResNet 1996 project would not be funded.

## Slide 13: Selecting the Project Manager
An important part of project initiation is selecting a project manager. Fay selected Peeter because
  he knew the airline business
  he understood the technology
  he knew that technologies could improve business productivity
  Peeter used his passion for the project to convince Fay and others that he should be the project manager

## Slide 14: Preparing Business Justification for the Projects
For the Beta project
Fay convinced senior managers to invest $500,000 into developing a prototype system
Peeter emphasized his track record as a leader and what the competition was doing
Arvid was well-known and respected for his IS expertise

## Slide 15: Preparing Business Justification for the Projects
For the ResNet 1995 and 1996 projects
Very strong justification was needed to make major investments
Peeter prepared detailed plans and focused on
  key business objectives of the project
  impressive results from the beta project
  the opportunity to make money with the new system (NPV estimate of $37.7M)

## Slide 16: What Went Right?
Peeter and the ResNet team prepared outstanding business justification for all of the ResNet projects. Using his strong technical and business skills, Peeter wrote persuasive documents justifying ResNet, and he made his case well in presentations. Peeter's justification strategy for the 1995 and 1996 ResNet projects included very strong financial analysis, which greatly impressed the finance committee. Peeter knew that the decision-makers wanted to see the bottom line numbers, and Peeter provided them as well as detailed rationale for how he got them. He prepared a five-year cash flow analysis of all costs and benefits, clearly defined major assumptions, and described the basis for all of his projections. It was obvious to the finance committee that Peeter knew what he was doing. They also appreciated the fact that someone leading a major information technology project was driven by business needs instead of technology needs.

## Slide 17: Table 12-3. ResNet 1995-96 Financial Summary

## Slide 18: Figure 12-2. Sample ResNet Screen

## Slide 19: “What ResNet is to PARS Is Like What AT&T Is to Two Sticks and a Hollow Log”
ResNet integrated information from different areas and put it all on one screen
Context-appropriate sales messages helped agents provide customers with information that would help close a sale
ResNet ensured accuracy and consistency in call handling

## Slide 20: Figure 12-3. Executive Summary for Justifying ResNet Project
Northwest Reservations offices currently operate with the PARS reservations system using 30 year old technology. As a result, reservations agents must remember cryptic commands to access vast amounts of quickly changing marketing information. Because of the inflexibility of the current system, the time, and consequently the cost of taking a reservation is difficult to manage, agents are not able to consistently follow procedures, and training costs are high. Most of Northwest's competitors, and now also travel agencies, have been aggressively addressing reservations inefficiencies by installing intelligent reservations terminals. These airlines and agencies have realized significant operating improvement through cost savings and revenue enhancements.
Marketing requests approval to install intelligent sales terminals - to be called ResNet - in the eight domestic Reservations Sales offices, in the new Chisholm WorldPerks office, and in the Sales Action Center. The 5 year NPV of the project is $37.7 M.
There is limited downside risk to the project as it has been proven in a National Sales beta test at NW and similar versions of the product are in service with many domestic and international competitors. As the extensions of the applications are built for other parts of Reservations, they will be built to the same standards as the current applications. Of the total one-time costs to implement ResNet, the majority (65%) is hardware or facility related.
Furthermore, there are substantial upside benefits possible. The software is a small part of the total cost of the system, but can be modified without change to the hardware to accommodate a wide variety of revenue enhancing and cost reducing add-ons to the base software. Because the software chosen for this application and the ability of the reservations users to complete many of their own enhancements, rapid deployment of new functionality throughout the project term will be encouraged.

## Slide 21: Developing the Project Charter
NWA did not use official project charters in the early 1990s
Receiving formal budget approval was the main means for chartering projects
The project plan for ResNet was called a Purchase Request 2 (PR2), which included information on the project, technical, development, applications, operations, and change management approaches

## Slide 22: Table 12-4. Next Steps After Beta ResNet Project

## Slide 23: Actions of the Project Manager and Senior Management in Project Initiation
Quickly assembling a strong project team
Getting key stakeholders involved in the project early
Preparing detailed analysis of the business problem and developing project measurement techniques
Using a phased approach
Preparing useful, realistic plans for the project

## Slide 24: Discussion Questions
What was Fay's role in initiating ResNet? Why did she succeed when other NWA employees in the Information Systems department had similar ideas years earlier?
What were some of Peeter's strengths as a project manager? How do these strengths relate to concepts discussed in earlier chapters?
Review the executive summary Peeter prepared to help justify investing in ResNet. What points were made to convince the finance committee to support the project?
Discuss the major differences between the three ResNet projects. What was the emphasis for each project? How might each be managed differently?