## Slide 1: Chapter 14: Executing

## Slide 2: What Is Involved in Executing Projects?
Project execution involves taking the actions necessary to ensure that activities in the project plan are completed
The products of the project are produced during execution
The 1996 ResNet project involved installing over 2,000 PCs in seven different offices, creating more software, training agents, and measuring the benefits of the system

## Slide 3: Recall Figure 2-5. Level of Process Group Activity Over Time
The most time and money are usually
spent on executing processes

## Slide 4: Importance of Good Project Execution
Project execution means getting the work done, and stakeholders want to see results
June 21, 1999 Fortune cover story highlighted why most CEO’s fail - poor execution! The same is true for project managers

## Slide 5: Table 14-1. Executing Processes and Outputs

## Slide 6: Providing Project Leadership
Peeter was an experienced project manager and effective leader
He thought the three main success factors on ResNet were
  having clear goals
  making the work fun, and
  sticking to schedules

## Slide 7: What Went Right?

## Slide 8: Developing the Core Team
Peeter developed a strong core team with Arid and Kathy leading major parts of the projects
Peeter was a hands-on manager and felt every single person involved in ResNet was important
Peeter also kept Fay well informed of the project’s progress
Peeter provided necessary resources to help his people succeed

## Slide 9: Verifying Project Scope
Peeter focused on the broad goals of the project, then the details
Peeter was notorious for having long meetings to clarify project scope
Peeter and Fay planned for incrementally developing the ResNet interface by budgeting for people to continue developing enhancements. The scope was limited by what they could do, so users focused on the most important enhancements

## Slide 10: Assuring Quality
Industrial engineers developed techniques to measure the impact of ResNet and analyzed the reservations process
This work helped justify spending money on ResNet and in developing the user interface
Quadrant 4 had cells positioned based on the workflow of making reservations
The team also followed internal procedures for software development and hardware installation

## Slide 11: Figure 14-1. ResNet Quadrant 4

## Slide 12: Disseminating Information
Communication was a key factor in ResNet’s success
“Fear of the unknown is detrimental to a project,” said Kathy Christenson
The ResNet team disseminated project information often and in different ways to meet stakeholder needs

## Slide 13: Figure 14-2. Detroit Reservations Center Progress Report
Training Room 2
Training Room 1
Training Room 3
Comm. Room
Network
Progress indicated by shading
Implementation: February 26 to November 15, 1996
240 of 543 PCs Installed to Date
Reservation Agents, 6 PCs/pod
Other offices

## Slide 14: Change Management Teams
The ResNet team set up change management teams at each office to keep them informed
Training at each office included brief one-on-one sessions with each agent in addition to formal classroom training
ResNet management wanted to address the unique questions and concerns of each agent

## Slide 15: Procuring Necessary Resources
ResNet involved procuring many off-the-shelf hardware, software, and networking products
The ResNet architecture was fairly complex, as shown in Figure 14-3
Arvid Lee was instrumental in working with various vendors, and he used his expertise and experience to the company’s advantage

## Slide 16: Figure 14-3. ResNet Data Network Overview Schematic

## Slide 17: Training Users to Develop Code
Recall that a lack of user involvement is the main reason why many IT projects fail
A critical decision concerning the ResNet interface software was to have users—sales agents —help to write code
Peeter interviewed interested agents and worked with their union to be fair
6 sales agents and 3 IS staff wrote the bulk of the ResNet interface after attending a training course by Qantas

## Slide 18: Table 14-2. Sample Scripting Language for ResNet User Interface

## Slide 19: Agents’ Reactions to ResNet
"This computer is just wonderful. The colors are great. It's easy to look at. It's a lot of fun."
"It makes the customer feel confident that you know what you're doing."
"You have time to think about more important things like non-stop service to certain cities that we have that other airlines don't."
"Not going home at night with headaches. That's my favorite part."
"It's fun. It's new and it's different. You look at the big picture and what it can save Northwest and the revenue we can bring in. The bottom line is it's a great system - it's a moneymaker. It's quick, it's fun and it's easy. What more can you want?"

## Slide 20: Discussion Questions
Describe Peeter's leadership style. What made him an effective project leader? Would he be an effective project leader in a different organization? Why or why not? What role did organizational culture play in his leadership style?
What do you think about having users go to training classes to learn to write code to develop their own systems? Do you think this could or should be done on more information technology projects?
How much impact do you think making the project fun had on project success? Do you think that most large information technology projects could copy this approach?