## Slide 1: Chapter 16: Closing

## Slide 2: What Is Involved in Closing Projects?
Closing processes include gaining stakeholder acceptance of the final product and bringing the project or phase to an orderly end
Closing verifies that all of the deliverables have been completed
A project audit is often done

## Slide 3: Transition Planning
It is important to plan for and execute a smooth transition of the project into the normal operations of the company
Most projects produce results that are integrated into the existing organizational structure
Some projects require the addition of new organizational structures
Some projects end by extinction or starvation

## Slide 4: Table 16-1. Closing Processes and Outputs

## Slide 5: Administrative Closure
Administrative closure involves
  verifying and documenting project results to formalize acceptance of the products produced
  collecting project records
  ensuring products meet specifications
  analyzing whether the project was successful and effective
  archiving project information for future use
NWA had several reviews of the benefits of ResNet

## Slide 6: Table 16-2. ResNet Benefits Results from March 1996 Benefits Review

## Slide 7: ResNet Audit
A formal audit was completed on December 10, 1996
Two main questions addressed:
  What benefits, in terms of selling and call handle time, have been realized by the Reservations Department as a result of ResNet
  How do those real results compare with projected results in the PR2 plan?

## Slide 8: Audit Answers to Questions
The Reservations Department has significantly increased selling as a result of management leadership, the market environment, and the opportunities provided by ResNet as a selling tool
While increased selling, new hires, E-ticket sales, and other factors have increased Reservations' average call handle time for 1996, statistics support a handle time benefit from ResNet conversion
Of the two items audited, the higher than expected increase in selling compensated for the shortfall in call handle time, resulting in a net gain of $0.8 million to Northwest Airlines in 1996 versus the PR-2 projections.

## Slide 9: Final Audit Report Results
ResNet greatly surpassed expectation
ResNet increased direct sales by 17.7% versus the planned 5.5%
This increase in direct sales meant an additional $2.3 million in 1996 commission savings
In its first year of operation, ResNet saved Northwest Airlines over $15 million, and savings were over $33 million in the second year

## Slide 10: Figure 16-1. Selling Impact of ResNet
Direct sales greatly exceeded expectations!

## Slide 11: Audit Methodology
The audit methodology showed the amount of rigor that NWA put into its project audits and benefits measurement (see What Went Right?)
Experts analyzed historical information and ensured that data was not biased
Several statistical techniques were used to develop and measure the benefits of ResNet

## Slide 12: ResNet Final Recognition Party and Personnel Transition
Peeter and his team knew how important strong starts were, and they also wanted to have a strong finish
A final recognition party celebrated everyone’s achievements on ResNet
Peeter again authorized funds to hire actors to help organize fun events like the ResNet Rap performance

## Slide 13: Figure 16-2. ResNet Developers’ Rap*
* Written by Nancy Desch

## Slide 14: What Went Wrong?
NWA still struggles with transferring people, roles, and responsibilities between projects and on-going operations. For example, there were problems after completing the Computer Telephony Integration (CTI) work for ResNet 1996. This new technology provided better call handling by having customers respond to telephone prompts before talking to a sales agent. When the ResNet team had completed the work, the functional group that should have taken over support for it did not understand or willingly accept their new roles and responsibilities. NWA also did not budget enough people to support this new technology. This lack of transition planning caused several conflicts after the ResNet project ended. Senior management had to intervene to resolve these conflicts.

## Slide 15: Lessons Learned
Although the ResNet team did not write any formal lessons learned, Peeter, Kathy, and Arvid shared the following advice:
  Let workers have fun
  Beginnings are important
  Top management support is critical
  Managing change is 50% of project management
  Make management reviews interactive
  Set realistic milestone dates, and then stick to the schedule as much as possible
  Plan at a workable level

## Slide 16: What Is Next For ResNet?
Business and market forces have added new requirements to ResNet
Kathy Christenson is leading the ResNet+ project to add more capabilities to ResNet
NWA is focusing on business needs as the basis for the new project

## Slide 17: Figure 16-3. Business Need for ResNet+

## Slide 18: Discussion Questions
Review the goals of the ResNet final audit report. What was the focus of the audit? Why was it important to document the methodology assumptions? What other questions could be included in a final project audit?
Which lessons learned do you think Peeter, Kathy, and Arvid will most likely use on future projects?
Which lessons learned do you think will be hardest to replicate on future projects?