## Slide 1: Chapter 8: Project Human Resource Management

## Slide 2: The Importance of Human Resource Management
People determine the success and failure of organizations and projects
The shortage of good IT workers makes human resource management even more challenging for IT projects
  ITAA calculated that there were over 345,000 openings for IT jobs - about 10% of programmer, systems analysts, and computer engineering positions are open
  70% of CEOs in high-tech firms listed the lack of highly skilled, trained workers as the number one barrier to growth

## Slide 3: Long Hours and Stereotypes of IT Workers Hurt Recruiting
Many people are struggling with how to increase the IT labor pool. Noted problems include
  The fact that many IT professionals work long hours and must constantly stay abreast of changes in the field
  Undesirable stereotypes that keep certain people away from the career field, like women
  The need for better human resource management

## Slide 4: What is Project Human Resource Management?
Project human resource management includes the processes required to make the most effective use of the people involved with a project. Processes include
  Organizational planning
  Staff acquisition
  Team development

## Slide 5: Keys to Managing People
Psychologists and management theorists have devoted much research and thought to the field of managing people at work
Important areas related to project management include
  motivation
  influence and power
  effectiveness

## Slide 6: Motivation
Abraham Maslow developed a hierarchy of needs to illustrate his theory that people’s behaviors are guided by a sequence of needs
Maslow argued that humans possess unique qualities that enable them to make independent choices, thus giving them control of their destiny

## Slide 7: Figure 8-1. Maslow’s Hierarchy of Needs

## Slide 8: Herzberg’s Motivational and Hygiene Factors
Frederick Herzberg wrote several famous books and articles about worker motivation. He distinguished between
  motivational factors: achievement, recognition, the work itself, responsibility, advancement, and growth, which produce job satisfaction
  hygiene factors: cause dissatisfaction if not present, but do not motivate workers to do more. Examples include larger salaries, more supervision, and a more attractive work environment

## Slide 9: Thamhain and Wilemon’s Ways to Have Influence on Projects
1. Authority: the legitimate hierarchical right to issue orders
2. Assignment: the project manager's perceived ability to influence a worker's later work assignments
3. Budget: the project manager's perceived ability to authorize others' use of discretionary funds
4. Promotion: the ability to improve a worker's position
5. Money: the ability to increase a worker's pay and benefits
6. Penalty: the project manager's perceived ability to dispense or cause punishment
7. Work challenge: the ability to assign work that capitalizes on a worker's enjoyment of doing a particular task
8. Expertise: the project manager's perceived special knowledge that others deem important
9. Friendship: the ability to establish friendly personal relationships between the project manager and others

## Slide 10: Ways to Influence that Help and Hurt Projects
Projects are more likely to succeed when project managers influence with
  expertise
  work challenge
Projects are more likely to fail when project managers rely too heavily on
  authority
  money
  penalty

## Slide 11: Power
Power is the potential ability to influence behavior to get people to do things they would not otherwise do
Types of power include
  Coercive
  Legitimate
  Expert
  Reward
  Referent

## Slide 12: Improving Effectiveness - Covey’s 7 Habits
Project managers can apply Covey’s 7 habits to improve effectiveness on projects
  Be proactive
  Begin with the end in mind
  Put first things first
  Think win/win
  Seek first to understand, then to be understood
  Synergize
  Sharpen the saw

## Slide 13: Empathic Listening and Rapport
Good project managers are empathic listeners; they listen with the intent to understand
Before you can communicate with others, you have to have rapport
Mirroring is a technique to help establish rapport
IT professionals often need to develop empathic listening and other people skills to improve relationships with users and other stakeholders

## Slide 14: Improving Relationships Between Users and Developers
Some organizations require business people, not IT people, to take the lead in determining and justifying investments in new computer systems
CIOs push their staff to recognize that the needs of the business must drive all technology decisions
Some companies reshape their IT units to look and perform like consulting firms

## Slide 15: Organizational Planning
Organizational planning involves identifying, documenting, and assigning project roles, responsibilities, and reporting relationships
Outputs and processes include
  project organizational charts
  work definition and assignment process
  responsibility assignment matrixes
  resource histograms

## Slide 16: Figure 8-2. Sample Organizational Chart for a Large IT Project

## Slide 17: Figure 8-3. Work Definition and Assignment Process

## Slide 18: Figure 8-4. Sample Responsibility Assignment Matrix (RAM)

## Slide 19: Figure 8-5. RAM Showing Stakeholder Roles

## Slide 20: Figure 8-6. Sample Resource Histogram for a Large IT Project
Excel file

## Slide 21: Issues in Project Staff Acquisition and Team Development
Staffing plans and good hiring procedures are important in staff acquisition, as are incentives for recruiting and retention
Some companies give their employees one dollar for every hour a new person they helped hire works
Some organizations allow people to work from home as an incentive

## Slide 22: Resource Loading and Leveling
Resource loading refers to the amount of individual resources an existing project schedule requires during specific time periods
Resource histograms show resource loading
Over-allocation means more resources than are available are assigned to perform work at a given time

## Slide 23: Figure 8-7. Sample Histogram Showing an Over-allocated Individual
Project 98 file

## Slide 24: Resource Leveling
Resource leveling is a technique for resolving resource conflicts by delaying tasks
The main purpose of resource leveling is to create a smoother distribution of resource usage and reduce over-allocation

## Slide 25: Figure 8-8. Resource Leveling Example

## Slide 26: Team Development
It takes teamwork to successfully complete most projects
Training can help people understand themselves, each other, and how to work better in teams
Team building activities include
  physical challenges
  psychological preference indicator tools

## Slide 27: Meyers-Briggs Type Indicator (MBTI)
MBTI is a popular tool for determining personality preferences and helping teammates understand each other (www.keirsey.com)
Four dimensions include:
  Extrovert/Introvert (E/I)
  Sensation/Intuition (S/N)
  Thinking/Feeling (T/F)
  Judgment/Perception (J/P)
Most IT professionals are NTs or rationals
Vary most from general population in not being extroverted or sensing

## Slide 28
Quick Team Development Exercise*
Rank from 1 to 5 which figures you like the best
*Dellinger, Susan, Psycho-Geometrics, Prentice Hall, 1989

## Slide 29: Behavioral Style Differences*
*David Merril and Larry Wilson

## Slide 30: Reward and Recognition Systems
Team-based reward and recognition systems can promote teamwork
Focus on rewarding teams for achieving specific goals
Allow time for team members to mentor and help each other to meet project goals and develop human resources

## Slide 31: General Advice on Teams
Focus on meeting project objectives and producing positive results
Fix the problem instead of blaming people
Establish regular, effective meetings
Nurture team members and encourage them to help each other
Acknowledge individual and group accomplishments

## Slide 32: Using Software to Assist in Human Resource Management
Software can help in producing RAMS and resource histograms
Project management software includes several features related to human resource management such as
  viewing resource usage information
  identifying under and over-allocated resources
  leveling resources

## Slide 33: Discussion Questions
Discuss the evidence pointing to a shortage of IT workers. How has Y2K affected the labor shortage? Why are there not more students majoring in computer science or MIS if there is such a labor shortage? Speculate about whether the IT labor shortage will continue into the first decade of the 21st century.
Give examples of different ways to have influence on projects. Which do you think would be most effective with you?