## Slide 1: Chapter 13: Planning

## Slide 2: What is Involved in Project Planning?
Planning is often the most difficult and most unappreciated process in project management
Many people have a negative view of planning because they do not use plans to facilitate action
The main purpose of project plans is to guide execution
Every knowledge area includes planning

## Slide 3: Table 13-1. Planning Processes and Outputs

## Slide 4: Table 13-1. Planning Processes and Outputs

## Slide 5: Developing the Project Plans
The ResNet beta project plan was successful due to planning at a fairly high level, getting strong user involvement, and developing solid measurement tools
The ResNet 1995 and 1996 plans were more detailed and focused on key milestones needed to install the 3,000 PCs and develop new software

## Slide 6: What Went Right?
The PR-2 for the ResNet 1996 project included performance results from implementing ResNet in Baltimore in 1995. Because the project team developed measurement tools and used them on the ResNet 1995 project, they had a strong business case for justifying further investments in the ResNet 1996 project. The call handle time actual results in Baltimore showed a 6.7 percent improvement after implementing ResNet, and the percentage of direct ticket sales increased from 3.2 percent to 7.5 percent. This increase in direct sales translated to over $15 million in profits that ResNet generated in 1995 alone.

## Slide 7: Determining Project Scope and Schedules
Peeter and the ResNet team clearly defined the scope of each project
They focused on meeting key milestones, one at a time
NWA did use Microsoft Project to create Gantt charts, but they did not link any tasks or enter actuals
The ResNet team did not miss any milestone dates!

## Slide 8: Table 13-2. Planned Software Development and Office Implementation Milestones

## Slide 9: Figure 13-1. ResNet 1996 Application Development Gantt Chart
Project 98 file

## Slide 10: Figure 13-2. ResNet 1996 Level 2 WBS for Office Implementations

## Slide 11: What Went Wrong?
There was a lot of political pressure related to the Iron Range Reservations Center (IRRC) in Hibbing, Minnesota. The state of Minnesota funded a large portion of this office, which was the central point for handling the WorldPerks system. The WorldPerks implementation date of March 31, 1996 was firm. The ResNet team was a little overconfident in their planning, and several problems developed. WorldPerks involved a new communications protocol, and the ResNet team did not plan enough time up-front to analyze all of the system requirements. They expedited testing, and there were several quality problems that were difficult to resolve because of a lack of precision in planning.

## Slide 12: Figure 13-3. ResNet 1996 Office Implementation Plan
Project 98 file

## Slide 13: ResNet Cost Estimates
Peeter, Arvid, and other project members developed cost estimates
They used vendor quotes for estimating hardware, software, and network equipment
They estimated internal labor costs based on the number of people needed from various departments and the labor cost per hour for those employees

## Slide 14: Table 13-3. Maximum Departmental Headcounts by Year

## Slide 15: Table 13-4. Summary of ResNet Total Life Cycle Costs

## Slide 16: Human Resources and Communications Planning
Peeter was good at motivating people and providing strong communications with project stakeholders
The ResNet team used informal and formal networking and plans

## Slide 17: Table 13-5. ResNet Staffing Plan (in person-months)

## Slide 18: Figure 13-4. ResNet Project Organization Chart
. . . . . . . . . . . . . . . . .
.
.
.
.
.
.
.
.
.
.
.
.
.
.
. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .
: : : :
. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .
: : . .
. .
. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .
: . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .
Joan Charnas
Mktg & Cust Svc
Director
Lori Manecke
Reservations
Appl Mgr
Arvid Lee
IS ResNet
Project Mgr
Norm Renner
System SW
Director
Mike Cameron
Distributed
Sys Manager
Randy Pool
Sys SW Splst
Michael Besch
Tom Vande Hei
Ntwk Res
Director
Ron Vycital
Network Dev
Manager
Jim Campbell
NR ResNet
Project Mgr
Network
Services
Paul Battaglia (NYC)
Larry Buesgens
Diane Cornwell
Todd Grimm (SEA)
Teresa Hendershott
Frank Kluge (HQA)
Roy Knapp (BWI)
Mark Kummer (DTT)
Keith Long (LAX)
Alan Millar (TPA)
Dean Oines (CHIS)
Mark Sparks (MSP)
Keith Struck
Dave Vesper (TPA)
Network
Development
Mike Fulkerson
Liani Lee
Steve Muench
Doug Smart
Network
Operations
Rich Peterson
George Sandmeyer (MSP)
Dave Timp
Dennis Halloran
Systems Res.
Director
Amy Wages
Help Desk
Manager
Merle Baldus
Help Desk
Analyst
Mike Anenson
Cecily Johnson
Kim Kuppenbender
Ruby Madison
Peeter Kivestu
ResNet Proj
Director
Mona Dass
ResNet TL
Dave
Hopperstad
ResNet TL
Jim Foster
Proj Control
Analyst
Tom Atz
Nancy Hansen
Hugh Plappert
Dirk Visker
Min Zhuang
. .
. .
. .
.
.
.
. .
. .
. . . . . . . . . . . . . . . . . . . . .
. . . . . . . . .
. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .
Bob Dufek
Plng & Support
Director
Tam Rath
Prod Sys Sup
Manager
Joe Santos
Info Center
Manager
Ken Bietz
ESD
Sandy Hart
Change Mgmt
Israel Hill
Level 4 Comp
Mike Powers
MS Office
Training
Sue Bromen
Cyndi Gust
Kaye Hayes
Jim Kath
.
.
. . .
.
.
.
.
.
.
.
.
.
.
.
. . .
. . . . .
Kathy Krammer
ResNet Appl
Development
Nancy Strobel
ResNet Chg
Management
Dan Newstrom
Operations
Research
Randy
Pemberton
Project
Specialist

## Slide 19: ResNet Communications
Most of the people assigned to ResNet were full-time, making communications easier
The ResNet team created templates for communicating project information like weekly and monthly status reports
They set up a shared network drive for all project information
They held regular meetings for various team members and stakeholders

## Slide 20: Quality, Risk, and Procurement Planning
The PR2 included some information related to quality, risk, and procurement planning
The measurement techniques for tracking call handling time and number of direct sales closes were critical elements in assessing quality
NWA used past experience in dealing with vendors
NWA managed risk by following expert advice and having strong user involvement

## Slide 21: Discussion Questions
Discuss Peeter's request for Arvid to create a plan for the beta ResNet project in one week. How would you react to this request? Is it realistic to take only one week to plan a project that will last more than a year? How do you think Peeter made this request since Arvid responded so well?
Review the Gantt charts for ResNet 1996 application development and office implementation. Why do you think these were created as two separate Gantt charts? Why do you think the project team did not link activities in Microsoft Project? Do you think linking activities in project management software is done often on real projects? Why or why not?
Review the WBSs and cost estimates provided. Discuss any questions you might have about them