## Slide 1: Chapter 10: Project Risk Management

## Slide 2: The Importance of Project Risk Management
Project risk management is the art and science of identifying, assigning, and responding to risk throughout the life of a project and in the best interests of meeting project objectives
Risk management is often overlooked on projects, but it can help improve project success by helping select good projects, determining project scope, and developing realistic estimates

## Slide 3: What is Risk?
A dictionary definition of risk is “the possibility of loss or injury”
Project risk involves understanding potential problems that might occur on the project and how they might impede project success
Risk management is like a form of insurance; it is an investment

## Slide 4: Why Take Risks? Because of Opportunities!
Opportunities
Risks
Try to balance risks and opportunities

## Slide 5: Risk Utility
Risk utility or risk tolerance is the amount of satisfaction or pleasure received from a potential payoff
  Utility rises at a decreasing rate for a person who is risk-averse
  Those who are risk-seeking have a higher tolerance for risk and their satisfaction increases when more payoff is at stake
  The risk neutral approach achieves a balance between risk and payoff

## Slide 6: Figure 10-1. Risk Utility Function and Risk Preference

## Slide 7: What is Project Risk Management?
The goal of project risk management is to minimize potential risks while maximizing potential opportunities. Major processes include
  Risk identification: determining which risks are likely to affect a project
  Risk quantification: evaluating risks to assess the range of possible project outcomes
  Risk response development: taking steps to enhance opportunities and developing responses to threats
  Risk response control: responding to risks over the course of the project

## Slide 8: Common Sources of Risk on Information Technology Projects
Several studies show that IT projects share some common sources of risk
The Standish Group developed an IT success potential scoring sheet based on potential risks
McFarlan developed a risk questionnaire to help assess risk
Other broad categories of risk help identify potential risks

## Slide 9: Table 10-1. Information Technology Success Potential Scoring Sheet

## Slide 10: Table 10-2. McFarlan’s Risk Questionnaire

## Slide 11: Market, Financial, and Technology Risk
Market risk: Will the new product be useful to the organization or marketable to others? Will users accept and use the product or service?
Financial risk: Can the organization afford to undertake the project? Is this project the best way to use the company’s financial resources?
Technology risk: Is the project technically feasible? Could the technology be obsolete before a useful product can be produced?

## Slide 12: What Went Wrong?
Several information technology projects fail because of technology risk. One project manager documented an important lesson he learned on a large IT projectfocus on business needs first, not technology. David Anderson, a project manager for Kaman Sciences Corp., shared his lessons learned from a project failure in an article for CIO Enterprise Magazine. After spending two years and several hundred thousand dollars on a project to provide new client-server based financial and human resources information systems for their company, Anderson and his team finally admitted they had a failure on their hands. Anderson admitted that he was too enamored by using cutting edge technology and took a high-risk approach on the project. He "ramrodded through" what the project team was going to do, and he admitted that he was wrong. The company finally decided to switch to a more stable technology to meet the business needs of the company.
Hildebrand, Carol. “If At First You Don’t Succeed,” CIO Enterprise Magazine, April 15, 1998

## Slide 13: Risk Identification
Risk identification is the process of understanding what potential unsatisfactory outcomes are associated with a particular project
Several risk identification tools include checklists, flowcharts, and interviews

## Slide 14: Table 10-3. Potential Risk Conditions Associated With Each Knowledge Area

## Slide 15: Risk Quantification
Risk quantification or risk analysis is the process of evaluating risks to asses the range of possible project outcomes
Determine the risk’s probability of occurrence and its impact to the project if the risk does occur
Risk quantification techniques include expected monetary value analysis, calculation of risk factors, PERT estimations, simulations, and expert judgment

## Slide 16: Figure 10-2. Expected Monetary Value (EMV) Example

## Slide 17: Figure 10-3. Chart Showing High-, Medium-, and Low-Risk Technologies

## Slide 18: Simulation for Risk Analysis
Simulation uses a representation or model of a system to analyze the expected behavior or performance of the system
Monte Carlo analysis simulates a model’s outcome many time to provide a statistical distribution of the calculated results

## Slide 19: What Went Right?
McDonnell Aircraft Company used Monte Carlo simulation to help quantify risks on several advanced-design engineering projects. The National Aerospace Plan (NASP) project involved many risks. The purpose of this multi-billion dollar project was to design and develop a vehicle that could fly into space using a single-stage-to-orbit approach. A single-stage-to-orbit approach meant the vehicle would have to achieve a speed of Mach 25 (25 times the speed of sound) without a rocket booster. A team of engineers and business professionals worked together in the mid-1980s to develop a software model for estimating the time and cost of developing the NASP. This model was then linked with Monte Carlo simulation software to determine the sources of cost and schedule risk for the project. The results of the simulation were then used to determine how the company would invest its internal research and development funds. Although the NASP project was terminated, the resulting research has helped develop more advanced materials and propulsion systems used on many modern aircraft.

## Slide 20: Expert Judgment
Many organizations rely on the intuitive feelings and past experience of experts to help identify potential project risks
The Delphi method is a technique for deriving a consensus among a panel of experts to make predictions about future developments

## Slide 21: Risk Response Development
Risk avoidance: eliminating a specific threat or risk, usually by eliminating its causes
Risk acceptance: accepting the consequences should a risk occur
Risk mitigation: reducing th4e impact of a risk event by reducing the probability of its occurrence

## Slide 22: Table 10-4. General Risk Mitigation Strategies for Technical, Cost, and Schedule Risks

## Slide 23: Risk Management Plans, Contingency Plans, and Contingency Reserves
A risk management plan documents the procedures for managing risk throughout the project
Contingency plans are predefined actions that the project team will take if an identified risk event occurs
Contingency reserves are provisions held by the project sponsor for possible changes in project scope or quality that can be used to mitigate cost and/or schedule risk

## Slide 24: Table 10-5. Questions Addressed in a Risk Management Plan
Why is it important to take/not take this risk in relation to the project objectives?
What specifically is the risk and what are the risk mitigation deliverables?
How is the risk going to be mitigated? (What risk mitigation approach is to be used?)
Who are the individuals responsible for implementing the risk management plan?
When will the milestones associated with the mitigation approach occur?
How much is required in terms of resources to mitigate risk?

## Slide 25: Risk Response Control
Risk response control involves executing the risk management processes and the risk management plan to respond to risk events
Risks must be monitored based on defined milestones and decisions made regarding risks and mitigation strategies
Sometimes workarounds or unplanned responses to risk events are needed when there are no contingency plans

## Slide 26: Top 10 Risk Item Tracking
Top 10 risk item tracking is a tool for maintaining an awareness of risk throughout the life of a project
Establish a periodic review of the top 10 project risk items
List the current ranking, previous ranking, number of times the risk appears on the list over a period of time, and a summary of progress made in resolving the risk item

## Slide 27: Table 10-6. Example of Top 10 Risk Item Tracking

## Slide 28: Using Software to Assist in Project Risk Management
Databases can keep track of risks
Spreadsheets can aid in tracking and quantifying risks
More sophisticated risk management software helps develop models and uses simulation to analyze and respond to various project risks

## Slide 29: Figure 10-4. Sample Monte Carlo Simulation Results for Project Schedule

## Slide 30: Figure 10-5. Sample Monte Carlo Simulations Results for Project Costs

## Slide 31: Results of Good Project Risk Management
Unlike crisis management, good project risk management often goes unnoticed
Well-run projects appear to be almost effortless, but a lot of work goes into running a project well
Project managers should strive to make their jobs look easy to reflect the results of well-run projects

## Slide 32: Discussion Questions
Discuss the risk utility function and risk preference chart in Figure 10-1. Would you rate yourself as being risk averse, risk neutral, or risk seeking? Give examples of each approach from different aspects of your life, such as your current job, your personal finances, romances, and eating habits.
What is your organization’s (your employer's or your college's) risk preference when it comes to information technology projects? Give evidence to support your position.
Describe the Top 10 Risk Item Tracking approach. How could you use this technique in your organization?