The Project Plan Template

The project plan forms the basis for all management efforts associated with the project. A project plan templateis included in this document.

The information contained in this plan is required for IT projects in varying degrees. The actual plan items required are defined specifically in project management policies.  The exact format of the information may vary from the template; however, the basic information is required as defined.

This plan template emphasizes documenting only the pertinent information associated with the plan. The blank template for the project plan is provided in Appendix B: Templates & Sample Forms.

The information associated with the plan  evolves as the project moves through its various stages and is updated as new information is determined about the project.

The plan does not require verbose textual content filled with boilerplate material. Information associated with detailed procedures for executing such processes as technical development, configuration management, and quality assurance should be documented in the state organization’s procedures. For example, the configuration management information contained in the plan might reference a procedures document that defines the specific activities and responsibility for each configuration item.  The project plan only summarizes who is responsible for the configuration management activities, what is under configuration control, and where the repository will reside.

The project plan documents the project planning process and consists of the following basic tasks:

- Defining the sequence of tasks to be performed.

- Identifying all deliverables associated with the project.

- Defining the dependency relationship between tasks.

- Estimating the resources required to perform each task.

- Scheduling all tasks to be performed.

- Defining the budget for performing the tasks.

- Defining the organization executing the project.

- Identifying the known project risks.

- Defining the process ensuring quality of the project product.

- Defining the process for configuration management.

- Defining the process specifying and controlling requirements.

The plan documents and defines the objectives of the project, the approach to be taken, and the commitment being assumed. The project plan evolves through

the early stages and, at project start-up time, contains the detail required to successfully execute the project.  Once project execution begins, the plan should be reviewed, baselined,  and updated on a regular basis.

Plan Approval

It is important that project plans are approved prior to beginning a project. These approvals should be easily located at the beginning of the plan to emphasize support for the project plan. In the template format, approval signatures are included on the cover of the plan, as shown below.

Project Management Plan Approval Signatures Form

(Page one of the sample)

Project Summary

Following the approvals page, there should be a project summary and charter information that defines:

- The estimated value of the project.

- The project deliverables.

- The duration of the effort.

- The purpose of the project.

- The goals, acceptance, and completion criteria.

- Assumptions made affecting cost and/or schedule.

- Major dependencies/constraints.

The Project Summary, begun at project initiation, is maintained over the course of the project. The first page includes areas that need to be filled in and then updated with each new release of the plan. These include:

- Project name and start date.

- State organization, name, and submitted by.

- Prime Contractor (if applicable) and date awarded.

- Current stage of the project.

- Project status in terms of schedule and budget.

- Budget summary.

Page 2 of the Project Summary includes points of contact and prime contractor information.

The following two pages show a completed sample project summary from the template.

1. Project Summary (Sample)

Information in the project summary areas was started during the project concept phase and should be included here

Project Summary - Continued

Points of Contact

This should be the list of individuals that will be involved with the project during the execution phase.

Project Charter

The project charter follows the project summary information. Like the project summary, the project charter information was developed during the project conception and definition phase and includes a business problem, statement of  work, objective, success factors, project dependencies, and constraints.  In the plan template, this information is contained on two pages or in the following two figures.  A sample of the completed information from the template is shown below.

2. Project Charter(Sample)

B.	Project Charter:

Business Problem.

All projects start with a business problem/issue to solve.

Sample

The lack of a statewide automated planning system for scheduling transportation road repair maintenance resources has resulted in road closures, duplicated capital expenditures, and increased staff overtime costs.

Statement of Work (Goal).

The statement should be short and to the point. It should not contain language or terminology that might not be understood.

Sample

Design and prototype an automated, dynamic planning system by Q4, 1997, based on an SQL database and GUI front end. Based on the prototype, pilot the system  and complete full implementation by Q4, 1998.

Project Objectives:

Provide a brief, concise list of what the project is to accomplish.

The project objectives are a detailed version of the statement of work. Taken with  the statement of work, the objectives define the boundaries (scope) of the project.  The objective statement can also be seen as a decomposition of the statement of work into a set of necessary and sufficient objective statements, including:

Outcome - Be specific in targeting an objective

Measurement- Establish a measurable indicator(s) of the progress

Ownership - Make the object assignable to a person for completion

Timeframe - State what can realistically be done with available resources

Sample

1.	Define the planning requirements for the system by Q2, 1997

2.	Define user needs in terms of inputs and outputs by Q2, 1997

3.	Conduct user and stakeholder meetings during Q1 and Q2, 1997

4.	Develop the prototype and test, with a completion date of  Q4, 1997

5.	Conduct the pilot of system with completion by  Q2, 1998, with the pilot lasting at least three months

6.	Complete system acceptance and user documentation by Q3, 1998

7.	Complete system installation at all locations by Q4, 1998

Project Trade Off Matrix and Status Summary

Managing a project requires the balancing of three factors: resource, schedule, and scope.  These three factors are interrelated, i.e., a change in one of them causes the others to change as well.  The project trade off matrix shows the relative importance of each factor:

- constrained means the factor cannot be changed

- accepted means the factor is somewhat flexible to the project circumstance

- improved means that the factor can be adjusted.

Also included on this page of the template is a matrix for project status. The matrix  reflects whether the technical, schedule, and cost estimates for each task are behind, on schedule, or ahead of schedule. Comments are added for any deviation from the original estimate.  For each project, the unique teams or phase should be filled in the appropriate category.

3. Project Tradeoff Matrix and Status Summary

Project Organization

The project plan should include a description of the organization that defines the persons responsible for  the following types of functions: project manager, development manager, quality assurance, and configuration management.  A project manager is required for every project.

Many plans may also include a narrative of key project member responsibilities. This would include the person’s name, project position, and key responsibilities.

Small projects will require less organizational definition than larger projects, but responsibilities should always be defined.

A sample project organization chart is shown in the following figure.  Most times this information is graphically presented.

4. Project Organization (Sample)

Activity List

Activity sequencing involves dividing the project into smaller, more manageable components (activities) and then specifying the order of completion. The following figure show s: 1) activities organized in outline form, and 2) activities in graph form.

5. Activity List (Sample Work Breakdown Structure)

Work Breakdown Structure

The activity list can also be graphically presented as a work breakdown structure and included in the project plan. The work breakdown structure, describes each task required in the project. For large projects, work packages, with a description showing how specific tasks are to be completed by specific project teams, may also be included.

These work packages describe required schedules, identify requirements to be completed and describe specific work to be performed. Refer to Activity Definition and Sequencing for further information on activity sequencing and development of a work breakdown structure.  A sample graphical work breakdown structure is shown in the following figure.

Work Product Identification

The list of project deliverables that includes the date due and the person responsible for the delivery should be part of the plan.  This information is derived from the project activity list, and is expanded to include the assignment of the deliverable to a specific author and tracking of delivery of the document. A sample of the Work Product Identification Template is shown below.

6. Work Product Identification

Project Schedule

The project schedule included in the project plan can either be a GANTT or PERT chart.  It should include milestones, task dependencies, task duration, work product delivery dates, quality milestones (reviews/audits/inspections), configuration management milestones, and action items (with deadlines and responsibilities). A sample project schedule is shown below.

PERT Chart

7. Project Schedule (Sample)

GANTT Chart

7. Project Schedule (Sample)

Estimate Cost at Completion

This estimated cost at completion is an assessment of the total project effort in terms of either time or dollars.  The template provides space for both types of analyses.

8. Estimated Cost at Completion

Resource Loading Profiles

The staffing plan shows the number of personnel, by type, that are required on the project on a monthly basis. A sample is included. This information is compared monthly on a planned versus actual basis. Refer to the Resource Planning section for further information about resource planning.  For small 1 - 2 person efforts, a graph should not be  necessary.

9. Project Staffing Plan (Sample)

Project Requirements

The detailed listing of project requirements, with references to the statement of work, work breakdown structure, and specifications, is included. Refer to Top-Level Requirements Specification. A sample listing is shown in the figure below.

10. Project Requirements

Risk Identification

A description of the risks identified for the project is included. A risk is anything  that could potentially affect the successful completion of the project.  The contractual, management, and technical risks associated are identified and assessed for the probability of the risk occurring, the cost to correct if the risk occurs, the impact of the risk on the project, and the suggested mitigation activities and cost of mitigation. Refer to Risk Identification section for further information.

11. Risk Identification

Configuration Management Plan

The Configuration Management Plan, which defines the person responsible for project configuration management, the procedures used, the planned configuration items, planned release dates for configuration items, and resources required to conduct Configuration Management, is included. This Configuration Management Plan is summarized in a format depicted in the figure below. Refer to the Configuration Management section for further information on configuration management planning.

12. Configuration Management Plan

Quality Plan

The Quality Plan, which defines the person responsible for project quality activities, the procedures used, the planned quality activities, and resources required to conduct QA activities is summarized in the project plan.  Refer to the Quality Plan Development section for further information on quality planning. The QA Plan is summarized in a format illustrated in the figure below.

13. Quality Plan

Top Five Issues

Included is the list of known issues associated with the project, personnel responsible for resolving the issue, and an associated open and close date, with proposed or recommended solutions. See the figure below and refer to the  Change and Issue Management section for further information about issue management.

14. Top Five Issues

Action Item Status

The plan should include a list of action items, that are maintained as part of project tracking. A sample table is included as part of the template and shown here.

15. Action Item Status

References:

The template for the Project Management Plan is included in Appendix B: Templates & Sample Forms.