## Control Panel
11/5/1996
12
9
9
12
12
9
CHANGE
Earned Value (BCWP)
$ Millions
$ Millions
Months
12/5/1996
PROGRESS
COMPLETION
PRODUCTIVITY
STAFF
QUALITY
RISK
Cost
Performance
Index (CPI)
Performance
Index (TCPI)
To-Complete
Configuration Management
Churn Per Month (%)
Requirements Change
Per Month (%)
Voluntary Turnover
Per Month (%)
Overtime Hours
Per Month (%)
Actual Cost (ACWP)
Elapsed Time
Reporting Period
From
To
Completed On Time
Total Due
Completed Late
Total Over Due
0
6
3
Total Program Perfomance Efficiency
Quality Gate
Quality Gate
Task Status This Period
Tasks Completed
Risk Exposure
Risk Reserve
Metrics Problem
Anonymous Channel Unresolved Warning
0
6
3
0
6
3
0.7
0.8
0.9
1.0
1.1
1.2
1.3
0.7
0.8
0.9
1.0
1.1
1.2
1.3
0.5
1.0
1.5
2.0
2.5
3.0
3.5
0.5
1.0
1.5
2.0
2.5
3.0
3.5
0.5
1.0
1.5
2.0
2.5
3.0
3.5
10
20
30
40
50
60
70
14
3
3
8
BCWS
BAC
EAC

## Project Data
Program Name: | Date of Report:
Control Panel Example | 2026-07-30 17:33
Project Date Data |  |  |  |  | Project Baseline Data |  |  | Color Legend:
Type of Reporting Period (M=Monthly or W=Weekly) | Project start date (month/day/year) | Total length of project (in reporting periods) | Current Reporting Period |  | Budget at Completion (BAC) | Original number of project requirements |  | Current Reporting Period | Final Reporting Period | Data Imported from MS Project
Monthly | 1996-08-06 | 12 | 4 |  | 10000000 | 85
Reporting Period Data |  |  | Earned Value Measures |  |  | Requirements |  | Quality Gate Tasks |  |  |  |  | Configuration Items |  | Voluntary Turnover |  | Overtime Hours |  | Risk Reserve |  | Defects By Activity | [7 empty] | Warning Indicators
REPORTING PERIOD N0. | Period End Date | Cumulative Planned Value (BCWS) | Cumulative Earned Value (BCWP) | Actual Cost (ACWP) | Estimate at Completion (EAC) | Total No. at Beginning of Period | No. Additions, Deletions, or Changes this Period | No. Scheduled this Period | Total Due this Period (#scheduled + #overdue from last period) | No. Completed On Time this Period | No. Completed Late this Period | Cumulative No. Overdue at End of Period | Total No. in CM System at End of Period | No. Modified and Rechecked into CM this Period | No. of Staff at Beginning of Period | No. Staff Leaving Voluntarily this Period | Base No. Staff Hours this Period | No. Overtime Staff Hours this Period | Total Budget Risk Reserve ($) | Total Schedule Risk Reserve (days) | Requirement defects open | Requirement defects closed | Design defects open | Design defects closed | Coding defects open | Coding defects closed | Test defects open | Test defects closed | Metrics problem indicator (yes/no) | Anonymous channel unresolved warning (yes/no)
1 | 1996-09-05 | 500000 | 500000 | 650000 | 10000000 | 90 | 3 | 5 | 5 | 3 | 1 | 1 | 50 | 1 | 75 | 5 | 13000 | 1000 | 30000 | 20 | 20 | 10 | 12 | 4 | 2 | 2 | 1 | 0 | yes | yes
2 | 1996-10-05 | 1000000 | 970000 | 1550000 | 11000000 | 96 | 3 | 7 | 8 | 2 | 1 | 5 | 52 | 0 | 70 | 2 | 13500 | 2000 | 28000 | 19 | 22 | 5 | 12 | 6 | 8 | 3 | 5 | 6 | yes | no
3 | 1996-11-05 | 2000000 | 2000000 | 2500000 | 11500000 | 100 | 2 | 7 | 12 | 2 | 2 | 8 | 60 | 3 | 80 | 1 | 13500 | 3375 | 28000 | 19 | 10 | 15 | 15 | 4 | 12 | 3 | 4 | 2 | no | yes
4 | 1996-12-05 | 3500000 | 3000000 | 3700000 | 12000000 | 98 | 1 | 6 | 14 | 3 | 3 | 8 | 65 | 2 | 85 | 2 | 13200 | 500 | 28000 | 18 | 5 | 20 | 8 | 12 | 25 | 10 | 8 | 5 | yes | no
5 | 1997-01-05 | 4000000 | [5 empty] | 10 | 18 |  |  | 18
6 | 1997-02-05 | 5250000 | [5 empty] | 12 | 30 |  |  | 30
7 | 1997-03-05 | 6150000 | [5 empty] | 15 | 45 |  |  | 45
8 | 1997-04-05 | 7000000 | [5 empty] | 13 | 58 |  |  | 58
9 | 1997-05-05 | 7750000 | [5 empty] | 11 | 69 |  |  | 69
10 | 1997-06-05 | 8500000 | [5 empty] | 16 | 85 |  |  | 85
11 | 1997-07-05 | 9250000 | [5 empty] | 12 | 97 |  |  | 97
12 | 1997-08-05 | 10000000 | [5 empty] | 5 | 102 |  |  | 102
13 | 1997-09-05 | [7 empty] | 102 |  |  | 102
14 | 1997-10-05 | [7 empty] | 102 |  |  | 102
15 | 1997-11-05 | [7 empty] | 102 |  |  | 102
16 | 1997-12-05 | [7 empty] | 102 |  |  | 102
17 | 1998-01-05 | [7 empty] | 102 |  |  | 102
18 | 1998-02-05 | [7 empty] | 102 |  |  | 102
19 | 1998-03-05 | [7 empty] | 102 |  |  | 102
20 | 1998-04-05 | [7 empty] | 102 |  |  | 102
21 | 1998-05-05 | [7 empty] | 102 |  |  | 102
22 | 1998-06-05 | [7 empty] | 102 |  |  | 102
23 | 1998-07-05 | [7 empty] | 102 |  |  | 102
24 | 1998-08-05 | [7 empty] | 102 |  |  | 102
25 | 1998-09-05 | [7 empty] | 102 |  |  | 102
26 | 1998-10-05 | [7 empty] | 102 |  |  | 102
27 | 1998-11-05 | [7 empty] | 102 |  |  | 102
28 | 1998-12-05 | [7 empty] | 102 |  |  | 102
29 | 1999-01-05 | [7 empty] | 102 |  |  | 102
30 | 1999-02-05 | [7 empty] | 102 |  |  | 102
31 | 1999-03-05 | [7 empty] | 102 |  |  | 102
32 | 1999-04-05 | [7 empty] | 102 |  |  | 102
33 | 1999-05-05 | [7 empty] | 102 |  |  | 102
34 | 1999-06-05 | [7 empty] | 102 |  |  | 102
35 | 1999-07-05 | [7 empty] | 102 |  |  | 102
36 | 1999-08-05 | [7 empty] | 102 |  |  | 102
37 | 1999-09-05 | [7 empty] | 102 |  |  | 102
38 | 1999-10-05 | [7 empty] | 102 |  |  | 102
39 | 1999-11-05 | [7 empty] | 102 |  |  | 102
40 | 1999-12-05 | [7 empty] | 102 |  |  | 102
41 | 2000-01-05 | [7 empty] | 102 |  |  | 102
42 | 2000-02-05 | [7 empty] | 102 |  |  | 102
43 | 2000-03-05 | [7 empty] | 102 |  |  | 102
44 | 2000-04-05 | [7 empty] | 102 |  |  | 102
45 | 2000-05-05 | [7 empty] | 102 |  |  | 102
46 | 2000-06-05 | [7 empty] | 102 |  |  | 102
47 | 2000-07-05 | [7 empty] | 102 |  |  | 102
48 | 2000-08-05 | [7 empty] | 102 |  |  | 102
49 | 2000-09-05 | [7 empty] | 102 |  |  | 102
50 | 2000-10-05 | [7 empty] | 102 |  |  | 102
51 | 2000-11-05 | [7 empty] | 102 |  |  | 102
52 | 2000-12-05 | [7 empty] | 102 |  |  | 102
53 | 2001-01-05 | [7 empty] | 102 |  |  | 102
54 | 2001-02-05 | [7 empty] | 102 |  |  | 102
55 | 2001-03-05 | [7 empty] | 102 |  |  | 102
56 | 2001-04-05 | [7 empty] | 102 |  |  | 102
57 | 2001-05-05 | [7 empty] | 102 |  |  | 102
58 | 2001-06-05 | [7 empty] | 102 |  |  | 102
59 | 2001-07-05 | [7 empty] | 102 |  |  | 102
60 | 2001-08-05 | [7 empty] | 102 |  |  | 102
Formulas:
Project start date (month/day/year) = DATE(YEAR(DateStart),MONTH(DateStart)+[Project Date Data],DAY(DateStart)-1)

## Risk Data
RISK DATA RISK No. | Estimated risk consequence - in days | Probability of risk occurrance | Estimated risk consequence - in dollars ($)
1 | 40 | 0.5 | 5000
2 | 20 | 0.3 | 41000
3 | 15 | 0.8 | 10000
4 | 12 | 0.2 | 20000
5 | 8 | 0.3 | 5000
6 | 30 | 0.1 | 50000
7 | 50 | 0.05 | 100000
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Earned Value Chart
Return
Help

## CPI & TCPI Chart
Note: See the Earned Value Chart for BCWP, ACWP, and BAC historical data.
Return
Help

## Total Program Performance Chart
85%
87%
Return
Help

## Quality Gate Tasks Chart
The gap between the Planned quality gates and the Actual quality gates along the top of the graph ( measured in Reporting Period Intervals) indicates schedule slip.
Help
Return

## CM Churn Chart
Help
Return

## Requirements Change Chart
Return
Help

## Voluntary Turnover Chart
Return
Help

## Overtime Hours Chart
Return
Help

## Risk Chart
Return
Help

## Defects by Activity Chart
Return
Help

## Problem Report Form
Project Control Panel Problem Report Form
To return this form:
1 | Copy this sheet to its own Excel workbook
2 | Name the file "XXXXmmdd.xls" where "XXXX" is the first four letters of your last name, "mm" is month and "dd" is day
3 | Attach it to an email and send it to: cntrlpnl@spmn.com
or send or fax problem reports to:
Software Program Manager's Network
Project Control Panel Initiative
758 S. 23rd St.
Arlington, VA 222202
Phone: | (703) 521-5231
Fax: | (703) 549-9583
Name:
email:
Phone:
FAX:
Title:
Company:
Address:
City, State, Zip:
Problem Number | Control Panel Version (ie CP 2.0) | Date of Problem: | Problem Severity (1=anoyance, 5= severe) | Cost of Quality (person-hours) this problem caused you | Location of Problem: Sheet name, item | Description of Problem | Suggested Solution
1
2
3
4
5
6
7
8
9
10

## Chart Data (hidden)
| Requirement defects | Design Defects | Code Defects | Test Defects
| Reqts | Design | Code | Test
Open | 5 | 8 | 25 | 8
Closed | 20 | 12 | 10 | 5
R.R. $ | 28000
R.L. $ | 38300
R.R. Time | 18
R.L. Time | 48.3
Dollar Libilities | Time Liabilities |  |  | Quality Gates Progress |  |  |  | Abba Chart | BAC = | 10000000
2500 | 20 |  |  | Planned | Actual | Planned | Actual | EAC | BCWP | ACWP | Efficiency Required to Meet the Estimate at Completion (TCPI) | Efficiency at Completion | Cumulative CPI | Current CPI (Monthly Efficiency) | CM Churn | Req Change | Vol Turn | Overtime | EAC | BAC | CPI | TCPI
12300 | 6 |  | 1 | 5 | 4 | 5 | 4 | 10000000 | 500000 | 650000 | 1.016 | 1 | 0.76923 | 0.76923 | 0.02 | 0.033333 | 0.066667 | 0.076923 | 10000000 | 10000000 | 0.76923 | 1.016
8000 | 12 |  | 2 | 7 | 3 | 12 | 7 | 11000000 | 470000 | 900000 | 0.94356 | 0.90909 | 0.62581 | 0.52222 | 0 | 0.03125 | 0.028571 | 0.14815 | 11000000 | 10000000 | 0.62581 | 0.95556
4000 | 2.4 |  | 3 | 7 | 4 | 19 | 11 | 11500000 | 1030000 | 950000 | 0.85024 | 0.86957 | 0.8 | 1.0842 | 0.05 | 0.02 | 0.0125 | 0.25 | 11500000 | 10000000 | 0.8 | 0.88889
1500 | 2.4 |  | 4 | 6 | 6 | 25 | 17 | 12000000 | 1000000 | 1200000 | 0.83333 | 0.83333 | 0.81081 | 0.83333 | 0.030769 | 0.010204 | 0.023529 | 0.037879 | 12000000 | 10000000 | 0.81081 | 0.84337
5000 | 3 |  | 5 | 10 | 0 | 35 | 17 | 0 | -3000000 | -3700000 | 3.5135 | #DIV/0! | #DIV/0! | 0.81081 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
5000 | 2.5 |  | 6 | 12 | 0 | 47 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 7 | 15 | 0 | 62 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 8 | 13 | 0 | 75 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 9 | 11 | 0 | 86 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 10 | 16 | 0 | 102 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 11 | 12 | 0 | 114 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 12 | 5 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 13 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 14 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 15 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 16 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 17 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 18 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 19 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 20 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 21 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 22 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 23 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 24 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 25 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 26 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 27 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 28 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 29 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 30 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 31 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 32 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 33 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 34 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 35 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 36 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 37 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 38 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 39 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 40 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 41 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 42 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 43 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 44 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 45 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 46 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 47 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 48 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 49 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!
0 | 0 |  | 50 | 0 | 0 | 119 | 17 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 10000000 | #DIV/0! | #DIV/0!

## DialDialog (hidden)
Edit Dial Gauge: Sample gauge 4 (Units)
OK
Cancel
Greater than Critical Value
Less than Critical Value
Minimum
Maximum
Scale label
Critical Value:
Direction of redzone:
Redzone
Value to display
Number, Named Range, or Formula containing a Cell Reference:
10
20
30
40
50
60
70
Test Guage 1
1 2 3 4 5
6 7 8 9 10
11 12 13 14 15
16 17 18 19 20
Location of gauge (enter grid cell #):
Gauge Position
Gauge Caption:

## BarDialog (hidden)
Edit Bar Gauge: Sample Gauge number 3 ($)
OK
Cancel
Minimum
Maximum
Scale label
Arrow definitions
Caption
Value to display
Text Label:
Number, Named Range or Formula:
EAC
BAC
Test Guage number12
$ Millions
Refresh
0
25
50
75
100
Arrow 1
Arrow 2
1 2 3 4 5
6 7 8 9 10
11 12 13 14 15
16 17 18 19 20
Gauge Placement
Example
Number (eg. 40), Named Range (eg. BarValue), or Formula (eg. ='DataSheet'!A1:B1):
Location of gauge (enter grid cell #):

## SelectTypeDialog (hidden)
Select Gauge Type
OK
Cancel

## SelectEditDialog (hidden)
Select Gauge to Remove
OK
Cancel

## CP_DialGauges (hidden)
Worksheet | Rect Top | Rect Left | Rect Width | Rect Height | Min | Max | Value | Redline Value | Redline Direction | Number of tics | Caption | Position | Enabled
Control Panel | 24 | 195 | 70 | 56 | 0.6 | 1.4 | 0.81081 | 1 | FALSE | 9 |  |  | Yes
Control Panel | 24 | 263 | 70 | 56 | 0.6 | 1.4 | 0.84337 | 1 | TRUE | 9 |  |  | Yes
Control Panel | 168 | 18 | 80 | 66 | 0 | 4 | 3.0769 | 2 | TRUE | 9 |  |  | Yes
Control Panel | 168 | 97 | 80 | 66 | 0 | 4 | 1.0204 | 2 | TRUE | 9 |  |  | Yes
Control Panel | 168 | 189 | 80 | 66 | 0 | 4 | 2.3529 | 2 | TRUE | 9 |  |  | Yes
Control Panel | 168 | 265 | 80 | 66 | 0 | 80 | 3.7879 | 30 | TRUE | 9 |  |  | Yes

## CP_BarGauges (hidden)
Worksheet | Rect Top | Rect Left | Rect Width | Rect Height | Arrow 1 | Arrow 2 | Arrow Label 1 | Arrow Label 2 | Min | Max | Value | Units | Caption | Position | Enabled
Control Panel | 68 | 79 | 100 | 11 | 3500000 | 10000000 | BCWS | BAC | 0 | 12000000 | 3000000 | $ Millions | Earned Value (BCWP) |  | Yes
Control Panel | 106 | 79 | 100 | 11 | 12000000 | 0 | EAC |  | 0 | 12000000 | 3700000 | $ Millions | Actual Cost (ACWP) |  | Yes
Control Panel | 142 | 79 | 100 | 11 | 0 | 0 |  |  | 0 | 12 | 4 | Months | Elapsed Time |  | Yes

## SplashScreen (hidden)
SPMN Project Control Panel
OK
Project Control Panel
Version 2.0.1 for MS Excel 95/97
July 1998
Software Program Managers Network
(703)521-5231
John E. Moore PhD Kimberly C. Daines

## AboutBox (hidden)
About Project Control Panel
OK
Project Control Panel
Version 2.0.1 for MS Excel 95/97
July 1998
Developed for the Software Program Managers Network (SPMN)
by Computers and Concepts Associates
John E. Moore, PhD Kimberly C. Daines
For support please contact the SPMN:
(703)521-5231
cntrlpnl@spmn.com