Euromethod
Concepts Manual 3
Strategy Model

EM-3.3-SM

__________________________________

Abstract

This manual is one of three Euromethod Concepts Manuals. There is one manual for each of the models in Euromethod which between them contain all of the concepts provided by Euromethod.

The Euromethod Strategy Model provides the set of concepts necessary to apply a situational approach to IS-adaptation. Its purpose is to support the definition or assessment of an IS-adaptation strategy that is tailored to specific characteristics of a problem situation.

__________________________________

© Euromethod Project 1994

This document,

Euromethod Concepts manual 3 - Strategy Model,

is a document of the Euromethod Version 0.

In the layered document structure of Euromethod it constitutes a part of the Concepts Manuals Level. It is referenced by the Guides and the Overview; and makes use of the definitions in the Dictionary.

ContentsÊofÊtheÊStrategyÊModel

1.	Introduction	4

1.1.	Objectives	4

1.2.	SituationalÊApproach	4

1.3.	TheÊEuromethodÊStrategyÊModel	5

1.4.	TheÊDesignÊProcess	7

2.	Overview	8

3.	SituationalÊFactors	16

3.1.	TargetÊDomainÊFactors	18

3.1.1.	InformationÊSystem	18

3.1.2.	ComputerÊSystem	26

3.2.	ProjectÊDomainÊFactors	30

3.2.1.	ProjectÊTask	30

3.2.2.	ProjectÊStructure	32

3.2.3.	ProjectÊActors	33

3.2.4.	ProjectÊTechnology	34

4.	StrategyÊOptionsÊandÊHeuristics	36

4.1.	SystemÊInstallationÊApproach	38

4.2.	SystemÊConstructionÊApproach	39

4.3.	SystemÊDescriptionÊApproach	42

4.4.	ProjectÊControlÊApproach	44

5.	LimitationsÊofÊtheÊState-of-the-art	48

5.1.	EffectivenessÊofÊtheÊsituationalÊapproaches	48

5.2.	AssessmentÊofÊsituationalÊfactors	49

5.3.	DeterminationÊofÊtheÊIS-adaptationÊstrategy	50

References	51

Index	53

# 1.	Introduction

This manual is one of three Euromethod Concepts Manuals: Transaction Model, Deliverable Model and Strategy Model. There is one manual for each of the models in Euromethod which between them contain all of the concepts provided by Euromethod.

## 1.1.	Objectives

The objective of this manual is to describe the Euromethod concepts that constitute the Strategy Model, and which thus provide the basis for the guidance supplied by the Euromethod guides, and in particular, the Delivery Planning Guide.

The manual is intended to serve as a reference manual of the Euromethod concepts providing additional support to the information provided within the Euromethod guides. It is therefore expected that readers of this manual will come to it, as a means of obtaining clarification or greater detail regarding a concept described within the Euromethod guides, or possibly even the overview.

## 1.2.	SituationalÊApproach

Euromethod is concerned with problem situations where an organisation has recognised some needs for adaptation of the information system of a target domain and where the IS-adaptation may be regulated by a contract with a supplier. It is generally acknowledged that problem solving approaches are not universal and should depend on the problem situation. Therefore, Euromethod adopts a situational approach to the issue of defining an IS-adaptation strategy that is adequate to a particular problem situation (see Figure 1). An IS-adaptation strategy is the intended approach to achieve the objectives of the IS-adaptation.

Figure 1: An IS-adaptation strategy depends on the problem situation.

The need for tailoring an IS-adaptation strategy to the problem situation has been expressed by practitioners in IS-adaptation and situational approaches are considered as a major potential improvement area within current IS-development methods. In Euromethod the term is used with the following meaning:

Situational approach:

A problem solving approach which takes account of the properties of the problem situation, called situational factors, to determine the most suitable problem solving strategy. A situational approach has to assess the situational factors, estimate their likely consequences and propose appropriate problem solving strategies.

## 1.3.	TheÊEuromethodÊStrategyÊModel

The Euromethod Strategy Model provides the set of concepts necessary to apply a situational approach to IS-adaptation (see Figure 2). Its purpose is to support the definition or assessment of an IS-adaptation strategy that is tailored to specific characteristics of a problem situation.

An IS-adaptation strategy is defined in terms of a selected set of IS-adaptation strategy options. IS-adaptation strategy options are those options from which an IS-adaptation strategy must be selected when planning a particular IS-adaptation. The IS-adaptation strategy options are defined within the following approaches which are important from the customer-supplier relationship point of view:

¥	The system installation approach,

which defines how the information system is going to be installed in the target domain.

¥	The system construction approach,

which defines how the information system is going to be constructed and tested.

¥	The system description approach,

which defines how the information system is going to be designed and described.

¥	The project control approach,

which defines how the project is going to be controlled.

The selection of options for each of the approaches, i.e. the selection of the IS-adaptation strategy, depends upon the situational factors for the IS-adaptation in question. Heuristics for this selection are provided by the Strategy Model, thus facilitating the:

¥	Definition of an IS-adaptation strategy based upon a set of situational factors.

¥	Assessment of an IS-adaptation strategy against a set of situational factors.

Figure 2: A situational approach: The Euromethod Strategy Model.

An IS-adaptation strategy places general requirements on the decision points of an IS-adaptation, e.g. requirements to the sequence of changes of the information system through installation of operational items.

A decision point is a point in time where the customer, possibly together with the supplier, is making decisions on the information system adaptation. A decision point is characterised by the decisions that are made, the roles involved in these decisions, the transactions that take place and thus the deliverables that are exchanged. These deliverables serve as a basis for the decisions.

## 1.4.	TheÊDesignÊProcess

The design of the Euromethod Strategy Model has been based on an analysis of the existing situational approaches [Dav82, Boe91, Alt, McF82, Ahi, Gib] In addition, some recent work on situational approaches has been used [DoD, Mat, Mor, Rob, Rop, Saar, VM92]

The sources referenced above made use of different concepts and approaches. Therefore, it has been necessary to structure that knowledge and to integrate the approaches. Some critical review has also been performed: the concepts and rules that were insufficiently justified or proven were discarded. Finally, the concepts and terminology have been made consistent with the other parts of Euromethod. The final result of this process is the Euromethod Strategy Model.

During the design of the Euromethod Strategy Model, some limitations in the state-of-the-art of situational approaches have been recognised. The required research to change the limitations is outside the scope of Euromethod Phase 3A. The limitations are described in Chapter 5.

# 2.	Overview

The Strategy Model supports the customer-supplier relationships within an IS-adaptation by providing concepts that can be used to facilitate the mutual understanding between customers and suppliers regarding the:

¥	Appreciation of a problem situation in which a customer wants to perform an IS-adaptation by contracting some of the work to one or more suppliers.

¥	Definition of a suitable strategy for the IS-project contracted to a supplier.

¥	Understanding and assessment of the suitability of a strategy for an IS-adaptation.

The concepts in the Strategy Model, illustrated in Figure 2, are further detailed in Figure 3. The concepts can be used in a dynamic way during an IS-adaptation by a customer or a supplier. A customer and a supplier can use the Strategy Model several times in the tendering, production and completion processes that are described in the Transaction Model. The situational factors are classified by the:

¥	Domain they are related to: target domain or project domain, each containing domain sub-groups; and the

¥	Knowledge characteristics they represent: either complexity or uncertainty.

The domain classifications support the analysis of the problem situation and the knowledge characteristics support the selection of suitable IS-adaptation strategy options. The situational factors are described in more detail in Section 3.

The IS-adaptation strategy options are defined within four approaches that are considered important from the customer-supplier relationship point of view:

¥	The system installation approach,

which defines how the information system is going to be installed in the target domain.

¥	The system construction approach,

which defines how the information system is going to be constructed and tested.

¥	The system description approach,

which defines how the information system is going to be designed and described.

¥	The project control approach,

which defines how the project is going to be controlled.

The IS-adaptation strategy options are described in more detail in Section 4.

The IS-adaptation strategy heuristics are heuristics regarding the suitability of the IS-adaptation strategy options in a problem situation characterised by a set of situational factor values, e.g. an evolutionary system installation approach is suitable when the situation is uncertain. The IS-adaptation strategy heuristics are described in relation to the IS-adaptation strategy options in Section 4.

Figure 3: Overview of the Euromethod Strategy Model.

Figures 4 and 5 contain an overview of all the situational factors defined in the Strategy Model with their relations to the target and project domain and knowledge characteristics. Figures 4 and 5 also contain the situational factor values defined within the Strategy Model and their relations to the assessment of the complexity and uncertainty of a situation. Figure 6 contains an outline of the different IS-adaptation strategy options defined in the Strategy Model.

The limitations of the list of situational factors and the IS-adaptation strategy heuristics are explained in Chapter 5. From those limitations, it can be derived that:

The list of situational factors and the heuristics are neither definitive nor exhaustive. They are examples that can be used and enhanced based upon personal and organisational experience. The heuristics contain no complex relations, e.g. dependencies, between the situational factors.

| Knowledge Characteristic | Complexity | Values |  |  | Uncertainty | Values |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Target Domain |  | simple | moderate | com-plex |  | cer-tain | moderate | uncertain |
| Information System | Heterogeneity of actors | low | medium | high | Attitude of actors | posi-tive | neu-tral | negative |
|  | Size of target domain | small | medium | large | Ability of actors | high | medium | low |
|  | Size of distribution | small | medium | large | Stability of environment | high | medium | low |
|  | Complexity of information | low | medium | high | Formality of information | high | medium | low |
|  | Complexity of business processes | low | medium | high | Formality of business processes | high | medium | low |
|  |  |  |  |  | Stability of information and business processes | high | medium | low |
|  |  |  |  |  | Specificity of information system | low | medium | high |
|  |  |  |  |  | Understandability of existing system | high | medium | low |
|  |  |  |  |  | Strategic importance | low | medium | high |
|  |  |  |  |  | Importance of organisational changes | low | medium | high |
|  |  |  |  |  | Availability, clarity & stability of requirements | high | medium | low |
|  |  |  |  |  | Quality of existing specifications | high | medium | low |
| Computer System | Complexity of data | low | medium | high | Importance of technological changes | low | medium | high |
|  | Complexity of computerised functions | low | medium | high |  |  |  |  |
|  | Complexity of non-functional requirements | low | medium | high |  |  |  |  |
|  | Number of replications of computer system | one | few | ma-ny |  |  |  |  |
|  | Complexity of target technology | low | medium | high | Novelty of target technology | low | medium | high |

Figure 4: Situational factors characterising the target domain.

| Knowledge Characteristic | Complexity | Values |  |  | Uncertainty | Values |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Domain |  | simple | moderate | com-plex |  | cer-tain | moderate | uncertain |
| Project Task | Size of Project | small | medium | large | Novelty of IS-adaptation | low | medium | high |
|  | Complexity of migration | small | medium | large | Adequacy of schedules | - | nor-mal | tight |
|  |  |  |  |  | Adequacy of budget | - | nor-mal | tight |
| Project Structure | Number of sub-contractors | none | few | ma-ny | Dependency on sub-contractors | none | low | high |
|  | Number of interfaces to other IS-adaptations | none | few | ma-ny | Dependency on other IS-adaptations | none | low | high |
|  |  |  |  |  | Formality of customer-supplier context | high | medium | low |
| Project Actors | Number of project actors | small | medium | large | Capability of project team | high | medium | low |
| Project Technology | Complexity of develop-ment technology | low | medium | high | Novelty of develop-ment technology | low | medium | high |
|  |  |  |  |  | Availability of appro-priate dev. technology | high | medium | low |

Figure 5: Situational factors characterising the project domain.

| Approach | Options |
| --- | --- |
| System installation approach | 1. One shot installation: ¥ only one version. 2. Incremental installation: ¥ successive parts ¥ no change of requirements and specifications after first installation. 3. Evolutionary installation: ¥ successive versions ¥ changes of requirements and specifications are possible after learning from usage. |
| System construction approach | 1. One shot construction: ¥ only one version. 2. Incremental construction: ¥ successive parts ¥ no change of requirements and specifications after first construction. 3. Evolutionary construction: ¥ successive versions ¥ changes of requirements and specifications are possible after learning from test. |
| System description approach | 1. Mode of operation: ¥ Analytical: use of abstraction/specifications ¥ Experimental: use of experiments/prototypes. 2. Type of co-operation: ¥ Expert-driven: production and assessment separated ¥ Participatory: joint production and assessment. |
| Project control approach: ¥ Development control ¥ Quality control ¥ Configuration control | 1. Frequency: frequent or seldom. 2. Formality: degrees of formality. 3. Customer responsibility: different kinds of responsibility. |

Figure 6: IS-adaptation strategy options.

ExampleÊofÊIS-adaptationÊstrategy

Consider the situation in which a customer organisation has defined the following simplified IS-adaptation strategy as part of the IS-adaptation requirements within the call for tender document. From this example, it can be seen that the IS-adaptation strategy options can be combined in a flexible way and define a variety of overall approaches:

¥	Analytical and participatory description has been selected:

That is, an analytical method to specify the information system shall be used by the customer and supplier organisations in a joint description process with participation of user-representatives.

¥	Evolutionary construction and installation has been selected:

That is, information system versions are outlined with a description of their purposes, benefits and interfaces to existing information systems.

¥	Frequent and formal development, quality and configuration control has been selected:

That is, decision points regarding direction and quality of the target domain deliverables shall be scheduled every 4 months. A formal review technique shall be used in the quality control of the most important target domain deliverables. The requirements to the maintenance of target domain deliverables shall be well-defined.

¥	Customer responsibility is defined regarding the:

-	Quality control of the specifications of the system.

-	Configuration control of the specifications.

-	Generation of test cases that cover critical situations from the business point of view.

-	Installation of the new information system.

ExamplesÊofÊIS-adaptationÊstrategyÊheuristics

The IS-adaptation strategy heuristics are defined in relation to each of the four approaches. Heuristics regarding the overall IS-adaptation strategy, i.e. a combination of IS-adaptation strategy options are provided within the Delivery Planning Guide. The following are examples of heuristics described in Section 4:

¥	An experimental and participatory description approach is suitable when the situation is uncertain and the ability of the actors of the information system is sufficiently high and the adequacy of schedules is normal.

¥	A one shot installation approach is suitable when project schedules are normal, and the situation is not complex and not uncertain.

¥	An incremental or evolutionary installation approach is suitable when project schedules are tight, i.e. it is necessary to install something useful as fast as possible.

¥	An evolutionary installation approach is suitable when the importance of organisational changes is high.

¥	High degree of formality in development control is suitable when the situation is complex or uncertain.

¥	Frequent development and configuration control is suitable when dependencies are high or the stability is low, i.e. when:

-	Dependency of sub-contractors is high.

-	Dependency of other IS-adaptations is high.

-	Stability of information and business processes is low.

-	Availability, clarity and stability of requirements to the IS-adaptation is low.

# 3.	SituationalÊFactors

The situational factors are classified into two dimensions: the domain and the knowledge characteristic. These are treated as orthogonal dimensions.

¥	Domain:

The domain of which the situational factor is a property. The Strategy Model considers two domains:

-	Target : The part of the organisation for which the information system should be adapted.

-	Project : The organisation which performs the adaptation of the information system.

¥	Knowledge :

The characteristic of the knowledge that can be gathered to handle the problem situation. The Strategy Model considers two knowledge characteristics which are the:

-	Complexity of the knowledge that can be gathered to handle the problem situation; factors of this class show complexity in the problem situation when they take certain values. Complexity can be regarded as the difficulty encountered in managing the available knowledge. The scale for complexity of a situation is: simple, moderate, complex.

-	Uncertainty of the knowledge that can be gathered to handle the problem situation; factors of this class show uncertainty in the problem situation when they take certain values. Uncertainty can be regarded as the lack of available knowledge. The scale for uncertainty of a situation is: certain, moderate, uncertain.

As shown later on, a situational factor may affect the suitability of an IS-adaptation strategy individually and through its contribution to the uncertainty and the complexity.

StructureÊofÊsituationalÊfactorÊdescription

The description of a situational factor contains the following elements:

¥	Sources: references to the main sources for the situational factor from the study of the state-of-the-art of contingency models.

¥	Definitions of concepts to explain the situational factor.

¥	Values to be used in the assessment of the problem situation.

¥	Additional guidance, if the sources contain more operational assessment guidance.

¥	Sub-factors, if the factor is composed of several sub-factors.

¥	The risk of adverse consequences related to certain values of the factor. These risks are inherent in the problem situation described by the situational factor with that value. Accordingly, each risk is described in terms of the uncertain events that can occur in the problem situation:

-	For complexity factors, risks are related to management (loss of control of the project) and design (information system not working or incapable to deal with the complexity).

-	For uncertainty factors, risks are mentioned for each factor.

¥	Inhibition actions, when there are concrete measures which possibly inhibit the risks by changing the individual situational factor value. The situational factor value is changed by addressing the underlying problem. The proposed inhibition actions are examples and inhibition actions are not possible for all situational factors, e.g. the complexity and formality of information and business processes.

The elements are only covered when it is relevant. That means, some of the elements can be missing in some situational factor descriptions.

## 3.1.	TargetÊDomainÊFactors

The .i.target domain factor;s are grouped into two classes:

1.	Information system:

Those situational factors that are properties of the information system which should be adapted.

2.	Computer system:

Those situational factors that are properties of the computer system of the target domain.

### 3.1.1.	InformationÊSystem

3.1.1.1.	ComplexityÊofÊinformationÊsystem

HeterogeneityÊofÊactors

Sources:	[Dav82]

The actors may be heterogeneous for organisational reasons, political reasons or individual reasons.

¥	Example of organisational reason:

-	Different business areas or organisational units in an enterprise may have different views on a situation or different interests.

-	A management level and an operational level may have different views on a situation or different interests.

¥	Example of political reason:

-	There may be power conflicts within the actor group and the information system may be considered as an instrument of power.

¥	Example of individual reason:

-	Different individuals have different personalities and cognitive styles, e.g. analytical or intuitive.

Values:  	[low, medium, high]

When heterogeneity of the actors is high, there is a risk of:

¥	Conflicting requirements to the IS-adaptation.

¥	IS-adaptation not accepted by some actors.

Inhibition actions when heterogeneity is high:

¥	Designating one representative of the actors solving the conflicts, interfacing with the IS-adaptation and influencing the customer deciders.

¥	Creating consensus about the IS-adaptation.

SizeÊofÊtargetÊdomain

Sources:	[Ahi]

The size of the target domain can be expressed in terms of business areas (functional perspective) and organisational units (organisational perspective). See Deliverable Model.

Values:  	[small, medium, large]

Additional guidance:

¥	Large domain: The whole enterprise, or several business areas and/or organisational units.

¥	Medium domain: One business area in several organisational units, or several business areas in one organisational unit.

¥	Small domain: One business area in one organisational unit, or part of it.

SizeÊofÊdistributionÊofÊinformation system

The size of distribution describes the number of geographical sites which the information system is spread over.

Values:  	[small, medium, large]

ComplexityÊofÊinformation

Sources:	[VM92]

This information is the information resource of the target domain.

Values:   	[low, medium, high]

Additional guidance: A simplified method is recommended to classify the complexity of information. An example of the complexity of information which can be represented in a sequential or entity-relationship structure is presented in Figure 7. classified by means of the number of entities and the number of internal links (relationships or hierarchy levels). This table should be tailored to reflect the experience of each organisation making use of the Strategy Model.

| Complexity of Information | No. of Entities |  | No. of Relationships |  | No. of Attributes |
| --- | --- | --- | --- | --- | --- |
| low | < 10 | and | < 10 | or | < 20 |
| medium | < 40 | and | < 40 | or | < 100 |
| high | > 40 | or | > 40 | or | > 100 |

Figure 7: Example of classification of the complexity of information [VM92].

ComplexityÊofÊbusinessÊprocesses

Sources:	[VM92]

These business processes are the business processes of the target domain.

Values:   	[low, medium, high]

Sub-factors:

¥	Number of business processes.

¥	Number of process interfaces.

¥	Complexity of the business rules and algorithms.

3.1.1.2.	UncertaintyÊofÊinformationÊsystem

AttitudeÊofÊactorsÊtowardsÊthe informationÊsystemÊadaptation

Sources:	[Alt, Gib]

The attitude of human actors may be negative for organisational reasons, political reasons or individual reasons (see heterogeneity of the actors).

Values:  	[positive, neutral, negative]

Sub-factors:

¥	Actor perception of the need for the IS-adaptation.

¥	Level of commitment and involvement by the target domain management.

¥	Willingness to accept the change.

When the attitude of human actors is negative, there is a risk of:

¥	Lack of actor-participation.

¥	IS-adaptation not accepted by actors.

¥	Developing wrong information system.

Inhibition when the attitude of actors is negative:

¥	Actor motivation.

¥	Selling the IS-adaptation to the actors.

AbilityÊofÊactors

Sources:	[Dav82]

The ability of the actors concerns the human actors.

Values:  	[high, medium, low]

Sub-factors:

¥	Ability to specify requirements to the IS-adaptation.

¥	Experience with IS-adaptation.

¥	Experience with computer system.

¥	Capacity for abstraction.

When ability of the actors is low, there is a risk of:

¥	Uncertain or unfeasible requirements to the IS-adaptation.

¥	Developing wrong information system.

Inhibition when the ability of actors is low:

¥	Actor training.

StabilityÊofÊenvironment

Sources:	[EMPMB]

The stability of the environment of the target domain.

Values:  	[high, medium, low]

Sub-factors:

¥	Political stability (e.g. changes of governments).

¥	Legal stability (e.g. changes in law and regulations).

¥	Market stability (e.g. changes in the offer and demand, changes in the competition).

¥	Business stability (e.g. changes in the nature of the business).

¥	Financial stability (e.g. changes in the financial situation).

When stability of the environment is low, there is a risk of:

¥	Evolving requirements to the IS-adaptation.

¥	Developing wrong information system.

FormalityÊofÊinformation

This information is the information resource of the target domain.

Formality is the conformity to rules and structure.

Values:   	[high, medium, low]

Additional guidance:

¥	High formality refers to well structured information for which the range of values is well defined.

¥	Medium formality refers to structured information for which the range of values is not well defined.

¥	Low formality refers to weakly structured information for which the range of values is fuzzy.

When the formality of the information is low, there is a risk of:

¥	Uncertain or unfeasible requirements to the IS-adaptation.

¥	Unfeasible information system.

FormalityÊofÊbusinessÊprocesses

Sources:	[Dav82]

These business processes are the business processes of the target domain.

Formality is the conformity to rules and elaborate procedures.

Values:   	[high, medium, low]

Additional guidance:

¥	High formality refers to procedural processes: These processes are often found in administrative, operational and technical information systems.

¥	Medium formality refers to non procedural processes containing well defined rules.

¥	Low formality refers to non procedural processes with fuzzy rules: These processes are often found in executive information systems.

When the formality of the business processes is low, there is a risk of:

¥	Uncertain or unfeasible requirements to the IS-adaptation.

¥	Unfeasible information system.

StabilityÊofÊinformationÊandÊbusiness processes

Sources:	[Boe91, Dav82, VM92]

Values:  	[high, medium, low]

Sub-factors:

¥	Stability of the information in the target domain.

¥	Stability of the business processes in the target domain.

Additional guidance:

¥	High stability: only a minimum of changes is to be expected.

¥	Medium stability: (regularly realised) adaptations of local type are to be expected.

¥	Low stability: essential changes are very probable (e.g. by changing a law).

When the stability of the information is low, there is a risk of:

¥	Evolving requirements to the IS-adaptation.

¥	Developing wrong information system.

SpecificityÊofÊinformationÊsystem

Sources:	[Saar]

A specific information system has characteristics that make it distinct from other information systems.

Values:  	[low, medium, high]

Additional guidance:

¥	Low specificity is related to standard types of information system existing in many organisations.

¥	Medium specificity is related to types of information system existing in a certain class of organisations.

¥	High specificity is related to types of information system which do not exist or exist rarely in other organisations.

When the specificity of the information system is high, there is a risk of:

¥	Uncertain or unfeasible requirements to the IS-adaptation.

.i.UnderstandabilityÊofÊexistingÊinformationÊsystem

Sources:	[Rob]

Values:  	[high, medium, low]

When the understandability of existing information system is low, there is a risk of:

¥	Developing the wrong information system.

¥	Unpredictable costs for the organisation if maintenance is required.

¥	Unpredictable costs for the project if existing information system has to be taken into account.

Inhibition when understandability is low:

¥	Re-engineering.

StrategicÊimportanceÊofÊinformation system

Sources:	[EMPMB]

Importance of the strategic opportunities offered by the information system to the organisation.

Values:  	[low, medium, high]

When the strategic importance of the information system is high, there is a risk of:

¥	Unpredictable costs for the organisation.

¥	Business implications of IS-adaptation failure.

ImportanceÊofÊorganisationalÊchanges

Sources:	[Alt, Gib]

Importance of the changes in the target domain organisation.

Values:  	[low, medium, high]

Sub-factors:

¥	Impact of the IS-adaptation on the organisation structure and responsibilities.

¥	Impact of the IS-adaptation on actors' tasks.

When the importance of organisational changes is high, there is a risk of:

¥	IS-adaptation not accepted by actors.

¥	Unpredictable costs for the organisation.

¥	Business implications of IS-adaptation failure.

Availability, clarity and stability of requirements to the information system

Sources:	[Alt, Boe91, Dav82, Saar]

Requirements are the essential conditions that an information system has to satisfy.

Values:   	[high, medium, low]

Sub-factors:

¥	Availability of requirements to the information system.

¥	Clarity of requirements to the information system.

¥	Stability of requirements to the information system.

When the availability, clarity and stability of the requirements to the information system is low, there is a risk of:

¥	Uncertain and evolving requirements to the IS-adaptation.

¥	Uncertain interfaces to other information systems.

Inhibition when availability or clarity of requirements to the information system are low:

¥	Making a stringent requirements analysis.

QualityÊofÊexistingÊspecifications

Sources:	[Boe91, Dav82]

Specification is a formulation, in document form, which provides a definitive description of a system for the purpose of developing or validating the system. Specifications may exist at the start of a project depending on the work which has already been performed regarding the system.

Values:   	[high, medium, low]

When the quality of the existing specifications is low, there is a risk of:

¥	Developing the wrong information system.

¥	Unpredictable project costs.

Inhibition when the quality of the existing specifications is low:

¥	Redoing specifications.

¥	Review existing specifications with the actors of the information system.

### 3.1.2.	ComputerÊSystem

3.1.2.1.	ComplexityÊofÊcomputerÊsystem

ComplexityÊofÊdata

Sources:	[VM92]

These data are the representation of the information of the target domain stored in the computer system.

The choice between information and data to assess the complexity depends on the knowledge which is currently available on a problem situation, and the type of project task being performed (For example, requirements analysis of the information system, implementation of a computer system, etc.).

Values:   	[low, medium, high]

Additional guidance: refer to Complexity of the information.

ComplexityÊofÊcomputerisedÊfunctions

Sources:	[VM92]

These functions are the parts of the processes which are performed by the computer system.

The choice between business process and function to assess the complexity depends on the knowledge which is currently available on a problem situation, and the type of project task (e.g. requirements analysis of the information system, implementation of the computer system, etc.).

Values:   	[low, medium, high]

Sub-factors:

¥	Number and Complexity of the user interfaces.

¥	Number and Complexity of interfaces to other information systems.

¥	Number and Complexity of sub-functions.

¥	Number of internal interfaces.

Additional guidance: The estimate of the complexity of a function is a difficult issue which is also tackled by the methods for project estimation like Function Points Analysis (proposed for the first time by A. Albrecht in 1979). The way to estimate the complexity of a function depends on the available knowledge about the function at the time of the estimate.

At a high level of aggregation, function complexity may be evaluated by the complexity of its interfaces and the complexity of its structure. At a low level, the complexity of the rules or algorithms or the number of lines of codes may be considered.

As an example, V-Model [VM92] recommends a simplified method to classify the complexity of functions. This complexity is in Figure 8 classified based on the number of sub-functions, the number of interfaces and the code length. This table should be tailored to reflect the experience of each organisation making use of the Strategy Model.

| Complexity of Functions | No. of Sub-Functions |  | No. of Interfaces |  | No. of Program Lines |
| --- | --- | --- | --- | --- | --- |
| low | < 10 | and | < 10 | and | < 100 |
| medium | < 30 | and | < 30 | and | < 300 |
| high | > 30 | or | > 30 | or | > 300 |

Figure 8: Example of classification of complexity of computerised functions. [VM92]

Complexity of non-functional requirements to computer system

Sources:	[ISO-9126, VM92]

Values:   	[low, medium, high]

Functional requirements relate to the inputs of the computer system from its environment, its outputs to the environment, and the logical relationships between them. Non-functional requirements relate to the quality of the information system and resourcing constraints.

The following list of sub-factors is taken from the ISO-9126 Standard and the V-Model [VM92] It is given as an example and does not pretend to provide a definitive view on non-functional requirements. The estimate of these values for each of the listed sub-factors, depends on the type of information system. Therefore, Euromethod recommends to refer to the existing body of knowledge about non-functional requirements for the type of information system of interest.

Sub-factors:

¥	Efficiency:

The relationship between the level of performance of the system (or a component) and the amount of resources used, under stated conditions. Efficiency may be related to time behaviour (response time, processing time, throughput rates) and to resource behaviour (amount of resources used and duration of such use).

¥	Security:

Ability of the system (or a component) to prevent unauthorised access, whether accidental or deliberate, to programs and data.

¥	Criticality:

The criticality of the system (or a component) expresses the significance which will be given to that system or component in case of a functional failure. The criticality is expressed in levels; the higher the level, the more severe the consequences are in case of a functional failure.

¥	Reliability:

The capability of the system (or a component) to maintain its level of performance under stated conditions for a stated period of time. The mean time to failure metric is often used to assess reliability. The necessary reliability can be secured through defining the:

-	Necessary level of protection against failures.

-	Necessary measures for recovery from failures.

¥	Maintainability:

Maintainability bears on the effort needed to make specified modifications to the system (or a component).

Modification may include corrections, improvements or adaptation to changes in environment, and in requirements and functional specifications.

¥	Portability:

The ability of the system (or one of its components) to be transferred from one environment to another.

¥	Usability:

Usability bears on the effort needed for the use of the system (or one of its components) by the actors.

NumberÊofÊreplicationsÊofÊcomputer system

Sources:	[Comp]

Replication is the number of copies of the computer system that have to be installed.

Values:   	[one, few, many]

ComplexityÊofÊtargetÊtechnology

Sources:	[Alt, Boe91]

The target technology is the one used for the hardware and system software platform of the computer system.

Values:   	[low, medium, high]

3.1.2.2.	UncertaintyÊofÊcomputerÊsystem

ImportanceÊofÊtechnologicalÊchanges

Sources:	[Alt, Boe91]

Technological changes are changes in the computer system technology.

Values:  	[low, medium, high]

When the importance of technological changes is high, there is a risk of:

¥	Shortfalls in non functional requirements.

¥	IS-adaptation not accepted by actors.

¥	Developing wrong information system.

¥	Unpredictable costs for the organisation.

NoveltyÊofÊtargetÊtechnology

Sources:	[EMPMB]

This novelty factor is a measure of how innovative the target technology is with respect to the state-of-the-art. The target technology is the technology used for the hardware and system software platform of the computer system.

Values:  	[low, medium, high]

When the novelty of the target technology is high, there is a risk of:

¥	Shortfalls in non-functional requirements.

¥	Unfeasible information system.

¥	Unpredictable costs for the project.

## 3.2.	ProjectÊDomainÊFactors

In accordance with Leavitt [Lea], Euromethod "views the organisation as a multivariate system, in which at least four interacting variables loom especially large: the variables of task, structure, technology, and actors (usually people)". The project domain factors are grouped into four classes according to the four variables in Leavitt's model by use of the following definitions:

¥	A project task is:

a well defined work assignment for a project actor. It is a process subject to management accountability.

¥	The project structure is:

the systems of communication, the systems of authority, and the system of work flows in the project.

¥	A project actor is:

a performer of a part of the project.

¥	The project technology is:

the methods, the techniques and the tools used in the project.

### 3.2.1.	ProjectÊTask

The following situational factors are properties of the project domain, which relate to the task and sub-tasks of the project.

3.2.1.1.	ComplexityÊofÊprojectÊtask

SizeÊofÊproject

Sources:	[McF82, Saar, VM92]

The size of a project may be represented by the development effort, expressed as a number of person months or years. The size of a project is usually estimated on the basis of the complexity of the functions and the information of the system. This factor is then dependent on the complexity of the functions and the information.

Values:   	[small, medium, large]

ComplexityÊofÊmigration

Complexity of migration is the measure of the difficulty in migrating from the initial state information system to the final state information system across all the operational sites within the target domain.

Values:  	[low, medium, high]

Additional Guidance:	The complexity of migration is high when there are a lot of interfaces between the existing unchanged sub-systems and the sub-systems that have been changed or added.

3.2.1.2.	UncertaintyÊofÊprojectÊtask

NoveltyÊofÊIS-adaptation

Sources:	[Ahi]

This novelty factor is a measure of how innovative the IS-adaptation is with respect to the state-of-the-art.

Values:   	[low, medium, high]

When the novelty of IS-adaptation is high, there is a risk of:

¥	Unfeasible information system.

¥	Unpredictable costs for the project.

AdequacyÊofÊschedulesÊinÊcontract

Sources:	[Boe91, Gib, Rob]

Values:   	[normal, tight]

Loose schedules are not considered as values that can be actual in practice.

There may be two reasons for tight schedules for the whole or part of an information system:

¥ 	Bad estimates.

¥ 	Urgency of the IS-adaptation: this is the case when an enterprise wants to install a strategic application as soon as possible for gaining competitive advantage.

When the schedules are tight, there is a risk of:

¥	Poor quality of the products, e.g. with bad commercial impact.

¥	Increased costs.

AdequacyÊofÊbudgetÊinÊcontract

Sources:	[Boe91, Gib, Rob]

Values:   	[normal, tight]

Loose budgets are not considered as values that can be actual in practice.

When the budgets are tight, there is a risk of:

¥	Poor quality of the products, e.g. with bad commercial impact.

¥	Delays in the delivery of the products.

### 3.2.2.	ProjectÊStructure

The following situational factors are properties of the project domain, which relate to the structure of the project.

3.2.2.1.	ComplexityÊofÊprojectÊstructure

NumberÊofÊsub-contractors

Values:   	[none, few, many]

The number of sub-contractors refers to the complexity of the project control required to manage the external project resources within the project structure of the IS-adaptation.

NumberÊofÊinterfacesÊtoÊother IS-adaptations

Values:   	[none, few, many]

The number of interfaces to other IS-adaptations refers to the complexity of the project control required to manage the external interfaces to other related IS-adaptations within the project structure of this IS-adaptation.

3.2.2.2.	UncertaintyÊofÊprojectÊstructure

DependencyÊonÊsub-contractors

Sources:	[Boe91]

The dependency on sub-contractors refers to the uncertainty associated with the dependence on the tasks performed by external resources within the IS-adaptation.

Values:   	[none, low, high]

When the dependency on sub-contractors is high, there is a risk of:

¥	Shortfalls in externally performed tasks or externally furnished products.

DependencyÊonÊotherÊIS-adaptations

Sources:	[Rob]

Dependency on other IS-adaptations refers to the uncertainty associated with the dependence on those IS-adaptations which have common interfaces or integration requirements to this IS-adaptation.

Values:   	[none, low, high]

When the dependency on other IS-adaptations is high, there is a risk of:

¥	Evolving requirements to the IS-adaptation.

¥	Integration problems.

FormalityÊofÊcustomer-supplierÊcontext

Sources:	[Boe91]

In this context, formality reflects the conformance within the customer-supplier relationships to defined rules and elaborated procedures.

Values:   	[high, medium, low]

When the formality of customer-supplier context is low, there is a risk of:

¥	Evolving requirements to the IS-adaptation.

¥	IS-adaptation not accepted by customer.

### 3.2.3.	ProjectÊActors

The following situational factors are properties of the project domain, which relate to actors of the project.

3.2.3.1.	ComplexityÊofÊprojectÊactors

NumberÊofÊprojectÊactors

Sources:	[McF82, Saar, VM92]

The number of project actors is a measure of the number of stakeholders who interact with the IS-adaptation, either as users, experts, developers, customers, or managers etc.

Values:   	[small, medium, large]

3.2.3.2.	UncertaintyÊofÊprojectÊactors

CapabilityÊofÊprojectÊteam

Sources:	[Alt, Boe91, Dav82, Saar]

Capability of project team refers to the uncertainty associated with the capability of the project team with respect to all the tasks which must be performed as part of this IS-adaptation.

Values:   	[high, medium, low]

Sub-factors:

¥	Skill shortfalls.

¥	Developers' knowledge about the information system.

¥	Ability of developers to elicit and evaluate requirements.

¥	Communication skills of the developers.

¥	Experience of the developers with the technology.

¥	Commitment of the developers.

When the capability of project team is low, there is a risk of:

¥	Developing the wrong information system.

¥	Straining computer science capabilities.

¥	IS-adaptation not accepted by users.

¥	Poor quality of the products

¥	Delays in the delivery of the products.

¥	Unpredictable costs for the project.

Inhibition when the capability of the project team is low:

¥	Training.

¥	Acquiring skills.

### 3.2.4.	ProjectÊTechnology

The following situational factors are properties of the project domain, which relate to the technology (methods, techniques and tools) to be used in the project.

3.2.4.1.	ComplexityÊofÊprojectÊtechnology

ComplexityÊofÊdevelopmentÊtechnology

Sources:	[Alt, Boe91]

The complexity of development technology refers to the complexity of using the development technology to perform the development tasks within the IS-adaptation.

Values:   	[low, medium, high]

3.2.4.2.	UncertaintyÊofÊprojectÊtechnology

NoveltyÊofÊdevelopmentÊtechnology

Sources:	[Alt, Boe91]

This novelty factor is a measure of how innovative the development technology is with respect to the state-of-the-art.

Values:  	[low, medium, high]

When the novelty of development technology is high, there is a risk of:

¥	Poor quality of the products.

¥	Delays in the delivery of the products.

¥	Unpredictable costs for the project.

AvailabilityÊofÊappropriateÊdevelopment technology

Sources:	[Alt, Boe91]

Availability of appropriate development technology refers to the uncertainty associated with the purchasing, delivery and accessibility of the development technology which must be used as part of this IS-adaptation.

Values:   	[high, medium, low]

When the availability of appropriate development technology is low, there is a risk of:

¥	Poor quality of the products.

¥	Delays in the delivery of the products.

¥	Unpredictable costs for the project.

# 4.	StrategyÊOptionsÊandÊHeuristics

An IS-adaptation strategy is defined in terms of a selected set of IS-adaptation strategy options. The IS-adaptation strategy options are defined within the following four approaches which are important from the customer-supplier relationship point of view:

1.	System installation approach:

The approach taken in the installation of the information system: This consists of the decisions regarding the sequence and types of versions of the information system to install in the target domain.

The following options can be defined for the installation of the information system: One shot installation, incremental installation and evolutionary installation.

2.	System construction approach:

The approach taken in the construction of the information system: This consists of the decisions regarding the sequence and types of versions of the information system to construct and test.

The following options can be defined for the construction of the information system: One shot construction, incremental construction and evolutionary construction.

3.	System description approach:

The approach taken in the design and description of the information system. This consists of:

-	The mode of operation in system description: The way information is processed to make design decisions [Mat] There are two modes of operation: analytical and experimental.

-	The co-operation approach: The way in which project actors work together with actors of the information system during the system design and description. Two types of co-operation approaches are distinguished: Expert-driven and participatory.

4.	Project control approach:

The approach taken in controlling the project, i.e. the frequency and formality of the project control measures, and responsibility for performing them, e.g. which organisation, procedures, disciplines, transactions, customer-supplier responsibilities, etc.

The main objective of most of the IS-adaptations is to make changes to the operational information system through installation of new or changed operational items. It is the installation of a new information system which makes the results of an IS-adaptation visible and usable for actors in the information system. The choice of an installation approach will put some constraints and requirements on the other approaches defined within Euromethod, for example on the scope and sequence of the deliverables within the description and construction of sub-systems. That is, the installation approach should be considered before the other approaches.

The four aspects which constitute a strategy are not of equal importance in all situations. For example, the installation approach is not relevant in a project without installation of operational items, and the description approach is of minor importance in a construction project when most of the description of the information system is completed at the project start.

The approaches in the Strategy Model are all approaches which compensate for adverse properties found in a certain situation. For each of the four approaches, the Strategy Model contains a number of options to choose from. Each of the options is described in some detail in the following sections.

These descriptions are supported by the provision of some heuristics regarding the suitability of each option. This is provided in terms of the situational factor values, either in terms of single factor values or the complexity or uncertainty of the situation. Most of the factors may indeed both influence the suitability of an approach individually and through their contribution to the complexity or uncertainty of the problem situation. For example, the adequacy of the project schedules defined in the contract is a factor which has an important influence on its own, in addition to its contribution to the uncertainty of the situation.

In the previous section, the description of each situational factor contained examples of those actions that can change the value of the situational factor and thereby inhibit the risk of an undesirable event occurring. These actions, which are specifically related to each situational factor, can be considered for inclusion as tasks in the plans.

In any case, Euromethod users should bear in mind the results of empirical studies on the use of contingency approaches, e.g. [Saar]: "The use of development strategies that fit the situation is one necessary but not sufficient condition for success. ... Factors affecting emergence and selection of the most profitable development projects remains a challenge for future research."

## 4.1.	SystemÊInstallationÊApproach

The installation of an information system is the process of making the information system operational within the target domain. The determination of a system installation approach consists of making decisions regarding the sequence and type of versions of the information system to install in the target domain.

4.1.1.	Options

The customer and supplier should choose among the following three system installation approaches (adapted from [DoD]):

1.	One :

The whole information system is installed (and used) in one version at once.

2.	Incremental :

The information system is installed (and used) in successive parts. Each part contains a sub-set of the information system functionalities. The requirements to the installed information system are fully defined before the first installation and will not be changed afterwards. This approach supposes that it is possible to determine parts of the information system which can be installed and used separately.

3.	Evolutionary :

The information system is installed (and used) in successive versions. Between any two versions, the requirements to the description and construction of the information system can be changed after learning from using the information system. Each version may contain a sub-set or the whole set of functionalities. This approach supposes that it is possible to determine versions of the information system which are usable.

4.1.2.	HeuristicsÊonÊtheÊsuitabilityÊofÊinstallationÊapproaches

The suitability of an installation approach depends on the complexity and uncertainty of the situation:

¥	Evolutionary is suitable when the situation is uncertain.

¥	Incremental is suitable when the situation is complex, but not uncertain.

Additionally, the suitability of an installation approach depends on some individual situational factors, for example:

¥	Incremental or evolutionary is suitable when the schedules are tight,

i.e. install something as fast as possible.

¥	One shot is suitable when the schedules are normal and the situation is not complex and not uncertain.

¥	Evolutionary is suitable when the importance of the organisational changes is high.

There are no general rules on the relative weight of the different situational factors in the assessment of the complexity and uncertainty of the situation. However, the effectiveness of the installation approach to manage complexity or uncertainty depends on the individual situational factors. For example, the heterogeneity of actors is a source of complexity which can hardly be managed through an incremental installation approach; similarly, the novelty of the development technology is a source of uncertainty which best can be managed by an evolutionary installation approach because an evolutionary installation approach implies an evolutionary construction approach.

## 4.2.	SystemÊConstructionÊApproach

A system construction approach consists of decisions regarding the sequence and types of versions of the information system to be constructed and tested.

4.2.1.	Options

The customer and supplier should choose among the following three system construction approaches (adapted from [DoD]):

1.	One .i.one shot construction;:

The whole information system is constructed (and tested, though not necessarily installed) in one version at once.

2.	Incremental :

The information system is constructed (and tested, though not necessarily installed) in successive parts. Each part contains a sub-set of the information system functionalities. The requirements to the installed information system are fully defined before the first construction and will not be changed afterwards. This approach supposes that it is possible to determine parts of the information system which can be constructed and tested separately.

3.	Evolutionary

The information system is constructed (and tested, though not necessarily installed) in successive versions. Between any two versions the requirements to the description and construction of the information system can be changed after learning from testing the information system. Each version may contain a sub-set or the whole set of functionalities. This approach supposes that it is possible to determine versions of the information system which can be tested.

From the customer-supplier relationship point of view, the installation approach is more important than the construction approach, because it will influence the customer-supplier relationship in all situations. The construction approach can have influence on the customer-supplier relationship, but can also solely have influence on the internal production process in the supplier organisation. It simply depends on the situation.

The following dependencies between installation and construction approaches exist:

¥	All the construction approaches can be combined with a one shot installation approach: Construction followed by a final acceptance test of the whole information system and then a one shot installation.

¥	All the construction approaches can be combined with an incremental installation approach:

-	One shot construction followed by a final acceptance test of the whole information system and then successive installation of parts.

-	Incremental construction of each part followed by the acceptance and installation of that part.

-	Evolutionary construction of each part followed by the acceptance and installation of that part.

¥	The use of an evolutionary installation approach always implies the use of an evolutionary construction approach.

4.2.2.	Heuristics on the suitability of construction approaches

The suitability of a construction approach depends on the complexity and uncertainty of the situation, together with the adequacy of the project schedules defined in the contract. The influence of situational factors on the suitability of construction approaches is very similar to their influence on the suitability of installation approaches:

¥	Evolutionary is suitable when the situation is uncertain.

¥	Incremental is suitable when the situation is complex, but not uncertain.

¥	Incremental or evolutionary is suitable when the schedules are tight,

i.e. construct something as fast as possible.

¥	One shot is suitable when the schedules are normal and the situation is not complex and not uncertain.

There are no general rules on the relative weighting of the different situational factors in the assessment of the complexity and the uncertainty of a situation. However, as for the installation approach, the effectiveness of the construction approach to manage complexity or uncertainty depends on the individual situational factors.

This dependency between the effectiveness of an approach and the situational factors is not exactly the same for the construction approach as for the installation approach. For example:

¥	The capability of project team, or the novelty of development technology are sources of uncertainty that can be better managed through using an evolutionary construction approach. They are only affected by the use of an evolutionary installation approach because this installation approach implies the use of an evolutionary construction approach.

¥	The number of replications of the computer system is a source of complexity that can be managed by an incremental installation approach and not by an incremental construction approach.

## 4.3.	SystemÊDescriptionÊApproach

A system description approach consists of those decisions regarding the primary mode of operation used in system design and description, and the primary co-operation approach adopted between the project actors and the actors in the information system. System description includes requirements determination. The mode of operation used in system design and description is the way information is processed in order to make design decisions. The co-operation approach is the way in which the project actors work together with actors of the information system during system design and description.

4.3.1.	Options

¥	Mode of operation:

Two modes of operations are distinguished (adapted from [Mat]):

-	Analytical

When information is processed in an analytical mode, the available information is simplified through abstraction in order to reach a deeper and more invariant understanding. An analytical mode is used to reduce the complexity of the system description. In an analytical mode the information system is mainly described by the use of documented specifications.

-	Experimental :

When operating in an experimental mode the project actors learn from experiments generating new knowledge. The purpose is to reduce the uncertainty by generating more information. Experiments can for example be based on prototypes, mock-ups or other kinds of techniques which make scenarios visible.

In [Mat] it is argued that the two modes of operation can be combined. This is formulated in The Principle of Limited Reduction: "Relying on an analytical mode of operation to reduce complexity introduces new sources of uncertainty requiring experimental countermeasures. Conversely, relying on an experimental mode of operation to reduce uncertainty introduces new sources of complexity requiring analytical countermeasures." It is therefore only the primary mode of operation that is part of the IS-adaptation strategy.

¥	Co-operation:

Two types of co-operations are distinguished (adapted from actor-participation strategy approaches, e.g. [Saar]):

-	Expert-driven:

In an expert-driven approach, project actors (the experts) will produce descriptions on the basis of interviews and observations of actors of the information system. The descriptions can then be delivered to the actors for remarks or approvals.

-	Participatory:

In a participatory approach, the project actors produce the descriptions in close co-operation with some or all the actors of the information system, e.g. in workshops with presentations, discussions and design decisions. Joint Application Design (JAD) is an example of a technique that can be used in a participatory approach. A participatory approach may allow the acquisition of knowledge, the refinement of requirements and the facilitation of organisational changes.

¥	Description approach:

The customer and supplier should choose among the four possible combinations of mode of operation options and co-operation options, i.e. the four system description approaches in Figure 9. The choice of system description approach will place requirements on the deliverables exchanged in customer-supplier transactions and on the methods and techniques used in the IS-production.

| Co-operation approach Mode of operation | Expert-driven | Participatory |
| --- | --- | --- |
| Analytical | 1. Analytical and Expert-driven | 2. Analytical and Participatory |
| Experimental | 3. Experimental and Expert-driven | 4. Experimental and Participatory |

Figure 9: System description approach options.

4.3.2.	Heuristics about the suitability of description approaches

.i.IS-adaptation strategy heuristics ;The suitability of a primary .i.mode of operation ;depends on the complexity and uncertainty of the situation:

¥	Analytical mode of operation is suitable when the situation is complex.

¥	Experimental mode of operation is suitable when the situation is uncertain.

The suitability of a primary co-operation approach depends on an overall assessment of a combination of specific situational factor values; no single value can enforce a co-operation approach. In general, it can be concluded that:

¥	An analytical and expert-driven description approach is suitable when the situation is complex, unless the complexity of the information or business processes is high.

¥	An analytical and participatory description approach is suitable when the complexity of the information or business processes is high.

¥	An experimental and expert-driven description approach is suitable when the situation is uncertain and a participatory co-operation is not suitable.

¥	An experimental and participatory description approach is suitable when the situation is uncertain and the ability of the actors in the information system is not low and the adequacy of the schedules is normal.

¥	An expert-driven approach is more simple to plan and control than a participatory approach. A participatory approach is easier to control when an evolutionary installation approach is used. That is, the installation, description, and control approaches are interdependent.

## 4.4.	ProjectÊControlÊApproach

Project control is the set of processes concerned with monitoring the progress of the project, i.e. its direction, quality, and resource utilisation, as compared with project plans.

The project control approach is the approach taken in controlling the project, i.e. the frequency and formality of the project control measures, and the responsibility for performing them.

Project control may be split among the three work areas: IS-development, quality assurance and configuration management defined by Euromethod. In accordance with this, three project control processes are distinguished:

1.	Development :

The project management process necessary to control the project tasks performed within the IS-development work area.

2.	Quality control:

The techniques and activities that are used to fulfil the quality requirements. Quality control involves techniques and activities aimed at both monitoring a process and eliminating the causes of unsatisfactory performance at all stages of the quality loop in order to achieve economic effectiveness.

3.	Configuration :

This is an element of configuration management, which consists of the evaluation and co-ordination, approval or disapproval, and implementation of changes to configuration items after the formal establishment of their configuration item identification.

4.4.1.	Options

Three aspects of project control are distinguished, each with two options:

¥	Frequency:

The frequency of customer-supplier transactions within the control process.

Options: Frequent or seldom.

¥	Formality:

The degree of formality within organisation, procedures and disciplines used by the control process.

Options: Degrees of formality with the extremes formal and informal.

High degree of formality in project control can contain, for example:

-	Periodical approvals of status and plan with delivery of management reports.

-	Well-defined requirements on the content of management reports.

-	Well-defined baselines deliverables with deadlines and defined approval procedures.

-	Use of well-defined metrics for project progress and quality.

-	Use of a well-defined inspection technique in quality control.

-	Well-defined configuration control procedures.

¥	Customer Responsibility:

The definition of customer responsibility within project control. It is assumed that the supplier is responsible for all aspects of the project control, unless the customer responsibility is explicitly defined in the contract.

Options: Different kinds of customer responsibility.

The kind of customer responsibility that should be defined depends on the situation. Examples of defined customer responsibility are where the:

-	Customer is responsible for the configuration control of requirements.

-	Customer is responsible for the quality control of descriptions with respect to the requirements and business needs.

-	Customer is responsible for the generation of test cases that cover critical situations from the business process point of view.

-	Customer is responsible for preparing the organisation for installation of the new information system.

-	Customer is responsible for obtaining agreements in the organisation regarding the system requirements.

4.4.2.	Heuristics about the suitability of project control approaches

In general, the following examples of heuristics can be concluded.

Frequency

¥	Frequent development control is suitable when the situation is uncertain.

¥	Frequent quality control is suitable when the:

-	Strategic importance of the information system is high.

-	Dependencies are high:

-	Capability of project team is low.

-	Situation regarding development technology is complex or uncertain.

¥	Frequent configuration control is suitable when dependencies are high or the stability is low.

Formality

¥	High degree of formality in development control is suitable when the situation is complex or uncertain.

¥	High degree of formality in development control is suitable when an evolutionary installation approach is used.

¥	High degree of formality in quality control is always suitable, but the procedures to apply can be more or less complex dependent on the size of the project.

¥	High degree of formality in configuration control is suitable when the stability is low or the situation is complex.

CustomerÊresponsibility

It is suitable to define the customer's responsibility in the project control regarding for example the:

¥	Handling the conflicts and the attitudes among actors in the target domain,

when the heterogeneity of actors is high or the attitude is negative.

¥	Provision of knowledge and decision making,

when the strategic importance is high or the situation regarding requirements is uncertain.

¥	Management of the changes in the target domain,

when the importance of organisational changes is high.

¥	Control of changes of requirements,

when the situation regarding requirements is uncertain.

# 5.	LimitationsÊofÊtheÊState-of-the-art

The situational approach to IS-adaptation is a response to the need for tailoring the development approaches to the problem situations. This need has been expressed by most practitioners in IS-adaptation and situational approaches are considered as a major potential improvement of current IS-development methods.

The situational approach is also supported by theoretical arguments: the most powerful of them is that the way for solving a problem must depend on the type of problem. This is true in all fields and therefore in IS-engineering.

However, the current state-of-the-art in situational approaches suffers from some limitations. We believe that these limitations will be progressively removed when the practice and the theoretical studies progress the state-of-the-art. In this respect, the use of Euromethod might be a key factor for the enhancement of situational approaches.

These limitations are explained below.

## 5.1.	EffectivenessÊofÊtheÊsituationalÊapproaches

The effectiveness of the situational approaches has not yet been proven.

As for any problem solving approach, situational approaches do not guarantee success: they just provide heuristics which increase the chances of success. Therefore, a proof of effectiveness can only be statistical.

Situational approaches are not yet widely used. When they are used, it is in a very intuitive way by expert practitioners. Therefore, there is a lack of statistical data which could be exploited to estimate their effectiveness.

Notwithstanding the fact that a proof of effectiveness is difficult and that subjectivity cannot be totally removed in such an area, some recent academic studies, in Scandinavia [Rop, Saar] and in the Netherlands [Brink. et al.], have undertaken pioneering work in the field of statistical studies on the effectiveness of different approaches in different contexts, based on the data collected from industrial projects.

It is too soon to make any firm statement on the effectiveness of situational approaches. Only a wider usage of them, hopefully encouraged by Euromethod, and more statistical studies could provide that proof of effectiveness.

## 5.2.	AssessmentÊofÊsituationalÊfactors

Situational factors are often difficult to assess in practice. Most of them can only be evaluated by an expert judgement: it is not possible then to entirely remove subjectivity from the process.

Moreover, the following assumption is made regarding the evaluation of situational factors: the customer and the supplier behave as rational people, aiming at understanding and clarifying a problem situation in the most honest way to determine the best approach for the IS-adaptation together. This is clearly a win-win situation. In case this assumption proves to be wrong for political, commercial or social reasons, the assessment of situational factors, especially the information system factors, might be very difficult.

Some of the factors require knowledge of a social and organisational nature (e.g. most of the information system factors), and of a technological nature (e.g. complexity of non-functional requirements to the computer system).

The complexity of non-functional requirements to the computer system can only be assessed in reference to a type of system (e.g. efficiency or usability may concern different aspects according to the type of system) and to the technological state-of-the-art. Therefore, Euromethod cannot give general guidance on these topics, but should recommend to refer to the body of knowledge existing in the corresponding fields.

Some factors may also overlap: they are probably not statistically independent variables. Therefore, the same phenomenon might be taken into account twice in the determination of the appropriate approach.

## 5.3.	DeterminationÊofÊtheÊIS-adaptationÊstrategy

Several issues make the determination of the IS-adaptation strategy by the means of the use of situational factors an uncertain process.

Firstly, the relative importance of the situational factors for the determination of the most appropriate strategy is not known. Some might even be of so little influence that they could be dropped in the future.

Secondly, the  for the determination of the IS-adaptation strategy as a function of the situational factors are not all known, or proven to be correct. They currently represent some empirical knowledge.

Thirdly, if it seems possible to give some heuristic for the influence of one situational factor on the IS-adaptation strategy, it is more difficult to assess the influence of a combination of these factors. Situational factors may potentially have complex relationships with each other:

¥	inhibition of a factor by another

¥	reinforcement of a factor by another

¥	conflicting requirements to the IS-adaptation strategy

¥	consistent requirements to the IS-adaptation strategy.

One way to overcome this problem is to assess global variables like the complexity and the uncertainty of the situation. These variables influence the strategy as indicated in the previous section. It is the reason why the situational factors have been classified into complexity factors and uncertainty factors. It is however difficult to assess these complexity and uncertainty from patterns of situational factors especially when they are conflicting.

In the future, heuristics are likely to address patterns of situational factors at a finer level than these overall factors.

In conclusion, we think that, despite the aforementioned limitations, the situational approaches represent an important step towards the improvement of IS-adaptation practices. Within the customer-supplier relationship, it is important that the supplier justify his IS-adaptation strategy with respect to the problem situation and the customer be able to assess his argumentation. This can already be done within the current state-of-the-art. A situational approach also helps to structure and direct thinking. The resulting analysis can be used in a pragmatic way.

# References

[EM-1-EO]	Euromethod Overview, 1994

[EM-2.1-CG]	Euromethod Customer Guide, 1994

[EM-2.2-SG]	Euromethod Supplier Guide, 1994

[EM-2.3-DPG]	Euromethod Delivery Planning Guide, 1994

[EM-2.4-MBG]	Euromethod Method Bridging Guide, 1994

[EM-2.5-CS]	Euromethod Case Study, 1994

[EM-3.1-TM]	Euromethod Concepts Manual 1 - Transaction Model, 1994

[EM-3.2-DM]	Euromethod Concepts Manual 2 - Deliverable Model, 1994

[EM-4-ED]	Euromethod Dictionary, 1994

---------

[Ahi]	Ahituv N., Hadass M. and Neumann S., "A Flexible Approach to Information System Development", MIS Quarterly, June 1984.

[Alt]	Alter S. and Ginzberg M., "Managing Uncertainty in MIS Implementation", Sloan Management Review, Fall, 1978.

[Atmos]	Atmosphere Glossary. Esprit Project 2565, Deliverable D2.4.1.1. (Siemens-Nixdorf, 1992).

[Boe91]	Boehm B., "Software Risk Management: Principles and Practices", 
IEEE Software, Jan. 1991.

[Brink. et al]	Brinkkemper, S., Lange, M. de., Looman, R., Steen, F. van der (1989). ÒOn the derivation of method comparisons by meta-modelling. Case Ô89, Third International Workshop on Computer-Aided Software Engineering, Imperial College, London, United Kingdom, July 17-21, 1989.

[Comp]	The Complement Consortium. ESPRIT Complement Project Glossary (Esprit project number 5409) 20/7/92.

[Dav82]	Davis Gordon B., Strategies for Information Requirements Determination, IBM Systems Journal, Vol. 21, No 1, 1982.

[DoD]	Department of Defence, United States. Military Standard Software Development and Documentation (draft). 
MIL-STD-SDD (DRAFT), 22 December 1992.

[EMPMB]	EMPMB evaluation report on the EM3a WP2 deliverables, 
EMPMB Document Number EM100, 25 October 1993.

[Gib]	Gibson C.F., Singer C. J., Schnidmann A. A. and Davenport T. H.., "Strategies for Making an Information System Fit Your Organisation", Management Review, Jan. 1984.

[Lea]	Leavitts H., "Applied Organisation Change in Industry: Structural, Technical and Human Approaches", New Perspectives in Organisational Research, John Wiley, 1964.

[ISO-9126]	ISO 9126 Information technology - Software product evaluation 
- Quality characteristics and guidelines for their use: 1991.

[Mat]	Mathiassen Lars and Stage Jan, "The principle of limited reduction in software design", Information Technology and People, 6:2-3 1992, Northwind Publication.

[McF82]	McFarlan Warren, "Portfolio Approach to Information Systems", Journal of Systems Management, Jan. 1982.

[MOR]	Morley Chantal, "MŽthodes et contingences", Thse de doctorat, Feb. 1991.

[Rob]	Robinson Keith: Lower ISE Guides, CCTA internal document.

[Rop]	Ropponen, Janne: "Risk management in Information System Development", Licentiate thesis in Information Systems, May 15,1993.

[Saar]	Saarinen, Timo: "Success of Information System Investments - Contingent strategies for development and a multi-dimensional approach for evaluation", Draft version of the doctoral dissertation, 10.4.1992.

[VM92]	V-Model, German Federal Ministry of the Interior, August 92.

# Index

AbilityÊofÊactors 21

actor 18; 20; 21; 33; 36

AdequacyÊofÊbudgetÊinÊcontract 32

AdequacyÊofÊschedulesÊinÊcontract 31

analytical mode of operation 42

AttitudeÊofÊactorsÊtowardsÊthe informationÊsystemÊadaptation 20

AvailabilityÊofÊappropriateÊdevelopment technology 35s

Availability, clarity and stability of requirements to the information system 25

CapabilityÊofÊprojectÊteam 34

co-operation approach 36; 42; 44

complexity 16

ComplexityÊofÊbusinessÊprocesses 20

ComplexityÊofÊcomputerisedÊfunctions 26

ComplexityÊofÊdata 26

ComplexityÊofÊdevelopmentÊtechnology 35

ComplexityÊofÊinformation 19

ComplexityÊofÊmigration 31

Complexity of non-functional requirements to computer system 27

ComplexityÊofÊtargetÊtechnology 29

configuration control 45

criticality 28

decision point 6

DependencyÊonÊotherÊIS-adaptations 33

DependencyÊonÊsub-contractors 32

development control 45

efficiency 28

evolutionary construction 40

evolutionary installation 38

experimental mode of operation 42

expert-driven approach 43

FormalityÊofÊbusinessÊprocesses 22

FormalityÊofÊcustomer-supplierÊcontext 33

FormalityÊofÊinformation 22

formality of project control 45

frequency of project control 45

HeterogeneityÊofÊactors 18

ImportanceÊofÊorganisationalÊchanges 24

ImportanceÊofÊtechnologicalÊchanges 29

incremental construction 40

incremental installation 38

installation of an information system 38

IS-adaptation strategy 5; 14; 36

IS-adaptation strategy heuristics 9; 14; 39; 41; 44; 46; 50

IS-adaptation strategy options 8; 13; 36

knowledge characteristic 16

maintainability 28

mode of operation 42; 44

NoveltyÊofÊdevelopmentÊtechnology 35

NoveltyÊofÊIS-adaptation 31

NoveltyÊofÊtargetÊtechnology 29

NumberÊofÊinterfacesÊtoÊother IS-adaptations 32

NumberÊofÊprojectÊactors 33

NumberÊofÊreplicationsÊofÊcomputer system 29

NumberÊofÊsub-contractors 32

one shot construction 40

one shot installation 38

participatory approach 43

portability 28

problem situation 4; 8; 16; 48

project actor 30

project control approach 44

project domain 16

project domain factor 30

project structure 30

project task 30

project technology 30

quality control 45

QualityÊofÊexistingÊspecifications 25

reliability 28

risk 17

risk management 38

security 28

situational approach 4

situational factors 8; 11; 12; 16

SizeÊofÊdistributionÊofÊinformation system 19

SizeÊofÊproject 30

SizeÊofÊtargetÊdomain 19

SpecificityÊofÊinformationÊsystem 23

StabilityÊofÊenvironment 21

StabilityÊofÊinformationÊandÊbusiness processes 23

StrategicÊimportanceÊofÊinformation system 24

Strategy Model 5; 8

system construction approach 39

system description approach 42

system installation approach 38

target domain 16

target domain factor 18

uncertainty 16

UnderstandabilityÊofÊexistingÊinformationÊsystem 23

usability 28

DocumentÊhistoryÊofÊtheÊEuromethodÊStrategyÊModel

| Version | Status | Author | Comment | Distribution |
| --- | --- | --- | --- | --- |
| 040294 | Ready for L2-review | MF | All remarks by the EMPMB have been taken into account plus the relevant remarks from the national reviewers (most of them from GW). | Project team |
| 220294 | Under L2 Review | MG | All remarks by the L2 review have been taken into account. Passed to NEA to make consistent with the DPG. | NA. |
| 280294 | Under L3-Review | NA | NA remarks incorporated. | ¥ Review Group ¥ Project Team |
| 280394 | Under L3-review | NA | Revised on the basis of remarks from the review group and the project team. New document layout is used. | ¥ AG ¥ Project Team |
| 050494 | Delivered | NA | Revised on the basis of remarks from MF. Layout standards implemented. | EC |
| 150694-m | Under L3-review | NA | Revised on the basis of remarks from EMPMB, see change request document. | ¥ Review group ¥ GW, MF |
| Version 0, June 1994 | Delivered | NA | Revised on the basis of remarks from the review group and GW. Marks are removed. | EC |

Inversely, the strategy model can be used to determine the modifications of the problem situation that should be done to fit a given strategy.

A combination of IS-adaptation strategy options can be considered as a process model type (mentioned in the contract for Euromethod Phase 3A [CEC 92/12290]).

Generally, a three grade scale is used. A larger number of grades would have caused difficulties in allocating a value to the factor when analysing the problem situation, and in associating a project strategy to each of the values. Two grades are often too rough insofar as they propose extreme cases and do not allow to express some normal or neutral situation.

The sub-factors should be taken into account in the evaluation of the factor. However, there is usually no algorithm or rule to derive the value based on the pattern of sub-factor values.

It is assumed that the choice of IS-adaptation strategy options is done after the initial and final states of an IS-adaptation are chosen and described.