Euromethod
Concepts Manual 2
Deliverable Model

EM-3.2-DM

__________________________________

Abstract

This manual is one of three Euromethod Concepts Manuals. There is one manual for each of the models in Euromethod which between them contain all of the concepts of Euromethod.

The Deliverable Model defines the concepts related to the description of deliverables in an IS-adaptation in which Euromethod can be applied.

__________________________________

© Euromethod Project 1994

This document,

Euromethod Concepts manual 2 - Deliverable Model,

is a document of the Euromethod Version 0.

In the layered document structure of Euromethod it constitutes a part of the Concepts Manuals Level. It is referenced by the Guides and the Overview; and makes use of the definitions in the Dictionary.

Contents of the Deliverable Model

1.	Introduction	4

1.1.	Objectives	4

1.2.	The Principal Deliverable Types	4

2.	Delivery Plan	6

3.	Target Domain Deliverables	9

3.1.	Target Domain	9

3.2.	The Types of Target Domain Deliverables	12

3.3.	IS-Descriptions - Definition of the Type of Content	13

3.3.1.	IS-Description Types	13

3.3.2.	Views and IS-Properties	16

3.3.3.	Non-functional Properties	27

3.3.4.	Consistency Rules between the Views	30

3.4.	IS-Descriptions - Definition of the Amount of Content	33

3.4.1.	Development State	34

3.4.2.	Deliverable Scope	36

3.4.3.	Degree of Formality	37

3.5.	Operational Items	38

3.6.	Quality State	39

4.	Project Domain Deliverables	40

4.1.	The Types of Project Domain Deliverables	40

4.2.	Project Plans	41

4.3.	Project Reports	44

4.4.	Quality State	48

Annex	49

A.	Concepts Overview	49

References	51

Index	53

# 1.	Introduction

This manual is one of three Euromethod Concepts Manuals: Transaction Model, Deliverable Model and Strategy Model. There is one manual for each of the models in Euromethod which between them contain all of the concepts of Euromethod.

## 1.1.	Objectives

The objective of this document is to describe the Euromethod concepts that are needed to describe deliverables in IS-adaptations, and which thus provide the basis for the guidance supplied by the Euromethod Guides.

The document is intended to serve as a reference document of the Euromethod concepts providing additional support to the information provided within the Euromethod Guides. It is therefore expected that readers of this document will come to it, as a means of obtaining the detailed definition regarding a concept used within the Euromethod Guides.

## 1.2.	The Principal Deliverable Types

The Deliverable Model provides the means to characterise deliverables that are exchanged between the customer and the supplier during the course of an IS-adaptation.

During the tendering process the desired outcome of the IS-adaptation and the necessary customer-supplier transactions of the production and completion processes are defined. During the production process the defined deliverables are produced under the defined control.

In considering the IS-production, the customer is mainly interested in those deliverables that are related to the information system considered by the IS-adaptation. That is those deliverables that the customer actually pays for and which he wants to use but not develop himself. These deliverables, which are either descriptions of the information system under consideration or operational parts of it, are represented in the Deliverable Model as:

•	Target domain deliverables.

Design decisions which are of contractual importance and which demand the participation of both the customer and supplier are based on target domain deliverables.

Nevertheless, in order to facilitate this decision making during the production process, the customer needs to have some insight into the supplier's internal IS-production in order to control the quality of the target domain deliverables. The deliverables that reflect these concerns in the Deliverable Model are the:

•	Project domain deliverables.

During the tendering process, and also in the customer-supplier transactions concerning the review of the IS-adaptation's planning, the document defining the IS-adaptation serves as a deliverable as well. This is the:

•	Delivery plan.

Furthermore, project domain deliverables and delivery plans related to future IS-adaptations can also be delivered during an IS-adaptation, if one of the results shall be a proposal for a subsequent IS-adaptation.

Figure 1 shows the principal deliverable types introduced above.

Figure 1: The principal deliverable types.

# 2.	Delivery Plan

The concept of delivery plan is defined in Concepts Manual 1 - Transaction Model. This chapter repeats the parts of the definition that describe the delivery plan in its function as a document that can be delivered in customer-supplier transactions. The delivery plan’s function in the execution of IS-adaptation is not relevant here.

A delivery plan is a product which defines the contractual customer-supplier relationship during the production and completion processes. A Euromethod delivery plan should contain the following elements:

•	A description of the problem situation, including descriptions of the initial and final states.

•	A description of the IS-adaptation strategy.

•	The sequence and descriptions of the required decision points and the related deliverables.

The initial state of an IS-adaptation is the state of the information system and the available knowledge on it, at the beginning of the production process, i.e.:

•	The initial state information system, i.e. the operational items contained in the operational information system.

•	The operational items of a future information system that are available to the IS-production process (they have been constructed but are not yet installed and part of the operational information system).

•	The IS-adaptation requirements, i.e.:

-	The IS-descriptions that are available to the production process; this can include both IS-descriptions of the initial state information system and IS-descriptions of a future information system;

-	The delivery plan.

-	Possibly project plans (development plan, quality assurance plan, configuration management plan).

The final state of an IS-adaptation is the state of the information system and the knowledge on it, at the end of the IS-adaptation, i.e.:

•	The final state information system.

•	The operational items of a future information system that are produced as a result of the IS-adaptation (they are constructed but not yet installed as part of the operational information system).

•	The IS-descriptions that are produced as a result of the IS-adaptation and that the customer wants to continue to use after the termination of the IS-adaptation; this can include both IS-descriptions of the final state information system and IS-descriptions of a future information system.

•	The plans for future IS-adaptations that are produced as a result of the IS-adaptation; this can include both delivery plans and project plans.

A description of the IS-adaptation strategy contains:

•	The reasoning that leads to the sequence of decision points defined in the delivery plan. Ideally this summarises the conclusion from applying the Strategy Model as described in the Delivery Planning Guide.

The decision points throughout the production and completion processes are characterised by:

•	The decisions that are made, the roles involved in these decisions, the customer-supplier transactions that take place and thereby the deliverables that are exchanged. These deliverables serve as a basis for the decisions.

The descriptions of decision points in the production and completion processes are part of the delivery plan. The types of customer-supplier transactions that can take place at the decision points are defined in Concepts Manual 1 - Transaction Model.

Delivery plans of future IS-Adaptations

An IS-adaptation can also result in delivery plans for future subsequent IS-adaptations. Such delivery plans have the function of defining future IS-adaptations foreseen as taking place after the current one, e.g. an IS-adaptation pursuing the design of an information system in more detail, or performing the construction or installation of the information system designed in the current IS-adaptation.

If an IS-adaptation produces a delivery plan for a future IS-adaptation, this is generally accompanied with plans for the project domain of the subsequent IS-adaptation (see Chapter “Project Domain Deliverables”).

In the Euromethod documents the term delivery plan generally designates the delivery plan of the regarded IS-adaptation. If the delivery plan for a future IS-adaptation - a deliverable of the regarded IS-adaptation - is meant, it is explicitly named: delivery plan for a future IS-adaptation or future IS-adaptation’s delivery plan.

# 3.	Target Domain Deliverables

This chapter explains:

•	The meaning of the term target domain and how to characterise it.

•	The types of target domain deliverables:

IS-descriptions and operational items.

•	How to characterise the type of knowledge contained in IS-descriptions by the IS-description type, the captured IS-properties and the captured non-functional properties.

•	How to characterise the amount of knowledge contained in IS-descriptions by the development state, the deliverable scope and the degree of formality.

•	How to characterise the operational items.

•	How to characterise target domain deliverables by their quality state.

## 3.1.	Target Domain

An organisation is characterised by the business it performs (e.g. trade, manufacturing, administration). In performing this business (e.g. selling, buying, manufacturing goods, providing services) the actors in the organisation:

•	Perform processes that contribute in attaining the business objectives.

•	Use information about the business to facilitate the performance of these processes.

In its business, the organisation may recognise a problem situation, i.e. a domain where there is some need for an IS-adaptation. This domain involved will be the target domain for that IS-adaptation. The organisation that decides to contract an IS-adaptation is the customer organisation, and the organisation performing the contract is the supplier organisation.

The target domain can be part of the customer organisation. It is also possible that the target domain is entirely outside of the customer organisation (when the customer works on behalf of, or is associated with other organisations).

The totality of the information kept in the target domain is called the information resource of the target domain: it represents the relevant parts of the organisation (its structure and functioning) and its environment (clients, suppliers, market, etc.). This information resource is needed by the actors to perform the processes of the target domain. The actors and processes of the target domain are regarded purely in terms of their relationship with the information resource.

The information system is the aspect of the organisation which provides, uses, and distributes the information. It is considered to include the associated organisational resources such as human, technical and financial resources. It is thus effectively a human system, possibly containing a computer system that automates selected elements of the information system.

Figure 2: Target domain.

The characterisation of the target domain

The target domain of an IS-adaptation is characterised by the processes that shall be considered in the IS-adaptation. There are two ways of delimiting the subset of processes an IS-adaptation considers:

•	Identification of the considered business areas;

which delimits a set of functionally related processes, i.e. processes which operate on the same information items and that exchange the results between one another.

•	Identification of the considered organisational units;

which identifies a set of processes allocated to an organisational unit, i.e. processes that are allocated to a group of actors in the organisation who have the responsibility to perform the related tasks.

These two characterisations of a target domain, which can be viewed as orthogonal dimensions, can be used to delimit the subset of the organisation processes to be considered in an IS-adaptation. The target domain of an IS-adaptation is thus determined by the subset of the processes performed by the chosen organisational units and comprised in the chosen business areas (see Figure 3).

Figure 3: Target domain characterisation.

The target domain of an IS-adaptation may thus be:

•	One business area in one organisational unit.

•	One organisational unit (covering several business areas).

•	One business area (covering several organisational units).

•	Several business areas for several organisational units.

•	All of the organisation.

Example

•	Organisational units of an organisation may be the research and development department, the manufacturing facilities and others.

•	Business areas may be administration of personnel, finance and others.

In this case the target domain of the considered IS-adaptation can be, e.g.

•	The whole organisation .

•	The research and development department of the organisation (covering all business areas for this department).

•	The administration of personnel of the organisation (covering all departments, i.e. organisational units of the organisation ).

•	The administration of personnel of the research and development department.

•	The financial administration of all manufacturing facilities.

## 3.2.	The Types of Target Domain Deliverables

Target domain deliverables are deliverables which describe the information system, which can be used as operational parts of the information system or which facilitate the functioning of the information system.

Therefore, they are distinguished in:

•	Operational items;

i.e. deliverables that can be used as operational parts of the information system or facilitate its functioning.

These facilitate the changes in the target domain.

•	IS-descriptions;

i.e. deliverables that capture knowledge about the considered information system.

They facilitate the decision making concerned with the direction of an IS-adaptation, i.e. specifying what the information system should do and what its design should look like.

Figure 4 represents the types of target domain deliverables introduced above.

Figure 4: The types of target domain deliverables.

These two types of target domain deliverables allow a flexible characterisation of the initial state and final state of an IS-adaptation; and thus flexibility in defining IS-adaptations.

## 3.3.	IS-Descriptions - Definition of the Type of Content

An IS-description is a target domain deliverable which captures knowledge about the information system.

This knowledge is characterised by the:

•	IS-description type, i.e. the type of knowledge.

•	Set of properties of the information system (IS-properties) that are described.

### 3.3.1.	IS-Description Types

An IS-description can be of one of the following IS-description types:

•	Requirements statement:

A requirements statement defines an essential condition that the information system under consideration has to satisfy (adapted from [ISO-2382-20]).

Thus a target domain deliverable stating requirements to the considered information system, is a deliverable that defines conditions for a set of IS-properties that the specification of these IS-properties must cover.

Example: A deliverable containing statements like “The response time for a dialogue is one second” or “all customer information must be stored in the database”, is considered as representing requirements because these statements represent essential conditions that have to be satisfied irrespective of how the system is designed.

•	Specification:

A specification is a product that provides a definitive description of an information system for the purpose of developing or validating it (adapted from [ISO-2382-20]).

Thus a target domain deliverable which provides a specification of the considered information system, is a deliverable that defines a set of IS-properties of this information system.

Example: A deliverable containing statements like “The dialogues are implemented using the window system A”, “The data are stored on hard disks of type X and backed up on tapes of type Y” or deliverables containing diagrams defining database entities or tasks of actors, are considered as representing specifications because these statements give a definite description of what the system will look like.

In this context, it is important to remember that the specification of an information system does not “overrule” the stated requirements. A specification is only valid, if all the requirements, i.e. the essential conditions that have to be satisfied, are satisfied.

In practice, it is sometimes difficult to distinguish between requirements statements and specifications. A statement can in one context be considered as a specification and in another context be considered as a requirements statement. However, it is important to make the distinction in each situation to avoid inappropriate discussions on solutions described in specifications.

•	Prototype:

A prototype is an operational trial model suitable for evaluating an information system specification or for better understanding or determination of requirements (adapted from [ISO-2382-20]).

Thus a prototype is a target domain deliverable which is an operational system that reflects a set of IS-properties.

When a prototype is required as a deliverable in an IS-adaptation, it is important to define the purpose of a prototype, e.g. to check a part of an information system specification against some of the requirements to that information system. In this case, it is necessary that the requirements statements against which the prototype is to be measured are made available.

It is important to be conscious about the difference between a prototype of the information system under consideration and the information system itself. A prototype, while being operational, neither is a part nor represents a state of the considered information system, but is a special (operational instead of on paper) means for capturing knowledge about the considered information system.

Figure 5 represents the deliverable types that are IS-descriptions as introduced above.

Figure 5: The types of IS-descriptions.

The characterisation of requirements statements, specifications and prototypes is based on the concepts of views and properties of information systems which are defined in the subsequent section. Requirements to an information system can additionally be characterised in terms of non-functional properties which are defined in a particular section.

The views, IS-properties and non-functional properties allow to completely characterise the knowledge about an information system that is necessary to facilitate a particular decision during an IS-adaptation.

### 3.3.2.	Views and IS-Properties

The type of knowledge about the information system that is contained in a deliverable is determined by the view the deliverable represents. Euromethod defines six such views. Each of them is characterised by a purpose and a set of IS-properties. An IS-property is a piece of knowledge on the information system that is used to make decisions on the IS-adaptation:

•	A requirement statement deliverable defines requirements to IS-properties.

•	A specification deliverable constitutes the specification of IS-properties.

•	A prototype deliverable is able to animate or simulate IS-properties.

The views define the concepts and the terminology which are used to characterise the knowledge about the information system of a target domain. In their totality they capture all the knowledge relevant for the development of an information system.

The terminology used in the definition of the views of the information system is based on the vocabulary standards [ISO-2382-01, IEEE-729] and also on glossaries compiled by European projects [Atmos, Comp]. Some of the terms in this terminology are used in practice with a variety of meanings, in these cases one of these interpretations is chosen and adapted; and the term is used in Euromethod exclusively with this meaning.

The six views are classified into information system views and computer system views. The information system views define the representation of the information resource, the actors using and producing it, their processes and the relationships between them. The computer system views define the representation of the structure and functionality of the computer system.

The information system views are the following:

•	The business information view:

This defines the IS-properties which characterise the knowledge about the information resource of the target domain.

•	The business process view:

This defines the IS-properties which characterise the knowledge about the processes in the target domain and their use of the information resource, independently from the actors of the information system.

•	The work practice view:

This defines the IS-properties which characterise the knowledge about the actors, their location, their tasks and the subset of the information resource they use.

The information system views are shown graphically in Figure 6.

Figure 6: Information system views.

Some of the actors in the target domain can be supported or replaced by a computer system. This means, some or all of their tasks are partially or fully performed by a computer system. This is described in the work practice view which defines the IS-properties characterising the knowledge about the selection of the tasks and the subset of the information resource that are computerised.

The knowledge about how the tasks of actors are automated and how the computer system is structured is described by the computer system views. The IS-properties encompassed by these views are defined by the computer system views (see Figure 7):

•	The computer system data view:

This defines the IS-properties that characterise the knowledge about the data retained in the computer system and which thus represents the automated part of the information resource.

•	The computer system function view:

This defines the IS-properties that characterise the knowledge about the functions performed by the computer system and which thus represents the automated parts of the tasks performed by the actors.

•	The computer system architecture view:

This defines the IS-properties related to the structure of and processing units in the computer system.

These computer system data and function views encompass the IS-properties that characterise the computer system knowledge, independent from the structure of the computer system (i.e. the processing units on which data are stored and the functions are implemented).

The IS-properties characterising processing unit dependent knowledge of the computer system are defined in the computer system architecture view.

The terminology used in the definition of the computer system views is based on the same vocabulary standards [ISO-2382-01, IEEE-729] and glossaries [Atmos, Comp] and compiled under the same premises as the one for the information system views.

Figure 7: The information system and computer system views.

The information system views and the computer system views (see Figure 7), encompass the IS-properties of an information system and the contained computer system that are necessary to facilitate decisions regarding the:

•	Design of the considered information system; and

•	Requirements to single IS-properties of the information system under consideration during an IS-adaptation.

Business information view

The purpose of the business information view is to represent the information resource of the target domain, independently of how the information resource is implemented and used by actual working practices. It encompasses the IS-properties that capture knowledge related to the information items that are relevant to the target domain i.e.:

•	Their semantics and their relationships between one another.

•	Their evolution and the rules for every information item’s evolution.

The IS-properties defined in the business information view are:

	Information items:

The identification of the information in the information resource in the target domain.

	Value ranges:

Possible values that occurrences of information items may take.

	Static dependencies:

The static dependencies between the information items, for example:

-	Relationships, e.g. binary or N-ary relationships, aggregation relationships, generalisation relationships.

-	Constraints between relationships, e.g. equality, exclusion, inclusion, cardinalities, functional dependencies.

	Item evolution:

The evolution of information items, in terms of the changes that can happen to an occurrence from its creation to its deletion. This includes the events that trigger these changes, the dynamic dependencies between these changes (e.g. sequence, alternative, iteration) and the events that are generated by these changes.

Business process view

The purpose of the business process view is to represent the processes in the target domain, independently of how these are performed by actors in the actual working practices. It encompasses the IS-properties characterising the knowledge about:

•	The processes in the target domain.

•	Their relations to one another.

•	Their triggering events and conditions.

•	Their use of the information resource.

The IS-properties defined in the business process view are:

	Business processes:

Identification of the processes in the target domain and their goals.

And for each business process:

	Triggering business events:

The events which may trigger the business process; and their origin.

	Triggering conditions:

The conditions that must be satisfied to trigger the business process.

	Generated business events:

The events which are generated by the business process; and their destination.

	Business process decomposition:

The decomposition of the business process into sub-processes. Sub-processes may be considered as processes and be described in the same way. Sub-processes may also be decomposed.

	Dynamic dependencies:

The dynamic dependencies between sub-processes of the business process, for example sequence, alternative, iteration, parallelism, synchronisation, information dependencies.

	Business rules:

The business rules governing the business process.

	Information use and generation:

The information used and generated by the business process.

The business information view and the business process view together encompass the properties that define a view of an information system that is independent of any actors (human or computer) performing the processes in the target domain and using the information resource.

Work practice view

The purpose of the work practice view is to represent the actors, and the way in which they perform the processes in the target domain and make use of the information resource.

The concept of task is used in the work practice view: a task is (a part of) a process performed by an actor.

The work practice view encompasses those IS-properties which characterise knowledge regarding:

•	The actors of the information system under consideration together with the organisational structure they work in and the physical locations they work at.

•	The tasks by which they achieve the business processes (as represented in the business process view) and the (partial) computerisation of these tasks.

The IS-properties defined in the work practice view are:

	Actors:

Identification of the actors (human and computer systems) in the information system; and their skills or capabilities, training requirements, etc.

	Locations:

The locations at which the actors work.

	Organisational structure:

The organisational relationships between the actors. This includes the aggregation of actors into organisational units (organisational units are considered as actors too).

	Communications:

The communications between the actors.

	Access needs and rights (of actors):

The information access needs and necessary rights for each actor, i.e. the external views of the actors on the information resource.

	Tasks:

Identification of the tasks in the information system and their goals.

And for each task:

	Task rules:

The rules or procedures governing the task.

	Computerisation:

The way of performing the task: manual, computerised or interactive. An interactive task is partly performed by human actors and partly by the computer system. The details of the computerisation are defined with the task decomposition.

	Task decomposition:

The decomposition of the task into sub-tasks. Sub-tasks may be considered as tasks and be described in the same way. Sub-tasks may also be decomposed.

An interactive task can be decomposed in manual and computerised sub-tasks. A computerised task is usually not decomposed (it may be decomposed in the computer function view).

	Information use and generation:

The (computerised and non-computerised) information used and generated by the task.

	Dynamic dependencies:

The dynamic dependencies with other tasks and between the sub-tasks of the task, for example sequence, alternative, iteration, parallelism, synchronisation, information dependencies.

	Triggering organisational events:

The events which may trigger the task; and their origin.

	Generated organisational events:

The events which are generated by the task; and their destination.

	Triggering conditions:

The conditions that must be satisfied to trigger the task.

	Performer:

The actor performing the task.

	Manager:

The actor controlling the task.

	Resources:

The resources necessary for performing the task.

	Static human-computer interface:

The information that has to be passed through the human-computer interface (this includes the definition of screen layouts, paper reports, etc.) and the organisational events which are generated by a manual task and trigger a computerised task or which are generated by a computerised task and trigger a task performed by a human actor.

	Behaviour of the human-computer interface:

Triggering conditions for the human-computer interface.

The behaviour of the human-computer interface also depends on the dynamic dependencies between computerised and manual tasks.

Computer system data view

The purpose of the computer system data view is to represent the computerised part of the information resource. It encompasses those IS-properties which characterise knowledge regarding:

•	That data representing the information resource which is retained in the computer system.

•	Those mechanisms enforcing the static and dynamic dependencies of that data.

The IS-properties defined in the computer data view are:

	Retained data:

The data retained in the computer, representing the information items that are computerised, and other data necessary for the functioning of the computer system.

	Value ranges:

Possible values that occurrences of data may take.

	Static dependencies:

The static dependencies between the data, for example:

-	Relationships, e.g. binary or N-ary relationships, aggregation relationships, generalisation relationships.

-	Constraints between relationships, e.g. equality, exclusion, inclusion, cardinalities, functional dependencies.

	Data evolution:

The evolution of data in terms of the changes that can happen to an occurrence from its creation to its deletion. This includes the events that trigger these changes, the dynamic dependencies between these changes (e.g. sequence, alternative, iteration) and the events that are generated by these changes.

Computer system function view

The purpose of the computer system function view is to represent the automated parts of the actor’s tasks independent from any processing units.

The concept of function is used in the computer system function view: a function is a part of a process performed by the computer system.

Some functions correspond to a specific computerised task (or parts of it) but other functions are supporting a certain number or all of the computerised tasks. These support functions are necessitated by the functioning of the computer system.

The computer system function view encompasses those IS-properties that characterise knowledge regarding:

•	The functions performed by the computer system.

•	Their use of the data retained in the computer system.

•	The corresponding data interfaces.

The IS-properties defined in the computer function view are:

	Functions:

Identification of the functions of the computer system and their purpose.

And for each function:

	Input messages:

The messages which may trigger the function; and their origin.

	Triggering conditions:

The conditions that must be satisfied to trigger the function.

	Output messages:

The messages which are generated by the function; and their destination.

	Function decomposition:

The decomposition of the function into sub-functions. Sub-functions may be considered as functions and be described in the same way. Sub-functions may also be decomposed.

	Dynamic dependencies:

The dynamic dependencies between sub-functions of the function, for example sequence, alternative, parallelism, iteration, synchronisation, data dependencies.

	Function rules:

The rules or procedures governing the function.

	Data access:

The retained data used and updated (created, deleted or modified) by the function.

Computer system architecture view

The purpose of the computer system architecture view is to represent the processing units of the computer system, the structure of the computer system and its physical characteristics.

A processing unit is a processor contained in the computer system. A processing unit in the computer system is analogous to actor of the information system.

The computer system architecture view encompasses those IS-properties that characterise the knowledge regarding the processing units in the computer system, their locations, their connections and the distribution of data, and functions to them.

It also encompasses those IS-properties that characterise the knowledge about the hardware, the system software and the application software constituting the computer system.

The IS-properties defined in the computer system architecture view are:

	Processing units:

Identification of the processing units in the computer system; and their type.

	Locations:

The locations where the processing units reside.

	Structure:

The structure of the computer system showing the relationships between processing units.

	Data distribution:

The distribution of data storage to the processing units.

	Function distribution:

The distribution of functions to processing units. The allocation of a function to processing units may require that further decomposition of this function, than has been performed in the computer system function view, is performed.

	External communication:

The external communication links of the processing units to the computer systems of other information systems.

	Internal Communication:

The communication links between the processing units of the computer system.

And for each processing unit:

	Hardware description:

The technical data on hardware devices on which the processing unit is implemented (e.g. processor type, memory size, transmission rate, storage capacity, etc.).

	System software description:

The technical data on system software on which the processing unit is implemented (operating systems, database systems, transaction monitors, network management systems, compilers, etc.).

	Application description:

-	Physical data: the description of the implementation of the stored data on the specific hardware and system software.

-	Programs: the description of the implementation of the functions on the specific hardware and system software. Programs can be decomposed depending on the processing units, e.g. human-computer interfaces on local processing units and handling of data accesses on central processing units.

### 3.3.3.	Non-functional Properties

In addition to stating requirements to the IS-properties that describe the structure and functionality the information system must have, there also exist requirements that put constraints on the way in which the information system is realised. These requirements are characterised in terms of non-functional properties. They relate to the performance and quality of the system and to its resourcing constraints.

A non-functional property can be related to:

•	The whole information system .

In this case it defines a general constraint, that applies to every component of the system or the system as a whole.

For example: “The new information system must be able to handle 250% of the current system’s maximum load.”

•	Some IS-properties.

In this case it defines a constraint that applies to all instances of that IS-property.

For example: “All application software must be portable to the operation systems X, Y, and Z.”

•	One instance of an IS-property.

In this case it defines a constraint that only applies to the specified instance of the IS-property.

For example: “The performer of the task Change-Financial-Status must have authorisation level 1.”

Especially for prototypes, where the specification of IS-properties shall be checked against requirements statements, it has to be defined which IS-properties shall be prototyped, and against which requirements and non-functional properties the prototype shall be measured.

The following list of non-functional properties is examples based on the ISO-9126 Standard:

	Cost:

The costs of production, maintenance and operation of the information system or of an individual component.

	Benefit:

The benefits that a component brings to the higher level component containing it or to the information system; or the benefits that the information system brings to the organisation’s business.

	Volume:

The number of component occurrences of a certain type: e.g. maximum number of occurrences of information items; average number of simultaneously performed occurrences of tasks; etc.

	Frequency:

The frequency of execution of a process, task or function.

Frequency of changes to an information item, or a data.

	Duration:

The duration of a process, task or function.

	Efficiency:

The relationship between the level of performance of the information system (or a component) and the amount of resources used, under stated conditions. Efficiency may be related to time behaviour (response time, processing time, throughput rates) and to resource behaviour (amount of resources used and duration of such use).

	Security:

Ability of the information system (or a component) to prevent unauthorised access, whether accidental or deliberate, to programs and data.

	Criticality:

The criticality of the information system (or a component) expresses the significance which will be given to that system or component in case of a functional failure. The criticality is expressed in levels; the higher the level, the more severe the consequences are in case of a functional failure.

	Reliability:

The capability of the information system (or a component) to maintain its level of performance under stated conditions for a stated period of time. The mean time to failure metric is often used to assess reliability. The necessary reliability can be secured through defining the:

-	Necessary level of protection against failures.

-	Necessary measures for recovery from failures.

	Maintainability:

Maintainability bears on the effort needed to make specified modifications to the information system (or a component).

Modification may include corrections, improvements or adaptation to changes in environment, and in requirements and functional specifications.

	Portability:

The ability of the computer system (or one of its components) to be transferred from one environment to another.

	Usability:

Usability bears on the effort needed for the use of the computer system (or one of its components) by the actors.

This list is not meant to be exhaustive. In some IS-adaptations and for some organisations additional non-functional properties may be identified.

### 3.3.4.	Consistency Rules between the Views

The different views are not independent from one another but are linked by a set of consistency rules. These rules must be obeyed by any consistent description of an information system.

In this section, the essential consistency rules between the above introduced IS-properties and thus between the information system and computer system views, that have to be respected to make an information system specification consistent, are defined. These rules are stated in general terms: they must be refined when dealing with specific modelling techniques.

Business process and business information view

•	Every information item must be used or updated (created, modified, deleted) by at least one business process.

•	Every information item that can be used or updated (created, modified, deleted) by a business process must be described.

•	There must be a relationship between the set of events triggering changes of information items and the set of business events.

•	The evolution of information items must be consistent with the dynamics of the business processes.

Work practice and business process view

•	Every business process must be achieved by one or several tasks.

•	Every business event must correspond to at least one organisational event.

•	The dynamics of the tasks  must be consistent with the dynamics of the business processes.

•	The information used and generated by a task must be consistent with the information used and generated by the part of the business process it achieves.

•	The information access needs and rights of an actor must be consistent with the information used and generated by the tasks it performs and thus with the information used and generated by the business processes achieved by these tasks.

•	The task rules must be consistent with the business rules.

•	The communication between the actors must be consistent with the dynamics of the tasks they perform and thereby with the dynamics of the business processes achieved by these tasks.

Work practice and business information view

•	The external views of the actors must be consistent with the description of the information items and their static dependencies.

•	Every information item must be used or updated (created, modified, deleted) by at least one task.

•	Every information item that can be used or updated (created, modified, deleted) by a task must be described.

Computer system data and business information view

•	The data retained in the computer system must correspond to information items or otherwise be necessary for the functioning of the computer system.

•	The aggregation and generalisation relationships between data must be consistent with the aggregation and generalisation relationships between information items.

•	The value ranges of data must be consistent with the value ranges of information items.

•	The static dependencies between data must be consistent with the static dependencies between information items.

•	The data evolution must be consistent with the information item evolution.

Computer system function and work practice view

•	Every computerised task must correspond to a function.

•	The dynamics of the functions  must be consistent with the dynamics of the tasks.

•	The retained data used and updated by a function must be consistent with the information items used and updated by the corresponding computerised tasks.

•	The function rules must be consistent with the corresponding computerised task rules.

•	The organisational events which are part of the human-computer interface must correspond to input and output messages of functions.

Computer system function and computer system data views

•	Every retained data must be used or updated (created, modified, deleted) by at least one function.

•	Every retained data that can be used or updated (created, modified, deleted) by a function must be described.

•	The evolution of data must be consistent with the functions' dynamics .

Computer system architecture and computer system function view

•	Every function must be allocated to at least one processing unit.

•	The communication links of the processing units must allow the messages to be exchanged between the distributed functions.

•	Every function must be realised by the hardware, system software or application software.

Computer system architecture and computer system data view

•	Every retained data must be allocated to at least one processing unit.

•	The communication links of the processing units must allow the static and dynamic dependencies (expressed in the data evolution) of the data to be maintained when they are distributed.

•	Every retained data retained must correspond to at least one physical data.

Computer system architecture and work practice view

•	The locations of functions must be consistent with the locations of those actors interfacing with them.

## 3.4.	IS-Descriptions - Definition of the Amount of Content

An important issue for customers and suppliers when planning an IS-adaptation, is to define an appropriate deliverable to make a certain decision. An appropriate deliverable is that one which contains the knowledge appropriate to make the required decision, and which will maximise the value for money.

Using Euromethod, the type of knowledge to be contained in an IS-description can be characterised by the concepts introduced above:

•	IS-description types.

•	Views.

•	IS-properties.

•	Non-functional properties.

Nevertheless, for an individual decision, it may not be necessary to have a fully developed IS-description available. Therefore, the customers and suppliers need a means to define to what detail the properties should be described to facilitate the required decision and to maximise the value for money.

Euromethod supports that by the following concepts:

•	Development state.

•	Deliverable scope.

•	Degree of formality.

### 3.4.1.	Development State

The development state can be used to characterise the amount of knowledge the deliverable must contain. This amount, i.e. the detail included or excluded, can vary between a fully developed product and a product where only parts are produced.

Using Euromethod, the level of detail is characterised by the level of abstraction related to the two general abstraction mechanisms: aggregation (decomposition) and generalisation (specialisation).

A development state of an IS-description is thus characterised by:

•	Degree of decomposition.

•	Degree of specialisation.

In a specific IS-adaptation, the customers and suppliers might identify additional means to characterise the necessary level of detail depending on the methods used, in particular depending on the modelling techniques used.

Take note!	In the process model of a supplier’s method, products are generally considered in a variety of different development states. But only a few of these will actually be given as deliverables to the customer.

It is only the states of the deliverables to the customer that are relevant in the customer-supplier relationship.

The degree of decomposition

The  indicates to what extent a system (information system or computer system) is decomposed within the IS-description.

The degrees of decomposition are defined as follows:

•	A deliverable is developed to a high degree of decomposition if all the system parts it captures are completely decomposed and described. A description is usually considered complete if no subsequent decomposition is required for the construction of the system and no further elements need to be added to the description.

•	A deliverable is developed to a low degree of decomposition if not all hierarchical levels are identified and described.

Some IS-properties are often described using hierarchical decomposition. For these the degree of decomposition relates to the number of decomposition levels. For example:

•	Business processes in the business process view.

•	Tasks, actors or organisational structures in the work practice view.

•	Functions in the computer function view.

•	Processing units in the computer architecture view.

Some IS-properties are often described using non-hierarchical techniques. For these the degree of decomposition generally relates to the elements of the technique that have to be described or can be omitted. For example:

•	Information items in the business information view.

•	Retained data in the computer system data view.

Example: A deliverable describing the first level of a function decomposition can be regarded as having a low degree of decomposition. Describing the complete function decomposition and providing descriptions of all the functions that are not decomposed further, can be regarded as the high degree of decomposition.

For a particular IS-adaptation, a range of degrees of decomposition may be defined where necessary, to facilitate a sequence of related decisions within that IS-adaptation.

The degree of specialisation

The  indicates whether the IS-description describes a generalised, and thus simplified, system (information system or computer system) or the system in all its specificity with all its special behaviours.

The degrees of specialisation are defined as follows:

•	A deliverable is developed to a high degree of specialisation if all the sub-types of the captured properties (processes, events, actors, etc.) or special cases are identified and described.

•	A deliverable is developed to a low degree of specialisation if not all the sub-types of the captured properties (processes, events, actors, etc.) or special cases are identified and described. Only the normal cases or general cases are described.

Example: A deliverable describing a sales process with all the special cases (domestic and international customers, different credit conditions, urgent and normal orders, etc.) defined can be regarded as having a high degree of specialisation. Describing the most usual cases only (domestic customer, normal order, etc.) can be regarded as the low degree of specialisation.

For a particular IS-adaptation a range of degrees of specialisation from low to high may be defined where necessary, to facilitate a sequence of related decisions within that IS-adaptation.

### 3.4.2.	Deliverable Scope

The deliverable scope defines whether the knowledge captured in a deliverable should have:

•	Full scope:

i.e. be described for the whole target domain, e.g. description of all processes in the target domain.

•	Partial scope:

i.e. be described for only a subset of the target domain, e.g. description of one process in the target domain. A set of similar deliverables is then necessary to cover the full scope. Sometimes the partial scope may be determined in terms of business area, organisational unit, or set of processes in the target domain.

The state and scope of a deliverable may be combined in different ways to provide the right basis for a decision, e.g. a decision about the:

•	Feasibility, costs and benefits of a system usually requires a full scope and low degrees of decomposition and specialisation.

•	Adequacy of a human-computer interface related to a certain task will require a partial scope, and high degrees of decomposition and specialisation.

For a particular IS-adaptation a range of partial scopes may be defined where necessary, to facilitate a sequence of related decisions within that IS-adaptation.

### 3.4.3.	Degree of Formality

The degree of formality describes the type of representation language that should be used in a deliverable. The degree of formality of a deliverable can be described as:

•	Formal;

if the representation language is based on mathematical or logic calculation systems.

•	Semi-formal;

if the representation language is based on graphical notations with defined meaning of the symbols or a textual notation consisting of a limited set of constructs with defined meaning and syntax.

•	Informal;

if the representation language is based on natural language, graphical illustrations, animation, etc.

## 3.5.	Operational Items

Operational items are deliverables that can be used as operational parts of the information system. Operational items are considered as either the instructions manually performed by human actors, or the hardware and software items found within the computer system.

The different types of operational items that can be characterised are:

•	Hardware s:

Computers, networking devices, storing devices, input-output devices, etc.

•	System :

Application independent software that supports the running of application software [ISO-2382-20]; e.g. operating systems, database management systems, transaction monitors, tools, etc.

•	Application :

A software that is specific to the solution of an application problem [ISO-2382-20]; and whose characteristics are determined by the specification of the information system. Application packages that fit the specification of the information system and therefore can be used are included here.

•	Data occurrences:

The occurrences of data of the target domain. These data must be migrated in case of a replacement of the computer system.

•	User :

Written documentation that facilitates the use and operation of the computer system by the human actors of the information system.

•	Work , job descriptions:

The instructions that the human actors of an information system have to follow in their work.

•	E, migration programmes:

The products and services that facilitate the migration to a new information system version and the education of human actors. This includes the actual training of the human actors in the information system.

## 3.6.	Quality State

The purpose of attributing a quality state to a target domain deliverable is to ensure that the quality procedures related to that quality state will be successfully completed prior to the delivery.

The quality states of target domain deliverables are characterised by the:

•	Review procedures, for IS-descriptions.

•	Test procedures, for operational items.

In both cases these procedures are intended to demonstrate the conformance of a deliverable with defined quality structures and criteria.

Which quality procedures and thus which quality states are used in the production process, depends on the individual IS-adaptation. The quality assurance plan of an IS-adaptation prescribes this set of quality procedures.

The quality state required for a deliverable at a certain decision point depends on the type of decision. Certain types of decisions do not require that certain quality requirements are checked or that the ultimate quality procedures have been applied.

Examples

Examples of review procedures (and thus of possible quality states) are:

•	Reviews,

where issues related to the target domain deliverables are raised.

•	Inspections,

where a line by line check of the target domain deliverables is performed.

Examples of tests (and thus of possible quality states) are:

•	Unit test:

Does a single operational item fulfil its specification?

•	Integration test:

Do a set of operational items co-operatively fulfil the related specification?

•	Test of single requirements:

Are the performance, security, stability, etc. requirements fulfilled?

# 4.	Project Domain Deliverables

This Chapter explains:

•	What a project domain deliverable is.

•	What the types of project domain deliverables are.

## 4.1.	The Types of Project Domain Deliverables

Project domain deliverables describe the project domain. They may be delivered by the supplier in order to give the customer control over, and confidence in, the content and quality of the target domain deliverables. They may also be delivered from the customer to the supplier in order to define customer requirements to the project organisation.

Information regarding the target domain deliverables production may therefore be of interest to the customer. It is useful to facilitate the customer’s decision making. Project domain deliverables are used to capture the relevant knowledge of the project’s production process.

Based on the separation of concerns within an IS-project into project management and IS-production and their relationships, two types of project domain deliverables with different content are identified:

•	Project plans:

The customer and the supplier need to have some control over the project's internal production process, in order to ensure that the goals of an IS-adaptation are reached. This control, i.e. the process requirements put on the project's internal production process is defined in project plans.

A project plan is also a means to define the necessary quality that has to be built into the target domain deliverables.

•	Project reports:

At a delivery the customer must have the means to assess the adequacy of the target domain deliverables. Besides the assessment of the content of the target domain deliverables, the customer assesses whether the defined process requirements have been met. The project domain deliverables capturing this knowledge about the project's internal production process are project reports. They document how the project plans were fulfilled, and thus, how the planned criteria were met.

Figure 8 shows the types of project domain deliverables introduced above.

Figure 8: The types of project domain deliverables.

A project domain deliverable captures knowledge about the IS-project's internal processes. This knowledge is characterised by the project property properties that the deliverable describes.

This allows a flexible characterisation of project domain deliverables. By the selection of the project properties that are prescribed in project plans and documented in project reports, the required rigour of the control over the project's internal process can be defined.

## 4.2.	Project Plans

Euromethod characterises the contents of project plans by means of a set of project properties addressing the three work areas defined in the Transaction Model [EM-3.1-TM]:

•	Development.

•	Quality assurance.

•	Configuration management.

Project plans can serve for two purposes:

•	They can define the project domain of the current IS-adaptation.

•	They can be deliverables that define the project domain of a future IS-adaptation.

The latter is used when an IS-adaptation has to produce a proposal for a subsequent IS-adaptation.

The first actually defines the project domain of the current IS-adaptation. This is the meaning in which the term project plan for the target domain is generally used in the Euromethod documents.

Development Plan Properties

The internal development plan of a supplier, plans the activities related to the production of the target domain deliverables. It is a refinement of the delivery plan and it must always be kept consistent with it.

The information contained in such a project plan that is of interest to the customer, and thus is relevant in the customer-supplier relationship, is principally the planning of the supplier's use of customer resources (personnel that is interviewed or involved in the production, documentation). However, in some cases (non fixed price contracts for example), the customer is also interested in the planning of the supplier resources to be convinced that the necessary resources for producing quality deliverables will be available .

It may be used to ensure that:

•	The correct information is used at the right time in the production of the target domain deliverables, which predicts the adequacy of the target domain deliverables that can be achieved.

•	The customer can plan for the availability of the resources to the supplier, which are necessary for the efficient work in the project.

•	The supplier is using the necessary resources.

The required content of a development plan can be characterised using the following project properties:

The target domain deliverables the plan is related to. These deliverables may go from the supplier to the customer and vice-versa.

Development organisation:

-	Structure (including sub-projects possibly sub-contracted).

-	Tasks and responsibilities.

-	Interfaces.

Network of tasks and their schedules.

Detailed manpower and budget.

Customer resources to be involved in the production of these deliverables, e.g. user experts; and their availability, e.g. number of interviews, user expert involvement in production; and their training.

Supplier resources to be involved in the production of these deliverables; and their training.

Input products to be used in the production of the deliverables and their availability, e.g. time when and location where input products can be accessed.

Infrastructure (hardware, software, CASE tools, etc.).

Quality Assurance Plan Properties

For target domain deliverables, a required quality state can be defined. This state defines the quality assurance procedures the IS-project has to perform and that must be successfully completed for the deliverable prior to its delivery to the customer. The information related to the quality procedures is relevant for the customer-supplier relationship.

The purpose of a quality assurance plan is to define the required quality assurance procedures that a deliverable has to pass in order to be considered of adequate quality.

A quality assurance plan thus allows to define the adequate quality of target domain deliverables in terms of quality requirements, i.e. quality criteria, that have to be fulfilled, and procedures that have to be followed in order to assure that the quality requirements are met.

The required content of a quality assurance plan can be characterised using the following project properties:

The target domain deliverables the plan is related to.

Quality management organisation:

-	Structure.

-	Tasks and responsibilities.

-	Interfaces.

The definition of the quality assurance procedures:

-	The definition or reference to the quality requirements that have to be checked for the deliverables.

-	The definition or reference to the quality assurance procedures that have to be applied to check the target domain deliverables against the quality requirements.

-	The planning of the execution of the quality assurance procedures,

e.g. involved resources, date, etc.

Configuration Management Plan Properties

A configuration management plan regulates the configuration management of the related target domain deliverables. Especially in large IS-adaptations, where several versions of target domain deliverables are used or installed into the considered information system, the customer needs to have some control over the configuration management.

In such a case the change control over the project plans might require co-operation between customer and supplier, in which case there may be a configuration management plan related to the project plans.

The required content of a configuration management plan can be characterised using the following project properties:

The target domain deliverables or project plans, the plan are related to.

Configuration management organisation:

-	Structure (e.g. change control board, deliverable library, etc.).

-	Tasks and responsibilities.

-	Interfaces.

Change procedure.

Type of version control.

## 4.3.	Project Reports

Euromethod characterises the contents of project reports by means of a set of project properties addressing the three work areas explained in the Transaction Model [EM-3.1-TM]:

•	Development.

•	Quality assurance.

•	Configuration management.

Additionally, Euromethod considers:

•	Project status reports,

which provides a description of the project status with regard to the delivery plan.

Development Report Properties

A development report permits the assessment of the deviations from the development plan. It reports on whether the correct expertise went into the production of the related target domain deliverables and on deviations from the planned inputs and resourcing. It thus supports the assessment of the content of the related target domain deliverables.

The required content of a development report can be characterised using the following project properties:

The target domain deliverables the report is related to.

Progress statement.

Used manpower and cost statement.

Customer resources actually involved in the production of these deliverables, and use made of these resources, e.g. number of interviews, involvement in production.

This allows an assessment of whether the correct sources of knowledge were used and whether they were used effectively.

Supplier resources actually involved in the production of these deliverables.

The actual input products to the production of the target domain deliverables and the use made of these inputs, e.g. references.

This allows an assessment whether the correct input documents were used and whether they were used effectively.

Deviations from the development plan (manpower, schedules, budget, etc.).

Proposal for corrective actions.

Proposal for changes in the development plan.

Quality Assurance Report Properties

The purpose of a quality assurance report is to document that the required quality assurance procedures are successfully completed.

The required content of a quality assurance report can be characterised using the following project properties:

The target domain deliverables the report is related to, and that were subject of the quality assurance procedures.

Report on the quality assurance procedures:

-	The quality state that is required for these target domain deliverables at the decision point (and which they have at delivery time as a result of the performed quality assurance).

-	The definition or reference to the quality requirements that were checked for the target domain deliverables (as defined by the quality assurance plan of the IS-adaptation).

-	The definition or reference to the quality assurance procedures (as defined by the quality assurance plan of the IS-adaptation) that were applied to check the target domain deliverables against the quality requirements.

-	Information on the execution of the quality assurance; involved resources, date, etc.

The protocol of the quality assurance procedures:

-	Documentation of the results of the performed quality assurance procedures.

-	Procedures taken to remove the identified defects, if any; and results of the quality assurance procedures related to these procedures.

Additionally, an evaluation of the quality assurance may identify project risks. During the customer-supplier transaction assessing the related target domain deliverables, the provided evaluation of the quality assurance may thus lead to the definition of corrective actions or revisions of project plans, and thus trigger customer-supplier transactions for approving process improvements or project plans. The related content of a quality assurance report can be characterised using the following project properties:

An evaluation of the quality assurance:

-	Sources of the detected defaults can be identified.

-	Trends of deviations between the planned results and observed expectations can be identified.

-	Based on the identified problems, a risk assessment can be provided.

-	Corrective actions can be proposed.

Configuration Management Report Properties

A configuration management report gives information about the configuration management of the related target domain deliverables or project plans. Especially where the changes of the deliverables are of interest in the customer-supplier relationship.

The required content of a configuration management report can be characterised using the following project properties:

The target domain deliverables or project plans the report is related to.

The change requests to the related deliverables.

The accepted changes to the related deliverables.

Project Status Report Properties

The purpose of the project status report is to give a description of the project status with regard to the delivery plan. The report facilitates the assessment of project risks and the definition of necessary corrective actions in the customer-supplier transactions dealing with the approval of project status and plans.

The required content from a project status report can be characterised using the following project properties:

Deviations from the delivery plan:

-	Schedules.

-	Budget.

-	Resource availability.

New issues to the IS-project:

-	Project risks detected during IS-development or quality assurance procedures.

-	Problems.

If considered necessary, the project status report can contain the following project properties:

Proposals for corrective actions.

Proposals for changing the delivery plan.

Proposals for contract change control.

This completes the definition of the project domain deliverable types used by Euromethod for the description of the content of project domain deliverables, i.e. for the description of the internal processes and status of the IS-project.

## 4.4.	Quality State

For project plans similar quality assurance mechanisms as for target domain deliverables can be applied. The quality states here are characterised by the:

•	Review procedures, for delivery and project plans of IS-adaptations.

These procedures are intended to demonstrate the conformance of a deliverable with defined quality structures and criteria.

Which quality procedures and thus which quality states are used in the production process, depends on the individual IS-adaptation. The quality assurance plan of the current IS-adaptation prescribes this set of quality procedures.

Examples

Examples of review procedures (and thus of possible quality states) are:

•	Reviews,

where issues related to the planning of an IS-adaptation are raised.

•	Inspections,

where a detailed check of a plan is performed.

# Annex

# A.	Concepts Overview

Figure A.1. The concept used for describing the type content of deliverables.

Figure A.2. The concepts used to describe the amount and quality of information in deliverables

# References

[EM-1-EO]	Euromethod Overview, 1994

[EM-2.1-CG]	Euromethod Customer Guide, 1994

[EM-2.2-SG]	Euromethod Supplier Guide, 1994

[EM-2.3-DPG]	Euromethod Delivery Planning Guide, 1994

[EM-2.4-MBG]	Euromethod Method Bridging Guide, 1994

[EM-2.5-CS]	Euromethod Case Study, 1994

[EM-3.1-TM]	Euromethod Concepts Manual 1 - Transaction Model, 1994

[EM-3.3-SM]	Euromethod Concepts Manual 3 - Strategy Model, 1994

[EM-4-ED]	Euromethod Dictionary, 1994

---------

[87/95/EEC]	The EEC Standards Decision.

[92/50/EEC]	The EEC Service Directive: 
Council Directive 92/50/EEC of 18 June 1992 relating to the co-ordination of procedures for the award of public service contracts.

[IEEE-729]	IEEE. Standard Glossary of Software Engineering Technology. 09.08.83. ANSI/IEEE Std 729.

[IEEE-P1074]	IEEE. Standard for Software Life Cycle Processes.
IEEE Technical Committee for Software Engineering P1074/D5.
December 1989.

[ISO-2382-01]	ISO/2382/1. Data Processing - Vocabulary. Part 01: 
Fundamental Terms. Second edition. 1984-10-01.

[ISO-2382-07]	ISO/IEC/2382-7. Information Technology - Vocabulary. Part 07: Computer Programming. Second edition. 1989-10-15.

[ISO-2382-20]	ISO/IEC/2382-20. Information Technology - Vocabulary. Part 20: 
System Development. First edition. 1990-03-01.

[ISO-8402]	ISO 8402 Quality - Vocabulary: 1986.

[ISO-9126]	ISO 9126 Information technology - Software product evaluation 
- Quality characteristics and guidelines for their use: 1991.

[ISO-LCP] 	Information Technology Software Life Cycle Processes; 
Second Committee Draft 12207.2, ISO/IEC(JTC1)-SC7. June 1993.

[SEI-CMM] 	The Capability Maturity Model for Software.
Software Engineering Institute, Carnegie Mellon University, Pennsylvania. August 1991, CMU/SEI-91-TR-24.

# Index

actor 9; 17; 21; 24

application software 27; 38

business area 11

business information view 19

business process view 20

computer system 10; 26

computer system architecture view 26

computer system data view 24

computer system function view 24

computer system view 18; 19

configuration management plan 44

configuration management report 47

consistency 30

criticality 29

data 24

decision point 7

deliverable 4; 7

Deliverable Model 4

deliverable scope 36

deliverable state 9; 33

deliverable type 5; 13; 15; 40

delivery plan 6

development plan 42

development report 45

development state

degree of decomposition 35

degree of specialisation 36

educational courses 38

efficiency 29

event 20; 24

final state 7

final state information system 7

function 25

hardware device 27; 38

information item 19; 24

information resource 10; 24

information system 10

information system view 16; 19

initial state 6

initial state information system 6

IS-description 13

IS-property 16

maintainability 30

migration programme 38

non-functional properties 27

operational item 38

organisation 9

organisational unit 11

portability 30

process 9; 20

processing unit 26

processor 26

product 14

project domain 40

project domain deliverable 40

project plan 41

project property 41

project report 44

project status report 47

prototype 14

quality assurance plan 43

quality assurance report 46

quality state 39

reliability 30

requirement 14; 27

requirements statement 13

security 29

specification 14

system software 27; 38

target domain 9; 11

target domain deliverable 13

task 21; 24

usability 30

user and operator manuals 38

view 16

work instructions 38

work practice view 21

Document history of Euromethod Deliverable Model

| Version | Status | Author | Comment | Distribution |
| --- | --- | --- | --- | --- |
| 161293 | Being Developed | MP |  |  |
| 311293 | Ready for L2-review | MF | The following issues have been solved: 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 26, 27, 30, 39, 40, 41, 42, 43, 45, 54, 55, 56. Not done: 4 I think it is not necessary. For issue 26, I have decided to keep the same meaning for view and model. IS-description properties have been strengthened and restructured to facilitate method bridging. I propose that in the method bridging guide, - a deliverable can be decomposed into component deliverables, - there is one profile per modelling view, in order to forbid method owners to mix properties of several modelling views in one elementary product. | Project team |
| 210194 | L2-Accepted | MF/MG | Introduced changes from L2 review, checked consistency with new version of the Method Bridging Guide and smoothed the English where found appropriate. | Project Team Method Owners |
| 020294 | L2-Accepted | MF | Few modifications to put it in line with dictionary | Project Team |
| 280294 | Under L3-Review | MP | Change of non-functional properties, change properties and plans for future IS-adaptations. | Project Team, Review Group |
| 280394 | Under L3-review | NA | Revised on the basis of remarks from the review group and the project team. New document layout is used. | • AG • Project Team |
| 050494 | Delivered | NA | Revised on the basis of remarks from MP. New standards implemented. | EC |
| 060694 | Under EMPMB Review | MP | All EMPMB and national remarks - either identified for discussion with GW - or incorporated. | Project Team, GW |
| Version 0, June 1994 | Delivered | NA | Revised on the basis of remarks from the review group and GW. Marks are removed. | EC |

For an IS-adaptation that shall produce a specification of a future information system, a specification of the current information system can be part of the initial state. For an IS-adaptation that shall construct and install a new version of an information system, a specification of this future information system can be part of the initial state.

A description of a desired final state should contain the identification of the operational items that shall be replaced and the types of operational items that shall be added to or replace the current ones.

The definition of the final state of an IS-adaptation shows that the Euromethod concepts are designed to support “development projects”, “maintenance projects” and "design projects". These can be characterised as follows:

-	“Development projects” are mainly concerned with adding new operational items 	rather than replacing existing ones.

-	“Maintenance projects” are mainly concerned with the replacement of operational 	items rather than adding new ones.

-	"Design projects" are not changing the operational items installed in the 	information system.

The state information that is attributed to a deliverable is also referred to under the term deliverable state.

For IS-descriptions this encompasses the development and the quality state.

For operational items the deliverable state is its quality state.

The separation into a data and a function view does not exclude the use of object-oriented techniques. Deliverables using object-orientation typically integrate IS-properties from both views.

The relationships between an aggregate information item and its component information items.

The relationships between an information item and its sub-types (specialised information items). It is sometimes called an ISA relationship, or inheritance (simple or multiple).

In literature the term function is used with a variety of meanings. In the context of views and IS-properties, the meaning of function is restricted here to the computer system, i.e. it is used in the sense of “computerised function”.

There are different opinions whether a statement like “the response time for every user dialogue must not be longer than one second” should be interpreted as stating requirement for the information system or as specifying part of it as the definitions provided by ISO which use the terms “essential conditions that must be satisfied” and “definite description for developing and validating” leave room for interpretation. In order to facilitate a uniform description of deliverables one of the two possibilities had to be chosen. For Euromethod the first interpretation was chosen.

Stating for instance a response time is definite and can for example be checked in a simulation prototype. But in this case, the view taken in Euromethod is:

•	An essential condition is stated.

•	In the prototype it is checked whether the specified system satisfies this 	condition.

The dynamics of business processes are expressed by the triggering business events and conditions, the generated business events, and the dynamic dependencies.

The dynamics of tasks are expressed by means of the triggering organisational events and conditions, the generated organisational events, and the dynamic dependencies.

The dynamics of functions are expressed by means of the input and output messages, triggering conditions, and the dynamic dependencies.