Euromethod
Concepts Manual 1
Transaction Model

EM-3.1-TM

__________________________________

Abstract

This manual is one of three Euromethod Concepts Manuals. There is one manual for each of the models in Euromethod which between them contain all of the concepts provided by Euromethod.

The Transaction Model defines the trans-actions necessary to describe the customer-supplier relationship during an IS-adaptation. It thus provides the overall basis for planning the interactions between customers and suppliers; and it defines the usage scenarios in which Euromethod can be applied.

__________________________________

© Euromethod Project 1994

This document,

Euromethod Concepts Manual 1 - Transaction Model,

is a document of the Euromethod Version 0.

In the layered document structure of Euromethod it constitutes a part of the Concepts Manuals Level. It is referenced by the Guides and the Overview; and makes use of the definitions in the Dictionary.

ContentsÊofÊtheÊTransactionÊModel

1.	Introduction	4

2.	IS-Adaptations	5

2.1.	RelationshipsÊatÊaÊContractualÊLevel	5

2.2.	WorkÊAreas	9

2.3.	RoleÊConcepts	11

3.	Customer-Supplier Relationship Framework	16

3.1.	IS-AdaptationsÊandÊTransactions	16

3.2.	Customer-SupplierÊTransactionsÊandÊDecisionÊPoints	17

3.3.	TenderingÊProcess	18

3.4.	ProductionÊProcess	21

3.5.	CompletionÊProcess	23

3.6.	DeliveryÊPlan	24

4.	Customer-SupplierÊTransactions	28

4.1.	CallÊforÊTender	28

4.2.	TenderÊResponse	30

4.3.	SupplierÊSelection	32

4.4.	ContractÊAwarding	33

4.5.	ApprovalÊofÊDeliverables	35

4.6.	ApprovalÊofÊProjectÊStatusÊandÊPlan	38

4.7.	ContractÊChangeÊControl	39

4.8.	ApprovalÊofÊFinalÊDeliverables	41

4.9.	ContractÊCompletion	43

References	46

Index	48

# 1.	Introduction

This manual is one of three Euromethod Concepts Manuals: Transaction Model, Deliverable Model and Strategy Model. There is one manual for each of the models in Euromethod which between them contain all of the concepts provided by Euromethod.

Objectives

The objective of this manual is to describe all the Euromethod concepts that constitute the Transaction Model, and which thus provide the basis for the guidance supplied by the Euromethod Guides. That is, it provides the view that Euromethod takes on contractual relationships between customers and suppliers and the means to model and document these concepts.

The manual is intended to serve as a reference manual which provides the definitions of the concepts on which the guides are based. It is therefore expected that readers of this manual will come to it, as a means of obtaining clarification or greater detail regarding a concept described within the Euromethod Guides, or possibly even the Overview.

# 2.	IS-Adaptations

In Euromethod, the development of information systems is considered in the context of what is called information system adaptation. An information system adaptation (IS-adaptation) is any kind of modification (correction, enhancement, improvement etc.) and automation of an information system to fulfil the changing needs of an organisation.

## 2.1.	RelationshipsÊatÊaÊContractualÊLevel

The Euromethod definition views IS-adaptations from the point of view of contractual relationships between customers and suppliers. That means, Euromethod is concerned with those periods of the life of the same information system which are regulated by contracts and the processes of establishing contracts. The life of an information system will typically contain several IS-adaptations regulated by contracts, e.g. one or more change analysis studies, and one or more system description, construction, installation, or maintenance projects. This is illustrated in Figure 1.

When an IS-adaptation contract is established, the information system and the related products are in a certain state; in Euromethod this is called the initial state of the IS-adaptation. The state of the information system and the related products at the termination of the contract is called the final state of the IS-adaptation. Euromethod provides the means to define both flexible initial and final states of IS-adaptations, and contains examples of typical initial and final states.

Figure 1: Examples of IS-adaptations with contractual arrangements
during the life of an information system.

For IS-adaptations, the Euromethod definition distinguishes between two levels of customer-supplier relationships: a relationship at a contractual level and a relationship at a project level, as illustrated in Figure 2.

The contractual level involves two organisations, the customer and the supplier organisations and a temporary relationship. This relationship at a contractual level is considered as having a life history starting with the call for tender document issued by the customer, going through the signing of a contract and ending when the contract itself is terminated. This corresponds to the acquisition and supply processes, i.e. the contract view found in [ISO-LCP].

Figure 2: The two levels of the Customer-Supplier Relationship.

The IS-project level is a temporary organisation, called the project domain, which aims at adapting an information system within an organisation called the target domain. The IS-project has relationships with both the customer and the supplier organisations. The main input into the IS-project is the provision of skills and knowledge by the supplier and the main output is the delivery of products (and services) from the IS-project to the customer. Secondary inputs are the provision of resources from the customer to the IS-project (e.g. customer personnel) and the secondary output is the delivery of products from the IS-project to the supplier (e.g. products reusable in other projects).

When considering the two levels of a customer-supplier relationship, the objectives of Euromethod are:

1.	To enhance the customer-supplier relationship in IS-adaptation contracts. That is, the relationship at the contractual level.

2.	To provide the means to define an IS-adaptation in a way that allows customer requirements to be expressed unambiguously, and which allows the definition of the customer-supplier relationship throughout the IS-adaptation. That is, relationships between the contractual level and the IS-project level.

A refined view on an IS-adaptation (see Figure 3) can be gained by a breakdown of the IS-project into a decision hierarchy comprising:

¥	IS-production: which performs the actual production work.

¥	IS-project management: which controls the IS-production.

Project management gets information from the IS-production and provides directives and plans as feedback.

Figure 3: Model of an IS-adaptation system.

IS-production is the production sub-system of the IS-project performing the information system development processes, as well as supporting processes related to quality assurance and configuration management that achieve an adaptation. This sub-system is controlled by the project management sub-system. This corresponds to the development and maintenance processes, i.e. the engineering view and some of the supporting processes found in [ISO-LCP].

Project consists of project planning and project control [ISO-2382-20]. Project planning is concerned with the specification of the components, timing, resources, and procedures of the project. Project control is concerned with monitoring the progress of the project, its direction, quality, and resource utilisation, as compared with project plans. This corresponds to the management process, i.e. the management view found in [ISO-LCP].

## 2.2.	WorkÊAreas

A complementary view of an IS-project is gained by regarding this organisation as a set of work areas co-operating to reach the organisation objectives. Such a view is used in organisational modelling and it corresponds to the development, maintenance and supporting processes found in [ISO-LCP].

The main work areas of an IS-project are the following:

¥	IS-development,

aiming at developing the products and services required by the IS-adaptation.

¥	Quality assurance,

consisting of all those planned and systematic actions necessary to provide adequate confidence that a product or service will satisfy given requirements for quality [ISO 8402].

¥	Configuration management,

which is a discipline applying technical and administrative direction and surveillance to: identify and document the functional and physical characteristics of a configuration item, control changes to those characteristics, record and report change processing and implementation status, and verify compliance with specified requirements [IEEE-1991].

A configuration item is a product which is designated for configuration management and treated as a single entity in the configuration management process (adapted from [IEEE-1991]). Not all products are configuration items.

The work areas are relevant to both IS-production and project management. Together, it gives an integrated view of an IS-project, as illustrated in Figure 4. The planning and control of the project by project management (which includes both the identification and management of risk) is both addressing an integrated view on the work areas in the project and specific views on each of the work areas, i.e. the specific plans must be integrated within the overall project plan. This integrated view of a project is an underlying principle in the design of the Euromethod concepts.

| Figure 4: Integrated view on work areas and the decision hierarchy. Work area Decision hierarchy | IS-Development | Quality Assurance | Configuration Management |
| --- | --- | --- | --- |
| Project Management | Plan and control the project |  |  |
|  | Plan and control IS-development | Plan and control QA | Plan and control CM |
| IS-Production | Perform IS-development | Perform QA | Perform CM |

It is also recognised that there are some other work areas, such as training, administration, infrastructure management, etc. (the reader is referred to the ISO and IEEE Life-cycle Processes Standards [ISO-LCP, IEEE-P1074]). These may be regarded as secondary work areas, since they deal with the internal organisation and structuring of the IS-project, and as such are less relevant to the customer-supplier relationship.

## 2.3.	RoleÊConcepts

In regarding an IS-adaptation from the point of view of the customer-supplier relationship, only two types of roles are relevant in order to describe the organisations involved. These are those regarding the customer and the supplier organisations, which are the two contractual partners involved in the IS-adaptation. The two contractual partners involved in the IS-adaptation are:

¥	The customer in an IS-adaptation:

The organisation that recognises the need for an IS-adaptation and decides to contract it to a supplier.

¥	The supplier in an IS-adaptation:

The organisation (or consortium) to which the IS-adaptation is contracted.

During the tendering process until the contract awarding transaction, the supplier is seen as a potential supplier for this IS-adaptation. Any organisation that submits a technical proposal in response to a call for tender document, is considered as a supplier to an IS-adaptation. There will usually be several suppliers submitting technical proposals.

Within each of these two organisations two key roles are identified, which are relevant in every instance where a customer and a supplier interact. These are the contract authority and project authority:

¥	A contract authority  is:

the person, or persons with the power to resolve or conclude an open issue with regard to a specific IS-adaptation contract. One contract authority represents the customer organisation and the other represents the supplier organisation. It is not necessary, or necessarily desirable that the same person acts as the contracting authority for every transaction within a given IS-adaptation.

¥	A project authority  is:

the person, or persons with the power to resolve or conclude an open issue with regard to a specific IS-adaptation project. Again, one project authority represents the customer organisation and the other represents the supplier organisation. It is not necessary, or necessarily desirable that the same person acts as the project authority for every transaction within a given IS-adaptation.

The behaviour of these key role types are affected by the imposition of external directives or constraints, and the provision of appropriate expertise respectively during certain transactions. That is, there are a number of further role types whose role is to either provide input with regard to the organisational direction, or to provide a particular expertise needed within a certain transaction. These are summarised as organisational authorities and operational expertise, which are found in both the customer and supplier organisations:

¥	An organisational authority is:

the role of a person or group of people with the power to resolve or conclude an open issue with regard to the strategic requirements of the organisation. Therefore at one level, any decision made by a contract authority may be affected by a number of organisational authorities found in his organisation. The implication of this fact, is that a decision can be imposed upon the contract authority by one of the organisational authorities within the organisation.

¥	An operational expertise role is:

the role of a person or group of people performing a development task or acting as an opinion maker based upon their expertise, skills or knowledge with regard to a specific IS-adaptation topic. In performing their work, the project authority roles make use of various skilled resources within their organisations. That is, they make use of operational expertise.

The role concepts are represented graphically in Figure 5.

Figure 5: The roles related to IS-adaptations.

Examples of organisational authorities which may affect the direction of an IS-adaptation are:

¥	Senior management:

Ensuring that the proposed IS-adaptation is in line with the strategic and tactical direction of the organisation.

¥	Customer financial authority:

Ensuring that the financial commitment required by the proposed IS-adaptation, and any amendments to the IS-adaptation are consistent with the financial constraints of the organisation

¥	Customer legal authority:

Ensuring that the organisation undertakes the IS-adaptation (and makes any amendments to the IS-adaptation) within the legal constraints of applicable European directives, national laws and GATT trade agreements; and ensuring that the contract regarding a particular IS-adaptation is legally sound.

¥	Customer QM-authority:

Defining the quality management requirements expected during an IS-adaptation and ensuring that these quality management requirements are adhered to.

Examples of operational expertise role types which are available to the supplier and customer project authority roles are:

¥	IS-expertise:

This operational role consists of the following:

-	Business expertise:

Providing operational resource and give expert opinion, skill or knowledge with regard to the business requirements to be considered by the IS-adaptation.

-	Technical expertise:

Providing operational resource and give expert opinion, skill or knowledge with regard to technical requirements of the IS-adaptation.

-	User expertise:

Providing operational resource and give expert opinion, skill or knowledge with regard to the user interests within the IS-adaptation.

¥	QA-expertise:

Providing operational resource and give expert opinion, skill or knowledge with regard to the quality assurance expertise required within the IS-adaptation.

¥	CM-expertise:

Providing operational resource and give expert opinion, skill or knowledge with regard to the configuration management expertise required within the IS-adaptation.

Although there is a degree of symmetry regarding the types of expertise needed by the supplier and customer project authorities, the requirements on these types of expertise are different for the customer and supplier organisations. For example, the information system expertise required by the customer organisation is primarily focused on the operation of the information system in the target domain, while for the supplier, expertise must be available for the technical design and construction activities as well related to the information system.

The roles identified by Euromethod are meant to represent authorities and responsibilities within an IS-adaptation and also the skills and knowledge provided. In a particular IS-adaptation each of the roles may be performed by a single person or a group of persons (especially the operational expertise is generally provided by a group of persons e.g. the project team). It can also be the case that a single person performs several roles, e.g. a person managing the supplier's work may thus perform the project authority role and at the same time participate in the work by providing operational expertise.

Lastly, the following points regarding the Euromethod roles concepts are important:

¥	The purpose of the Euromethod role concepts is not to tell procuring organisations how to perform their jobs.

¥	The Euromethod role concepts have been defined for the purposes of Euromethod. That is, they represent a higher level of abstraction than the role definitions found within development methods and should not be equated with existing organisational roles. Rather, it should be recognised that existing organisational roles may be mapped against the Euromethod roles and responsibilities defined here.

# 3.	Customer-Supplier Relationship Framework

The Transaction Model provides the customer-supplier relationship framework in which to manage and facilitate customer-supplier interactions within IS-adaptations, both within a single country and between customers and suppliers from different countries.

The Transaction Model addresses two objectives:

1.	It sets out the scenarios of usage for Euromethod and as such is the basis for the guidance on the usage of Euromethod within these situations.

2. 	It provides the basis to describe - and thus define - the customer-supplier relationship within an IS-adaptation.

In defining the set of necessary customer-supplier transactions, the Transaction Model also provides a definition of what the contractual relationship between a customer and a supplier is and thus clarifies the distinction between the contractual and the project level of an IS-adaptation.

## 3.1.	IS-AdaptationsÊandÊTransactions

As mentioned before, the life of an information system can contain several periods of time in which it works without further enhancement, and also periods in which it is adapted to the changing needs of the organisation. Euromethod is concerned with those periods of an information system life in which an adaptation is performed by a supplier and which are regulated by a contract. Each of these IS-adaptations consists of a sequence of three processes:

¥	The tendering process,

in which the desired changes of the information system and the process for achieving them are defined and contracted to a supplier.

¥	The production process,

in which the actual production of the deliverables is performed and the desired change is achieved.

¥	The completion process,

in which the IS-adaptation is terminated technically and commercially.

At the time when an IS-adaptation contract is established, the information system and the available documents are in a certain state. This is the initial state of the IS-adaptation. As a result of the IS-adaptation process, a final state of the information system and the related IS-descriptions shall be attained. It is the Transaction Model which provides the means to describe the customer-supplier transactions needed in progressing from the initial to the final state of an IS-adaptation.

## 3.2.	Customer-SupplierÊTransactionsÊandÊDecisionÊPoints

From the customer-supplier relationship perspective, the production and completion processes of an IS-adaptation consist of a sequence of decision points in which customer-supplier transactions take place and decisions regarding the IS-adaptation are taken.

In Euromethod, a decision point is that point in time where the customer, possibly together with the supplier, is making decisions on the information system adaptation. A decision point is characterised by the decisions that are made, the roles involved in these decisions, the transactions that take place and thereby the deliverables that are exchanged. These deliverables serve as a basis for the decisions.

In Euromethod, a customer-supplier transaction is defined as the exchange of products (and services) between the customer and supplier, in order to achieve a specified purpose, e.g. making decisions on the IS-adaptation. A customer-supplier transaction is characterised by its purpose and the deliverables that are exchanged.

Transactions are always performed at decision points. The decision points in the production and completion processes are part of the delivery plan. In planning the customer-supplier transactions of the production and completion processes, a decision point is further characterised by the:

¥	Starting time or starting conditions,

i.e. the time when the deliverables are exchanged, or the point when the conditions that make the customer-supplier transaction necessary are met.

¥	Completion time or closing conditions,

i.e. the time when a decision is made binding. This means that these customer-supplier transactions involve an assessment period, in which, based on the deliverables exchanged, the appropriate decision is reached.

¥	Roles involved:

i.e. the roles needed to complete the transaction. This includes:

-	The project personnel having the authority to make the required decision in a contractually binding way,

-	The project personnel providing the necessary support to the decision making of the above.

In practice, a customer-supplier transaction may have a more complex communication structure between the customer and supplier. For example, there may be requests for explanations during the assessment. However conceptually, each transaction constitutes a logical and temporal unit delimited by its planned starting and completion time.

Several of the Euromethod transaction types are prefixed as "Approval of ...". This approval refers to the customer's satisfaction with the current status of either, the deliverables in question, or the project itself, and the wish for the production or completion process to proceed as planned. That is, the approval statement is explicitly linked to the contractual level of the customer-supplier relationship.

Furthermore, the Transaction Model permits the evaluation of, and subsequent selection from, a set of technical or business options as part of this approval process. That is, suppliers can provide deliverables which contain several suitable options for progressing the IS-adaptation. In this situation, an evaluation of each option is performed internally by the customer organisation. Where this evaluation is concluded satisfactorily, the "Approval of" decision of the customer includes both an approval of the quality of the deliverable provided, and the selection of the preferred option.

## 3.3.	TenderingÊProcess

The tendering process consists of a sequence of customer-supplier transactions, during which a description of the intended production and completion processes is produced [92/50/EEC, ISO-LCP]. The intended production process of the IS-adaptation is documented within the delivery plan.

¥	Call for Tender:

In this transaction the customer-supplier relationship is initiated by publishing a call for tender document. In this call for tender document, the first versions of the IS-adaptation requirements comprising the initial and final state of the IS-adaptation and the requirements to the production and completion processes are defined.

¥	Tender Response:

A technical proposal describing a proposed solution to the final state and the intended production and completion processes as defined within the delivery plan are sent to the customer by suppliers.

¥	Supplier Selection:

On the basis of an evaluation, the supplier with the most appropriate proposal, is informed of his selection. In the absence of a preferred supplier, other alternatives, such as a new call for tender, will be considered here.

¥	Contract Awarding:

In this transaction, the selected supplier and the customer may negotiate on possible changes to the proposal prior to agreeing on the final contents of the contract.

From the contractual point of view the tendering process ends with the completion of the contract awarding transaction; and the production process starts (see Figure 6).

At the project level, the actual production work may start either with the signing of the contract, or as a result of the customer already notifying the supplier in a letter of intent; subject to the business practice at country level.

Figure 6: Tendering process.

Figure 6 shows the simplest case in which the Euromethod tendering transactions are used. In practice, organisations may wish to perform more complex tendering processes than that shown. These more complex exercises, however, can be viewed as iterations of the Euromethod transactions. The following examples illustrate a more complex tendering scenario:

[1]	Prior to the issue of either a provisional or final call for tender document, different suppliers may be contacted with "requests for information" by the customer. Thus, this iteration consists of a call for tender (CfT/ Draft 0.1), and a tender response transaction (TR/Draft 0.1).

[2]	The next scenario may represent either the situation subsequent to [1], or be the initial iteration of the tendering process itself within an IS-adaptation. In this scenario we see that, in response to a provisional call for tender document (CfT/Draft 0.2), a shortlist of suppliers is produced based upon an evaluation of their outline technical proposals (TR/Draft 0.2) (thereby reducing the costs incurred by suppliers who, based on their proposals, are unlikely to be awarded the contract). In this instance, the process consists of a call for tender (CfT/Draft 0.2), a tender response (TR/Draft 0.2) and a supplier selection transaction (SS/Draft 0.1).

[3]	The last scenario may represent either the situation subsequent to [1] or [2], or again be the initial iteration within an IS-adaptation. Here, a detailed tendering process may be undertaken, which is restricted to the shortlisted suppliers. In this instance, the process consists of all four tendering transaction types: call for tender (CfT/Version 1.0), a tender response (TR/Version 1.0), a supplier selection transaction (SS/Version 1.0) and a contract awarding transaction (CA/Version 1.0).

The contract awarding transaction is only required for those iterations of the tendering transactions which result in the production and completion processes being performed.

## 3.4.	ProductionÊProcess

The production process is sub-divided by a set of decision points concerning the target and project domains, i.e. regarding the information system that is being adapted. These decisions are crucial for the customer since they will determine the properties of the final state of the information system. They are as important for the supplier insofar as they determine the direction of the production process, its chances of success, costs, and so on.

The sequence of the customer-supplier transactions found at these decision points during a particular production process is usually specific to that IS-adaptation. This is defined during the tendering process and documented in the delivery plan. Nevertheless, the types of customer-supplier transactions that can occur are always the same [ISO-LCP, IEEE P1074, DoD]:

¥	Approval of deliverables:

The purpose of this transaction is for specified deliverables (target domain deliverables, and also delivery plans and project plans for future IS-adaptations) to be exchanged between the supplier to the customer. The customer may approve, disapprove or ask for change to the deliverables. The customer may also choose among proposed options. This transaction type relates to the decision points of the IS-adaptation's target domain.

¥	Approval of project status and plan:

The purpose of this transaction is to evaluate management reports, assessments of project risks, feasibility and quality and proposals for risk resolution, re-planning and resource allocation. On the basis of the evaluation reports, re-planning of the project or contract change control transactions may be triggered. This transaction type relates to the decision points of the IS-adaptation's project domain.

¥	Contract change control:

This transaction can be triggered by the supplier or the customer, if they detect changes in the goals, technical or planning risks that cannot be handled in the framework of the existing contract and delivery plan. In this transaction, the customer and the supplier may either agree on, or negotiate a compromise that is documented in an addendum to the contract and, if the changes make it necessary, a revised delivery and project plan.

Figure 7: The production process.

For any given IS-adaptation, the sequence of transactions that are to be performed within that IS-production, are defined within the delivery plan (see Figure 7). The production process ends when the final deliverables (as identified within the delivery plan) are made available to the customer for the first time. This delivery initiates the approval of final deliverables transaction, which is the first customer-supplier transaction found in the completion process.

In practice, the approval of deliverables, and approval of project status and plan transactions will be executed with a much greater frequency within an IS-adaptation than the contract change control transaction.

## 3.5.	CompletionÊProcess

The completion process aims at getting a formal closure of all the deliverables and remaining concerns of the project, so that the contractual arrangement between a customer and a supplier can be phased out in an effective manner [ISO-LCP]. As mentioned above, it is initiated with the receipt of the final deliverables by the customer from the supplier (see Figure 8).

The completion process is characterised by two transaction types:

¥	Approval of the final deliverables:

The last remaining deliverables (target domain deliverables, and delivery plans and project plans for future IS-adaptations) are exchanged between the supplier and the customer. The customer may approve, disapprove or request changes to the deliverables.

With the approval of the final deliverables the customer indicates satisfaction that the production process undertaken by the supplier has led to the desired final state of the information system. If the customer demands some rework to remove deficiencies identified in the evaluation exercise, a new approval of final deliverables transaction must be planned.

¥	Contract completion:

This is an administrative transaction which controls whether all the transactions regarding the IS-adaptation have been satisfactorily completed. It consists of the activities needed in order to phase out both the technical and commercial aspects of the IS-adaptation in a controlled way.

Figure 8: The Completion process.

The conclusion of the contract completion represents the end of the IS-adaptation and thus the end of the temporary customer-supplier contractual relationship with respect to the IS-adaptation contract under consideration. Contract completion can run in parallel with one or more transactions. For example, a customer may initiate further contractual negotiations (or perhaps issue a new call for tender) to address the post-contractual relationship i.e. the undertaking of a new IS-adaptation or finalising the maintenance service.

## 3.6.	DeliveryÊPlan

A delivery plan is a product which defines the contractual customer-supplier relationship during the production and completion processes. A Euromethod delivery plan should contain the following elements:

¥	A description of the problem situation, including descriptions of the initial and final states.

¥	A description of the IS-adaptation strategy.

¥	The sequence and descriptions of the required decision points and the related deliverables.

The initial state of an IS-adaptation is the state of the information system and the available knowledge on it, at the beginning of the production process, i.e.:

¥	The initial state information system, i.e. the operational items contained in the operational information system.

¥	The operational items of a future information system that are available to the IS-production process (they have been constructed but are not yet installed and part of the operational information system).

¥	The IS-adaptation requirements, i.e.:

-	The IS-descriptions that are available to the production process; this can include both IS-descriptions of the initial state information system and IS-descriptions of a future information system;

-	The delivery plan.

-	Possibly project plans (development plan, quality assurance plan, configuration management plan).

The final state of an IS-adaptation is the state of the information system and the knowledge on it, at the end of the IS-adaptation, i.e.:

¥	The final state information system.

¥	The operational items of a future information system that are produced as a result of the IS-adaptation (they are constructed but not yet installed as part of the operational information system).

¥	The IS-descriptions that are produced as a result of the IS-adaptation and that the customer wants to continue to use after the termination of the IS-adaptation; this can include both IS-descriptions of the final state information system and IS-descriptions of a future information system.

¥	The plans for future IS-adaptations that are produced as a result of the IS-adaptation; this can include both delivery plans and project plans.

A description of the IS-adaptation strategy contains:

¥	The reasoning that leads to the sequence of decision points defined in the delivery plan. Ideally this summarises the conclusion from applying the Strategy Model as described in the Delivery Planning Guide.

The decision points throughout the production and completion processes are characterised by:

¥	The decisions that are made, the roles involved in these decisions, the customer-supplier transactions that take place and thereby the deliverables that are exchanged. These deliverables serve as a basis for the decisions.

The descriptions of decision points in the production and completion processes are part of the delivery plan. More than one transaction can be performed at a single decision point. For example, the approval of deliverables and approval of project status and plan transactions can be, and often are, performed together at the same decision point in an IS-adaptation.

Decision points are introduced into production and completion processes for the following purposes:

¥	To remove uncertainties.

That is, to select one of several options, or to approve the delivered products (either fixing their content for later use, or by confirming the supplier's current understanding).

¥	To manage the direction and quality of the production and completion processes.

That is, to assess and decide upon the adequacy of the content of the target domain deliverables and the plans for future IS-adaptations, and to assess and decide upon the acceptability of their quality. This may also involve management procedures like putting accepted target domain deliverables under configuration management.

This is achieved by the approvals performed in the approval of deliverables and approval of final deliverables transaction types:

-	In the case where the customer registers his approval of the deliverables, the decision provides both a stable basis for the ongoing production or completion process and consolidates the customer's and supplier's expectations and obligations.

-	In the case where the customer rejects the deliverables, the decision may introduce additional transactions into the delivery plan, and potentially postpone succeeding customer-supplier transactions. Since the delivery plan is treated as part of the technical annex of the contract, the customer or the supplier can then insist on the revised delivery plan becoming the subject of a contract change control transaction.

¥	To assess and manage deviations from the planning of the production process.

This is achieved by the approval of deliverables related to the project domain, performed in the approval of project status and plan transactions, which may result in alterations to the delivery plan and the project domain deliverables concerned with planning issues. Again, since the delivery plan is treated as part of the technical annex of the contract, the customer or the supplier can then insist on the revised delivery plan becoming the subject of a contract change control transaction.

The description of a customer-supplier transaction scheduled in the delivery plan thus contains the following elements:

¥	The transaction purpose consisting of the kind of target or project domain decision that has to be taken,

¥	The products (and services) which are to be exchanged between the customer and supplier, in order to achieve a specified purpose, e.g. making decisions on the IS-adaptation.

It should be noted that in defining and scheduling decision points containing the customer-supplier transactions for the production process, the delivery plan places constraints on the internal processes, and hence the behaviour of both the customer and the supplier.

# 4.	Customer-SupplierÊTransactions

This chapter describes all the customer-supplier transaction types defined for the three processes found in an IS-adaptation (see Figure 9).

Figure 9: The types of customer-supplier transactions in IS-adaptations.

## 4.1.	CallÊforÊTender

A transaction of this type is initiated after the decision is taken by the customer organisation to undertake an IS-adaptation.In the circumstance, where the customer resides within the European Union, and is subject to European public procurement directives, an advertisement is placed in the European Journal. Supplier organisations who are interested in the proposed IS-adaptation, will request further information. Copies of the technical specification, containing the IS-adaptation requirements with respect to this call for tender document will be made available to:

¥	Either, all interested supplier organisations.

¥	Or, a shortlist of supplier organisations who conform to a pre-defined set of criteria (e.g. EN29000 certification).

For organisations not covered by the European directives, an advertisement regarding the Call for Tender may be published in the organisation's preferred outlets, such as professional journals or newspapers; or be sent to companies on the customer's supplier shortlist.

The IS-adaptation requirements within a call for tender document consist of the first versions of all or some part of the following:

-	IS-descriptions that are available to the IS-production process; this can include both IS-descriptions of the initial state information system and IS-descriptions of a future information system.

-	A delivery plan.

-	Project plans (development plan, quality assurance plan, configuration management plan).

The IS-adaptation requirements will be supplemented by additional information system or procurement requirements, such as the method or programming language standards to be followed, as demanded under the Standards Decision [87/95/EEC]; as well as documentation describing the tender evaluation criteria.

CustomerÊGoal:

To initiate a process resulting in an adaptation of the target domain information system by an external supplier.

KeyÊRoleÊResponsibilities:

The customer:

¥	Decides on the tendering strategy to follow and how to implement the appropriate rules e.g. the Services Directive [92/50/EEC].

¥	Approves the content of the call for tender document, ensuring that the IS-adaptation requirements in the call for tender document are of the correct detail and quality.

¥	Obtains the go-ahead for the call for tender.

¥	Defines the evaluation model to be used within the tender evaluation.

¥	Places the advertisement in the European Journal (where appropriate) or in professional business journals and newspapers.

¥	Provides copies of the IS-adaptation requirements to the interested supplier organisations.

The supplier:

¥	Reviews the European Journal, professional business journals and newspapers for appropriate calls for tender.

¥	Performs marketing activities in order to be included in appropriate supplier short lists.

## 4.2.	TenderÊResponse

In a transaction of this type a supplier's technical proposal is delivered to the customer organisation. The supplier organisation's technical proposal is based on the following key elements addressed by Euromethod:

¥	Understanding the customerÕs situation.

¥	Producing products proposing solutions.

These products constitute, together with those provided by the customer in the call for tender document, the initial state products available for the production process of the IS-adaptation.

¥	Producing proposals for changes to the final state profiles of the IS-adaptation (if and where they are considered necessary).

¥	Producing proposals for the sequence of decision points in the production and completion processes.

¥	Producing proposals for the products that should be delivered at each of the decision points.

These are documented within the technical proposal by the supplier. The proposed decision points define the customer-supplier interactions required by the proposed solution. In the technical proposal, the supplier should be able to demonstrate:

¥	A good understanding of the customerÕs situation.

¥	The ability to successfully complete the IS-adaptation.

That is, the tender response requires the supplier to produce a set of initial products which serve both to highlight the customer's business need, and propose a technical solution to the IS-adaptation requirements.

The production of the technical proposal is normally performed by people having bid management and information system expertise. Once the technical proposal is complete it is submitted to the customer organisation by the supplier.

CustomerÊGoal:

To receive several appropriate, competitive, technical proposals in order to subsequently select the best, most cost effective solution.

SupplierÊGoal:

To propose a feasible technical proposal addressing the customer's IS-adaptation requirements as stated in the call for tender document, in order to meet the customer organisation's strategic goals.

KeyÊRoleÊResponsibilities:

The customer:

¥	Receives and acknowledges the technical proposals.

The supplier:

¥	Decides whether the supplier organisation should participate in the tendering process by submitting a technical proposal to the customer organisation.

¥	Provides the complete technical proposal, including the proposed delivery plan.

¥	Provides terms and conditions or comments to the customer's proposed terms and conditions.

## 4.3.	SupplierÊSelection

The call for tender document issued by the customer organisation will always provide a closing date for the receipt of technical proposals. This date corresponds with the initiation of the tender evaluation. Prior to undertaking the supplier selection transaction, the customer must perform some activities. The transaction itself follows some internal evaluation which results in the decision of which technical proposal is selected. The transaction is concluded by awarding the IS-adaptation to one or more of the participating supplier organisations and terminates the relationship with those supplier organisations that have not been chosen on this occasion.

The evaluation criteria will have been outlined, in addition to the IS-adaptation requirements, within the call for tender document. Within the supplier selection transaction, they may be re-assessed by the customer for their completeness and rigour for establishing which technical proposal is the most appropriate to the needs of the customer organisation and the problem situation. The complete set of evaluation criteria used will assess supplier organisations both organisationally and for the project. The following aspects of the evaluation are generally undertaken:

¥	The broad suitability of an organisation is commonly controlled within the call for tender ("Tenders are invited from organisations meeting the following characteristics, EN 29000-registered, capitalisation of 1 MECU, etc."), or may be covered by the presence of a supplier on a customer organisation's qualified supplier list. However, the capability of the organisational processes will be assessed by the customer, by means of criteria elicited from within publicly available evaluation approaches.

¥	At the project level, the supplier will be assessed by the customer's tender evaluation team using criteria based upon the concepts and guidelines provided by Euromethod.

As part of the detailed tender evaluation process, the customer organisation may identify a list of issues regarding the production process of the selected or shortlisted suppliers.

CustomerÊGoal:

To select the best, most cost-effective technical solution proposal.

KeyÊRoleÊResponsibilities:

The customer:

¥	Performs the tender evaluations.

¥	Asks for additional clarification and explanation of aspects of a supplier's technical proposal.

¥	Decides which suppliers are to be shortlisted or selected based upon the results of the tender evaluations.

¥	Controls the process of informing potential suppliers that they have been short-listed or selected.

¥	Controls the process of informing rejected suppliers why they have not been short-listed or selected and distributes the tender evaluation results as requested.

The supplier:

¥	Responds to any questions by the customer organisation regarding the supplier's technical proposal.

## 4.4.	ContractÊAwarding

A customer-supplier transaction of this type involves the customer and the selected supplier negotiating on what the final form of the technical annex shall be and is concluded either with the formal signing of the contract or with the withdrawal by either party from the contractual process. The negotiations are characterised by the consideration of the known technical, financial, management and quality issues, and is performed within the legal contract framework.

In some IS-adaptation situations, draft contracts will have been prepared and discussed with shortlisted suppliers at an earlier stage within the tendering process, for example prior to the supplier selection transaction. However, contract awarding represents the only time that a complete technical annex, containing the final version of the delivery plan will be ready.

The transaction is characterised by a series of negotiations undertaken by the customer and supplier which are based upon the need for clarification within, or on requests for change to, the technical proposal.

The refined technical proposal can be augmented in all or some of the following ways:

¥	By incorporating the results of the contractual negotiations regarding the technical annex.

¥	By undertaking detailed delivery and project planning activities such as:

-	Identifying deliverables and detailed bridging to supplier's preferred IS-development method.

-	Any relevant additional mappings to further methods or techniques.

-	Defining the interface between the preferred method and the additional mappings to further methods or techniques.

-	IS-project resourcing.

¥	By including details of any corrective actions required within the process to be used in the IS-adaptation by the supplier.

That is, during the detailed tender evaluation process, the customer organisation identified a list of issues regarding the proposed processes of the selected or shortlisted suppliers. Each of these issues may now be considered for inclusion within the technical annex.

By the end of contract awarding the version of the delivery plan proposed in the selected technical proposal has become the contract version of the delivery plan, and which is included within the technical annex of the contract. On reaching this point, the transaction is formally concluded with the signing of the contract by the contractual parties.

CustomerÊGoal:

To award a contract consistent with the current IS-adaptation requirements which is likely to secure the best value for money from the project budget.

SupplierÊGoal:

To obtain a contract in line with the negotiated customer IS-adaptation requirements while ensuring that the commercial benefits identified within the original IS-adaptation solution remain.

KeyÊRoleÊResponsibilities:

The customer:

¥	Identifies the strengths and weaknesses of the selected technical proposal.

¥	Introduces the customer organisation's contractual concerns into the negotiation procedure.

¥	Obtains the best value for money possible from the project budget.

¥	Decides if the customer organisation's interests are still met by the selected supplier and proposed contract.

¥	Provides an impact analysis with respect to a proposed change and produces the technical proposal change request.

¥	Reviews the amended delivery and project plans.

The supplier:

¥	Introduces the supplier organisation's contractual concerns into the negotiation procedure.

¥	Obtains the best profit margin possible from the project.

¥	Decides if the supplier organisation's interests are still met by the proposed contract.

¥	Undertakes an impact analysis with respect to a proposed change and produces the amended delivery and project plans.

## 4.5.	ApprovalÊofÊDeliverables

A transaction of this type begins with the supplier delivering a set of deliverables that is required by the technical annex of the contract, and the delivery plan in particular. It consists of the customer either approving the deliverables or invoking a different action.

Between the delivery and his response, the customer undertakes an evaluation of the deliverables based on the project context defined within the technical annex of the contract, and his own quality management system. The deliverables are evaluated for technical content, quality, and consistency as defined within the IS-adaptation's deliverable profile for this decision point. This involves a consideration of deliverables approved earlier in the project, as well as the compatibility of these deliverables with the known customer needs and their practical usability in the customer organisation. Furthermore, the likelihood of achieving the successful delivery of the final state system based on these deliverables is assessed. Where the end result may be cast in some doubt by these deliverables, a redefinition of further deliveries may be triggered.

Based on the result of the evaluation, the customer can take one of the following actions:

1.	Approve the deliverables, since they satisfy all of his expectations.

2.	Accept the deliverables, without demanding rework (in the circumstances where most of the expectations are satisfied, and the risk associated with accepting the deliverables is judged to be small).

3.	Demand some rework of the deliverables, in order to remove deficiencies discovered during the evaluation.

4.	Reject the deliverables if they are completely insufficient.

5.	Lastly, trigger a change control of the contract, if it is recognised:

-	that the IS-adaptation requirements stated, e.g. the delivery plan, no longer reflect the customer's actual needs.

-	the IS-adaptation is no longer feasible due to the lack of progress made to date.

After accepting the deliverables, the content of each deliverable is considered as being binding in that state for the future production process. If a deliverable is an operational item it may be either:

¥	Tested, but not installed in the target domain immediately.

¥	Or, installed in the target domain, in which case it is being used operationally.

In those circumstances where the deliverables are not satisfactory, and must therefore be reworked, the reworked deliverables must be in line with the contractual and reworking objectives and have been successfully evaluated prior to being approved. Accordingly, the customer's objectives for reworked deliverables are closely linked with those of the original transaction which triggered the rework. The evaluation and acceptance of the rework is governed by:

¥	The definition of the rework.

¥	The contractual quality and acceptance criteria stated for the deliverables under consideration.

The requirement for rework may lead to additional transactions and decision points being defined. Accordingly, the customer or the supplier may insist that this results in an updated delivery plan being produced within a contract change control transaction.

A key element of any production process consists of informal liaison meetings between the customer and supplier organisations. These liaisons are not part of the contractual arrangement, and are thus not considered as part of the customer-supplier Transaction Model. However, it should be noted that the approval of deliverables transaction is often preceded by for example:

¥	Joint application development workshops.

¥	Joint design workshops.

¥	The presentation of a "straw man" delivery.

These are undertaken in order to obtain agreement with the customer (including remarks and requests) and hence some form of informal approval of the deliverables by the customer prior to delivery. In the long run, the purpose is to ensure the acceptance of the formal delivery and obtain customer satisfaction with the deliverables.

The main thrust of this transaction addresses the delivery of deliverables from the supplier to the customer. However, in some IS-adaptations, it is conceivable that the customer may be responsible for making a delivery to the supplier. In this instance, the Transaction Model treats the customer as a supplier and vice versa.

CustomerÊGoal:

To control the deliverables, which at this point, are consistent with the objective that the final deliverables will fit into the organisation and address the objectives identified within the IS-adaptation requirements within the contract.

SupplierÊGoal:

To deliver the deliverables that meet the customer expectations, to receive approval for those deliverables and hence permission to proceed with the IS-adaptation.

KeyÊRoleÊResponsibilities:

The customer:

¥	Receives the deliverables.

¥	Performs the deliverable assessment procedure.

¥	Approves, conditionally approves or rejects the deliverables.

The supplier:

¥	Decides whether the deliverables meet the IS-adaptation requirements within the contract and are ready for delivery to the customer organisation.

¥	Delivers the deliverables to the customer.

## 4.6.	ApprovalÊofÊProjectÊStatusÊandÊPlan

A transaction of this type is performed by the customer and supplier together but is approved by the customer alone. In this transaction, project domain deliverables covering topics such as management reporting, assessments of project risks, feasibility and quality and proposals for risk resolution, re-planning and resource allocation are evaluated. Based on the evaluation of the reports, contract change control may be triggered if necessary.

A further characteristic of this transaction is that, on the basis of the project reports, the customer can identify a number of corrective actions which could be performed by the supplier organisation in order to improve its processes. In this way, the approval of the project status and plan transaction may lead to the instigation of a process improvement programme to run in parallel with the IS-adaptation.

CustomerÊGoal:

To ensure the IS-adaptation feasibility by uncovering risks and defining preventative actions to prevent them i.e. to protect the project investment.

SupplierÊGoal:

To ensure the IS-adaptation feasibility by uncovering risks and defining preventative actions to prevent them i.e. to protect the benefit to be gained from the project.

KeyÊRoleÊResponsibilities:

The customer:

¥	Receives the deliverables regarding a project status and plan review.

¥	Decides on the scale of problems and risks and recommends options for resolution.

¥	Represents the customer organisation at the project status and plan review.

¥	Determines whether a contract change control transaction is necessary from the customer point of view.

The supplier:

¥	Delivers the necessary project status and plan deliverables to the customer.

¥	Represents the supplier organisation at the project status and plan review.

¥	Decides on appropriate solutions to problems and risks.

¥	Determines whether a contract change control transaction is necessary from the supplier point of view.

¥	Triggers any contract change control activities within the supplier organisation.

¥	Determines the technical implications to the supplier organisation within any triggered contract change control activities.

## 4.7.	ContractÊChangeÊControl

This transaction addresses the situation in which changes to the technical annex of the contract are identified and processed. The transaction is concluded when the new version of the technical annex containing the changes is approved. Changes to the body of the contract, which contains the legal and financial provisions of the contract are not addressed by this transaction.

Contract change control may be either planned within the delivery plan, or be triggered during the production or completion processes. It may be triggered by either the customer, or by the supplier when they detect technical or planning risks that are not handled clearly within the technical annex of the existing contract. Contract change control often follows an assessment of either some deliverables, or of the project itself, in which changes to the technical annex are identified which reduce a threat to the project's outcome.

As mentioned above, consists of the agreement of both contractual parties to a change to the technical annex. The nature of these changes is such that, the changes act as an amendment or clarification of a previously stated requirement. In the majority of cases the changes made as part of the contract change control do not have a substantial impact upon the content and intention of the contract. It simply records the advances in the understanding of the contractual goals and requirements.

In some circumstances, major technical changes may be involved which require radical changes to the plans and the contract itself. In this circumstance, the contract change control transaction is used to manage the technical changes to the technical annex. However, all re-negotiation of contract issues will be handled outside of the Euromethod concepts, using normal business practices.

For example, a conflict may have to be resolved in which one side claims that the technical annex does not reflect the real requirements to the IS-adaptation and the other defends the contractual position. As part of contract change control the customer and the supplier can negotiate a compromise that is documented in a substantially altered version of the technical annex, which results in the need to change the contractual arrangement. In this way, the contract change control transaction results in a re-negotiation of the contract which will be handled outside the scope of Euromethod.

Customer Goal:

Where customer requirements to the IS-adaptation have developed from those defined within the contract, they need to be documented within the project process as part of a controlled change process to ensure an up to date technical annex in the contract.

Supplier Goal:

The same as the customer goal but in line with the supplier's own technical capabilities and commercial objectives.

Key Role Responsibilities:

The customer:

¥	Determines the technical implications to the customer organisation of any proposed changes to the technical annex.

¥	Introduces the customer organisation's contractual concerns into the contract change control.

¥	Detects whether the IS-adaptation requirements defined in the technical annex are not being met by the supplier, and whether this corresponds to a breach of contract to be followed up by senior management.

¥	Obtains the best value for money possible for the project spend without bankrupting the supplier.

The supplier:

¥	Identifies the technical implications caused by the gap between the customer's stated and actual IS-adaptation requirements which must be resolved by contract change control.

¥	Introduces the supplier organisation's contractual concerns into the contract change control.

¥	Obtains the best profit margin possible from the project whilst meeting the customer expectations.

## 4.8.	ApprovalÊofÊFinalÊDeliverables

In the transaction, the customer receives and approves the remaining deliverables, which should constitute the final state required by the customer. At this time, all the deliverables associated with the IS-adaptation should be in their final development and quality states.

A transaction of this type begins with the supplier delivering the (at this time, proposed) last set of deliverables as demanded within the contract and the delivery plan. These might be a set of IS-descriptions and plans which comprise a change analysis, or a detailed design; or indeed an operational system. The transaction consists of the customer approving the deliverables or taking a different action.

Between the delivery and his reaction, the customer performs the IS-description evaluation or the acceptance testing of the final deliverables based on the project context which is defined by the technical annex of the contract and the customer organisation's own quality management system.

In the case of the delivery of an operational system, either installed or only constructed and tested, the transaction contains checks regarding whether the operational system has the necessary quality for further use by the customer.

Based on the resulting evaluation report the customer can take different actions:

1.	Accept the final deliverables, in the case where they satisfy all the expectations (i.e. approval).

2.	Accept the final deliverables, without demanding rework (in the circumstances where most of the expectations are satisfied, and the risk associated with accepting the deliverables in their current state is judged to be small).

3.	Demand some rework of the final deliverables, in order to remove deficiencies discovered during the evaluation (i.e. conditional approval). This implies that a new approval of final deliverables transaction must be planned.

4.	Reject the final deliverables if they are completely insufficient (i.e. rejection).

CustomerÊGoal:

To obtain the final deliverables that represent an acceptable response to both the contractual IS-adaptation requirements and the expectations in the organisation; in order that the on-going process of effecting an improvement in the organisation's business practices can be achieved.

SupplierÊGoal:

To provide the final deliverables in line with the contractual IS-adaptation requirements and satisfying the customer expectations as close as possible; in order to permit the successful termination of the contract.

KeyÊRoleÊResponsibilities:

The customer:

¥	Receives the final deliverables.

¥	Undertakes an assessment of the final deliverables via the deliverable assessment procedure.

¥	Approves, conditionally approves or rejects the final deliverables.

The supplier:

¥	Decides whether the final deliverables meet the IS-adaptation requirements within the contract and are ready for delivery to the customer organisation.

¥	Delivers the final deliverables to the customer.

## 4.9.	ContractÊCompletion

The transaction is essentially an administrative transaction which controls whether all the transactions regarding the IS-adaptation have been satisfactorily completed.

The contract completion transaction type is performed co-operatively by the customer and supplier. It consists of those activities needed in order to phase out all the technical, management and financial aspects of the IS-adaptation in a controlled way. Contract completion is always the final transaction to be undertaken within an IS-adaptation.

The contract completion transaction ensures that:

¥	All outstanding aspects associated with an IS-adaptation have been concluded. This can include both:

-	Technical aspects:

That is, in certain circumstances some technical details may continue to be outstanding, or were omitted by the supplier in deliverables which have been previously approved. These can be completed here.

-	Commercial aspects:

For example, ensuring that all sub-contracts have been honoured, all invoices completed, and all cost statements submitted to the appropriate organisations.

¥	It is identified how the project deliverables may be re-usable in future IS-adaptations.

In the situation where the contract completion occurs after the acceptance of the final deliverables, it is performed in the scheduled manner. In this instance, the contract completion represents the normal termination sequence for an IS-adaptation.

In the situation where the contract completion transaction is invoked as part of the cancellation of the IS-adaptation, this may be viewed as an abnormal termination.

In the case of abnormal termination of an IS-adaptation, the execution of the contract completion transaction may occur in parallel with that of contract change control transaction.

The conclusion of the contract completion transaction represents the end of the customer-supplier relationship with regard to the IS-adaptation contract. Commonly, this transaction may run in parallel with one or more tendering process transactions. For example, a customer may initiate further contractual negotiations (or perhaps issue a new call for tender) to address the post-contractual relationship i.e. the undertaking of a new IS-adaptation or finalising the warranty service.

CustomerÊGoal:

To ensure that all outstanding technical and commercial transactions regarding this IS-adaptation contract have been satisfactorily concluded.

SupplierÊGoal:

To ensure that all outstanding technical and commercial transactions regarding this IS-adaptation contract have been satisfactorily concluded.

KeyÊRoleÊResponsibilities:

The customer:

¥	Closes the contractual relationship with the supplier, keeping in mind the business implications of residual technical and commercial tasks and record all the important IS-adaptation experiences.

The supplier:

¥	Ensures the timely closure of the contractual arrangement, while keeping in mind the possibility of further business opportunities.

# References

[EM-1-EO]	Euromethod Overview, 1994

[EM-2.1-CG]	Euromethod Customer Guide, 1994

[EM-2.2-SG]	Euromethod Supplier Guide, 1994

[EM-2.3-DPG]	Euromethod Delivery Planning Guide, 1994

[EM-2.4-MBG]	Euromethod Method Bridging Guide, 1994

[EM-2.5-CS]	Euromethod Case Study, 1994

[EM-3.2-DM]	Euromethod Concepts Manual 2 - Deliverable Model, 1994

[EM-3.3-SM]	Euromethod Concepts Manual 3 - Strategy Model, 1994

[EM-4-ED]	Euromethod Dictionary, 1994

---------

[87/95/EEC]	The EEC Standards Decision.

[92/50/EEC]	The EEC Service Directive: Council Directive 92/50/EEC of 18 June 1992 relating to the co-ordination of procedures for the award of public service contracts.

[IEEE-729]	IEEE. Standard Glossary of Software Engineering Technology. 09.08.83. ANSI/IEEE Std 729.

[IEEE-P1074]	IEEE. Standard for Software Life Cycle Processes: IEEE Technical Committee for Software Engineering P1074/D5, 1st December 1989.

[ISO-2382-01]	ISO/2382/1. Data Processing - Vocabulary. Part 01: 
Fundamental Terms. Second edition. 1984-10-01.

[ISO-2382-07]	ISO/IEC/2382-7. Information Technology - Vocabulary. Part 07: Computer Programming. Second edition. 1989-10-15.

[ISO-2382-20]	ISO/IEC/2382-20. Information Technology - Vocabulary. Part 20: 
System Development. First edition. 1990-03-01.

[ISO-8402]	ISO 8402 Quality - Vocabulary: 1986.

[ISO-LCP] 	Information Technology Software Life Cycle Processes; 
Second Committee Draft 12207.2, ISO/IEC(JTC1)-SC7, 
21 June 1993.

[SEI-CMM] 	The Capability Maturity Model for Software.
Software Engineering Institute, Carnegie Mellon University, Pennsylvania. August 1991, CMU/SEI-91-TR-24.

# Index

CM-expertise 14

completion process 23

configuration management 10

contract authority 11

customer 11

customer-supplier relationship 6; 16

customer-supplier transaction 17; 28

approval of deliverables 35

approval of final deliverables 41

approval of project status and plan 38

call for tender 28

contract change control 40

contract completion 43

supplier selection 32

tender response 30

decision point 17; 25

deliverable 25

delivery plan 24

final state 25

final state information system 25

initial state 24

initial state information system 24

IS-adaptation 5

IS-adaptation requirements 28

IS-development 9

IS-expertise 14

IS-production 9

IS-project 7

key role 11

operational expertise 12

organisational authority 12

production process 21

project authority 11

project control 9

project domain 7

project management 9

project planning 9

QA-expertise 14

quality assurance 9

relationship at a contractual level 6

role 11

role concepts 11

supplier 11

technical annex 34

technical proposal 30

technical specification 28

tendering process 18

Transaction Model 16

work area 9

DocumentÊhistoryÊofÊEuromethodÊTransactionÊModel

| Version | Status | Author | Comment | Distribution |
| --- | --- | --- | --- | --- |
|  | Being Developed | MG | Start updating WP2 version |  |
| 250194 | Ready for L2-review | MG | This review version takes all the EMPMB recommendations and the national expert concerns which were appropriate into account. In addition, clearer definitions regarding the delivery plan and the tendering process transactions have been taken from the EMPMB presentation and the EU-Rent Case Study. Lastly, the document has been re-read with the purpose of smoothing the English. | Project team |
| 240294 | Under-L2-review | MG | All the L2 review comments have been incorporated in the document. | NA |
| 280294 | Under L3-review | NA | NA remarks incorporated | ¥ Review Group ¥ Project Team |
| 230394 | Under L3-review | NA, MG | Revised on the basis of remarks from the review group and the project team. New guide layout is used. Contract re-negotiation is changed to CCC and text altered to reflect the idea of CCC better (MG). Index is added. | ¥ AG ¥ Project Team |
| 050494 | Delivered | NA | Revised on the basis of remarks from MG. Layout standards implemented. | EC |
| 160694 | Under EMPMB review | MG | Revised on the basis of remarks from the EMPMB. Changes are marked | ¥ Review group ¥ GW |
| Version 0, June 1994 | Delivered | NA | Revised on the basis of remarks from the review group and GW. Marks are removed. | EC |

A project solely resulting in improved knowledge and documentation about the existing system or the design of a future system is also considered as an IS-adaptation.

Since the context of an Euromethod project is an information system project, IS-project management is abbreviated to project management for readability, in the same way that IS-project is abbreviated elsewhere to project.

The work area view is considered as orthogonal to the systemic view (the breakdown of the IS-project into IS-production and project management). This requires a special interpretation of the life cycle processes in [ISO-LCP], e.g. the development process in [ISO-LCP] is both viewed as part of IS-production and as a work area.

For an IS-adaptation that shall produce a specification of a future information system, a specification of the current information system can be part of the initial state. For an IS-adaptation that shall construct and install a new version of an information system, a specification of this future information system can be part of the initial state.

A description of a desired final state should contain the identification of the operational items that shall be replaced and the types of operational items that shall be added to or replace the current ones.

The definition of the final state of an IS-adaptation shows that the Euromethod concepts are designed to support Òdevelopment projectsÓ, Òmaintenance projectsÓ and "design projects". These can be characterised as follows:

-	ÒDevelopment projectsÓ are mainly concerned with adding new operational items 	rather than replacing existing ones.

-	ÒMaintenance projectsÓ are mainly concerned with the replacement of operational 	items rather than adding new ones.

-	"Design projects" are not changing the operational items installed in the 	information system.

In the EEC Service Directive [92/50/EEC], a technical specification is defined as "the totality of the technical prescriptions contained in particular in the tender documents, defining the characteristics required of a work, material, product or supply which permits that work, material, product or supply to be described in a manner such that it fulfils the use for which it is intended by the contracting authority. These technical prescriptions shall include levels of quality, performance, safety or dimensions..."

In the tender response provided by the supplier information such as financial data, work force profiles, experience and expertise levels may be included. This is not supported by the Technical Proposal defined by Euromethod.

In some contractual situations, no negotiation is allowed. In those circumstances where the tender response can not be adopted as the basis of a contract, the only option available is to redo the entire tendering process.

For example:

¡	Obtaining any plans for future IS-adaptations from the supplier for consideration 	by the customer.

¡	Obtaining bug-fixes or patches needed to ensure the smooth running of the 	operational system

¡	Ensuring all the quality review documentation has been completed,

¡	Ensuring the user documentation has been finalised and delivered to the customer.