Euromethod
Delivery Planning Guide

EM-2.3-DPG

__________________________________

Abstract

This is a guide to make a delivery plan for an IS-adaptation using Euromethod. It contains guidelines for assessment of a problem situation, for definition of an IS-adaptation strategy, for definition of decision points and for production and assessment of a delivery plan.

__________________________________

© Euromethod Project 1994

This document,

Euromethod Delivery Planning Guide,

is a document of the Euromethod Version 0.

In the layered document structure of Euromethod it constitutes a part of the Guide Level. It is referenced by the other Guides and the Overview; and makes use of the definitions in the other Guides, the Concepts Manuals and the Dictionary.

ContentsÊofÊtheÊDeliveryÊPlanningÊGuide

1.	Introduction	5

1.1.	Objectives	5

1.2.	TargetÊAudience	5

1.3.	Scope	6

1.4.	StyleÊConsiderations	6

1.5.	EntryÊPoints	9

2.	TheÊDeliveryÊPlan	11

2.1.	Purpose	11

2.2.	Contents	12

2.2.1.	ProblemÊsituation	14

2.2.2.	IS-adaptationÊstrategy	15

2.2.3.	DecisionÊpoints	16

2.3.	Versions	17

3.	DeliveryÊPlanning	19

3.1.	Context	19

3.2.	ActivitiesÊandÊresults	21

4.	HowÊtoÊAssessÊaÊProblemÊSituation	23

4.1.	InitialÊandÊfinalÊstates	25

4.2.	SituationalÊfactors	28

4.3.	Risks	32

5.	HowÊtoÊDefineÊaÊStrategy	37

5.1.	ApproachÊtoÊchangeÊsituationalÊfactors	39

5.2.	DevelopmentÊapproach	40

5.2.1.	InstallationÊapproach	40

5.2.2.	ConstructionÊapproach	46

5.2.3.	DescriptionÊapproach	49

5.3.	ProjectÊcontrolÊapproach	53

5.4.	RiskÊmanagement	58

5.4.1.	Complexity	59

5.4.2.	Uncertainty	61

6.	HowÊtoÊDefineÊDecisionÊPoints	63

6.1.	SequenceÊofÊdecisionÊpoints	64

6.1.1.	DescriptionÊapproach	65

6.1.2.	ConstructionÊapproach	73

6.1.3.	ConstructionÊandÊinstallationÊapproach	74

6.1.4.	ProjectÊcontrolÊapproach	76

6.1.5.	CombinedÊapproach	76

6.2.	DeliverableÊprofilesÊrelatedÊtoÊdecisions	77

6.2.1.	InvestmentÊdecisions	78

6.2.2.	DesignÊdecisions	80

6.2.3.	SystemÊacceptanceÊdecisions	82

6.3.	ApplyÊIS-developmentÊmethods	82

6.3.1.	ApplyÊmethodÊbridges	83

6.3.2.	ApplyÊmethodÊprocessÊmodels	84

7.	HowÊtoÊAssessÊaÊDeliveryÊPlan	87

7.1.	QualityÊofÊproblemÊsituationÊdescription	89

7.2.	SuitabilityÊofÊstrategy	89

7.3.	SuitabilityÊofÊdecisionÊpoints	90

Annexes	91

A.	DeliveryÊPlanÊExample: -ÊOneÊshotÊapproach	91

B.	DeliveryÊPlanÊExample: -ÊIncrementalÊapproach	94

C.	DeliveryÊPlanÊExample: -ÊEvolutionaryÊapproach	97

References	100

Index	101

# 1.	Introduction

## 1.1.	Objectives

The objective of the Delivery Planning Guide is to provide guidance on:

¥	How to produce a delivery plan; and

¥	How to assess a delivery plan,

for an IS-adaptation using Euromethod.

It shall therefore facilitate the practical use of the Strategy Model and support the guidance given in the Customer and Supplier Guides.

## 1.2.	TargetÊAudience

The target audience of this guide is:

¥	Those persons in charge of producing a strategy and an overall delivery plan for a particular IS-adaptation.

These are the contract and project authorities that are in charge of managing an IS-adaptation.

¥	Those persons in charge of defining the method deliverables of a specific IS-development method for a particular IS-adaptation.

These are the project authorities and the project actors, providing operational expertise, that are in charge of managing and performing activities which involve the identification and description of the method deliverables to be included in the IS-adaptationÕs delivery plan.

¥	Those persons in charge of assessing a delivery plan for a particular IS-adaptation.

These are the project authorities and the project actors, providing operational expertise, that are involved in the assessment of a delivery plan, e.g. as part of a tender evaluation procedure.

## 1.3.	Scope

The guide covers the production and assessment of a delivery plan. It does not cover the detailed project planning performed within the customer and supplier organisations. In an IS-adaptation, a delivery plan should be complemented by project plans, for example detailed development plans with resource allocations, time schedules, descriptions of techniques and tools.

The guide contains guidelines for the following delivery planning activities:

¥	Production of a delivery plan:

-	Assessment of a problem situation,

through the use of the concepts of initial and final state, and the situational factors and risks within the Strategy Model.

-	Definition of an IS-adaptation strategy,

through the use of specific options and some heuristics within the Strategy Model.

-	Definition of decision points,

through the use of the concepts defined within the Transaction Model and the Deliverable Model; and the guidance within the Method Bridging Guide.

¥	Assessment of a delivery plan,

through the use of the Euromethod guidance on the production of a delivery plan.

## 1.4.	StyleÊConsiderations

The style in which the advice is presented in this guide, may at some points, look somewhat procedural and mechanistic. However, this does not mean that these ÒproceduresÓ have to be followed slavishly. Rather, they show what results are prerequisites regarding the definition of, and decision making for, the production of certain delivery planning documents.

This guidance aims to help users of the guide to locate the answer to the problem they are currently addressing. In this way, the guide intends to help that person determine which step to take next, in order to provide the basis for a decision to be taken or in progressing some task.

The procedural style can also be used as a kind of checklist to avoid important activities and their dependencies being forgotten, but still allows the delivery planning expert to consciously omit those activities which are considered to be irrelevant.

LayoutÊandÊsymbols

Careful consideration has been given to the style of this guide to ensure that it makes reading easy, and thus has the ability to support the activities that Euromethod proposes. Each of the documentation features employed by this guide is now considered briefly.

Throughout the text of this guide a number of symbols are used that ease reading by giving graphical help to recognise the purpose of particular paragraphs.

BulletÊpointÊlists

These are used to emphasise enumerations. This can be used for several purposes:

¥	To highlight important terms; rather than hiding them in the text.

¥	To attribute additional information to terms; thus avoiding sentences that are too long and not well structured.

¥	To list topics that will be dealt with in subsequent sections.

ChecklistÊitems

These are used to give direct support to users of Euromethod.

Some question-answer checklists are provided:

×	Are you just reading this guide to learn about delivery planning?

=>	If so, the checklists provide you with additional information.

×	Are you using this guide while performing a delivery planning activity?

=>	If so, you should work through the checklists in order to achieve the correct results.

There are also checklist items that do not have a part prefixed with the arrow symbol. These just give information on things to be considered in the delivery planning activities.

ReferenceÊarrows

These appear in the left margin and indicate in which Euromethod document and under which key words additional information and definitions on the topic discussed there can be found.

¥	Key word 1

É

¥	Key word n

Reference to the other Euromethod documents is also provided by using the document name in the text. This is especially the case, when the document as a whole is mentioned without referencing particular key words, e.g. delivery planning is based on the concepts defined in the Strategy Model.

ReminderÊnotes

These are used to emphasise what should be kept in mind when reading the subsequent sections.

Remember: This section only gives a quick overview of the symbols used, not a detailed definition of the semantics of these symbols.

PlanningÊactivityÊoverviews

Special headers for the chapters that describe the planning activities give a quick overview of the contents of that chapter. The overview section is therefore the first information to be provided within each of these chapters. The contents of an overview section in this guide are:

| Purpose: | The objective of the activities described in the chapter. |
| --- | --- |
| Concepts: | List of the Euromethod concepts used in the activities. |
| Principles: | List of main principles to follow in the activities. |
| Activities: | List of the activities described in the chapter. |
| Results: | List of the results from the activities. |
| Checklists: | List of the checklists provided to support the activities. |
| Examples: | List of examples to be found in the Euromethod documents. |

HighlightÊboxes

These are used to emphasise statements of general importance.

Knowing the symbols eases using the guide.

Examples

Besides case study examples and the delivery plan examples in the annex, more general examples which are independent from these are used.

| Example | These example boxes are used for: ¥ Providing example information additional to the case studies. ¥ Small examples which serve to clarify points in the text. |
| --- | --- |

## 1.5.	EntryÊPoints

Based on the documentation content and the supporting document features described above, the guidance provided in this document aims to help users of Euromethod quickly to locate the problem they are currently addressing. In this way, the guide intends to help users to determine what step to take next, in order to facilitate a decision to be taken, or in progressing some task during the course of the activity being performed.

A reader can choose from different entry points for reading this guide. The choice of an entry point depends on the purpose of the reader using the guide.

The guide can be used for the following purposes:

×	To get a general overview of the usage of delivery planning in IS-adaptations.

=>	In this case, the Chapters "The Delivery Plan" and ÒDelivery PlanningÓ should be read. They describe the results of delivery planning activities in which Euromethod is applied.

×	To actually perform some of these activities.

=>	In this case, the reader should be familiar with the way of documenting a delivery plan described in the Chapter ÒThe Delivery PlanÓ.

Depending on the delivery planning situation one of the main activities can be chosen. The four delivery planning activities are described in the Chapters:

-	ÒHow to assess a Problem SituationÓ.

-	ÒHow to define a StrategyÓ.

-	ÒHow to define Decision PointsÓ.

-	ÒHow to assess a Delivery PlanÓ.

The definition of decision points is related to the use of IS-development methods and to the bridging of method products to the Euromethod concepts. These relationships are explained in the Section "Entry Points for using this Guide" in the Method Bridging Guide; and in Section 6.3 in this guide.

¥	Entry points

# 2.	TheÊDeliveryÊPlan

A delivery plan defines the customer-supplier decision points and s within the production and completion processes. Through the use of the Euromethod concepts, delivery plans can provide a common means of communication for customers and suppliers regarding IS-adaptations.

¥	Delivery plan

Remember: An IS-adaptation is any kind of modification (correction, enhancement, improvement, etc.) and automation of an information system to fulfil the ever changing needs of an organisation.

An IS-adaptation starts with a tendering process during which a definition of the two subsequent processes: the production process and the completion process, is produced [EM-4-ED]. The definition of the IS-adaptation is documented in a delivery plan, as described in this guide.

A Euromethod delivery plan is a delivery plan with the content as prescribed in this guide. In this guide, the term "delivery plan" always means: a Euromethod delivery plan.

## 2.1.	Purpose

The purpose of a Euromethod delivery plan is to:

¥	Support the customer-supplier relationship by defining the customer-supplier decision points and their related transactions in the production and completion processes.

¥	Document a contractual arrangement as part of the IS-adaptation requirements of an IS-adaptation contract.

Besides the delivery plan which defines the customer-supplier relationship in a particular IS-adaptation, an IS-adaptation can also produce delivery plans for subsequent IS-adaptations.

Such delivery plans have the function of defining future IS-adaptations foreseen as taking place after the current one. Generally, a delivery plan for a future IS-adaptation is accompanied with project plans for the project domain of that subsequent IS-adaptation.

Remember: Using Euromethod, the IS-adaptation requirements described in:

¥	a technical specification within a call for tender document,

¥	a technical proposal within a tender response document,

¥	or a technical annex within an IS-adaptation contract,

consist of the:

¥	IS-descriptions available for the IS-production:

-	IS-descriptions of the current (initial state) information system.

-	IS-descriptions of a future (final state) information system.

¥	Delivery plan.

¥	Project plans available for the IS-project management:

-	Development plan.

-	Quality assurance plan.

-	Configuration management plan.

## 2.2.	Contents

Using Euromethod, a delivery plan contains descriptions of the:

¥	Problem situation:

-	Starting point: the initial state of the IS-adaptation.

-	Goal: the final state of the IS-adaptation.

¥	IS-adaptation strategy: to go from the initial state to the final state.

¥	Decision points: how to go from the initial state to the final state.

Figure 1 prescribes a structure of a delivery plan. Following the figure, there is a short explanation of the contents of a delivery plan. The subsequent chapters provide guidance on how to make and assess delivery plans with these contents.

Delivery Plan:	<IS-adaptation identification>

1.	Problem Situation

¥	Overall description of the problem situation.

1.1.		Starting Point: The Initial State of the IS-adaptation

Overall description of the initial state with:

-	References to the initial state profile in Annex A.

1.2.		Goal: The FinalFinal State of the IS-adaptation

Overall description of the final state with:

-	References to the final state profile in Annex B.

1.3.		Appreciation of the Problem Situation

Complexity, uncertainty and critical risks with:

-	References to situational factor tables in Annex C.

2.	IS-adaptation Strategy

¥	Overall description of the IS-adaptation strategy.

2.1.		Approach to Change Situational Factors.

2.2.		Development Approach

Approaches to description, construction and installation.

2.3.		Project Control Approach

Approaches to development, quality and configuration control.

2.4.		Risk Management Approach.

3.	Decision Points

¥	Overall description of the sequence and contents of decision points 	with:

-	Schedules, purposes and justifications.

-	References to the decision point descriptions in Annex D.

Annex A.	Initial State Profile: deliverable profile of the available IS-descriptions.

Annex B. 	Final State Profile: deliverable profile of the required IS-descriptions.

Annex C. 	Situational Factor Tables: tables with situational factor values.

Annex D. 	Decision Point Descriptions: purpose, deliverable profile, roles involved.

Figure 1: Structure of a Euromethod delivery plan.

### 2.2.1.	ProblemÊsituation

Remember: The initial state of an IS-adaptation is the state of the information system and the available knowledge on it, at the beginning of the production process. The initial state consists of the existing operational information system, possibly some operational items of a future information system (which are not yet in use), and the IS-adaptation requirements defined in the IS-adaptation contract.

The final state of an IS-adaptation is the state of the information system and the knowledge on it, at the end of the IS-adaptation. This can include plans for future IS-adaptations. A description of a final state should contain the identification of the operational items that shall be replaced and the types of operational items that shall be added to or replace the current ones [EM-4-ED].

The initial and final state profiles consist of deliverable profiles as defined in the Method Bridging Guide. The following IS-descriptions should be described:

¥	The IS-descriptions that are available to the IS-production (part of the initial state).

¥	The IS-descriptions that the customer wants to use after the termination of the IS-adaptation (part of the final state).

The documentation of the initial state profile can be provided as part of early versions of a delivery plan, i.e. versions produced before signing the IS-adaptation contract. This is consisting of both profiles of existing products and profiles of products that have not yet been produced, but which are planned to be produced prior to the signing of the contract. The different versions of a delivery plan are presented in Section 2.3.

It should be recognised that within the production process, the initial state might be enhanced by identifying additional products that are made available to the IS-adaptation at a certain decision point. In particular, this can be useful in the case of contract change control transactions if deficiencies have been detected.

Remember: Situational factors are those properties of the problem situation that can be used to determine the most appropriate problem solving strategy. This includes those properties that can have an impact on the type of uncertain events which may occur and their adverse consequences. Therefore, they can be used to predict the risks and to determine the most appropriate strategies for their avoidance or containment [EM-4-ED].

A risk is a hazard, chance of adverse consequences, losses, etc.; exposure to mischance [EM-4-ED].

The appreciation of the problem situation should be documented in terms of situational factors. The situational factors that imply complexity or uncertainty of the situation and the critical risks should be emphasised as the basis for the justification of the chosen IS-adaptation strategy.

The guidance on how to assess a problem situation is given in Chapter 4.

### 2.2.2.	IS-adaptationÊstrategy

Remember: An IS-adaptation strategy is the intended approach to achieve the objectives of an IS-adaptation, i.e. an approach that is appropriate to effectively manage complexity and uncertainty inherent in a certain problem situation [EM-4-ED].

The description of the IS-adaptation strategy should contain a description of how the strategy is tailored to the situation. The relation between the appreciation of the problem situation and the chosen approaches should be documented, e.g. by use of the heuristics on the suitability of the approaches provided by Euromethod.

The description of the chosen IS-adaptation strategy should explain how the strategy will influence the customer-supplier relationships within the production process, and it can contain proposals and requirements to activities which should be included in the project plans, i.e. the development, quality assurance and configuration management plans. The first versions of the project plans can be part of the technical annex of the IS-adaptation contract together with the delivery plan and the available IS-descriptions.

The guidance on how to define an IS-adaptation strategy is given in Chapter 5.

### 2.2.3.	DecisionÊpoints

Remember: A decision point within an IS-adaptation is a point in time where the customer, possibly together with the supplier, is making decisions on the IS-adaptation. A decision point is characterised by the decisions that are made, the roles involved in these decisions, the customer-supplier transactions that take place and thereby the deliverables that are exchanged. These deliverables serve as a basis for the decisions to be made [EM-4-ED].

In a Euromethod delivery plan, a description of a decision point consists of:

¥	Purpose.

A description of the purpose of the decisions that shall be made at the decision point.

¥	Deliverables.

A description of the exchanged deliverables at the decision point:

-	How can the deliverables support the decision making.

-	The required deliverable profile and the related method deliverable profile.

¥	Roles involved.

An allocation of persons to the roles involved in the decision making.

Remember: The following roles in both the customer and the supplier organisations are defined in the Transaction Model [EM-3.1-TM]:

¥	The contract authority role.

¥	The project authority role.

¥	The organisational authority roles:

Senior management, financial authority, legal authority, QM-authority.

¥	The operational expertise roles:

IS-expertise (business, technical, user), QA-expertise, CM-expertise.

The structure of a decision point description within a Euromethod delivery plan is prescribed in Figure 2.

The sequence and schedules of the decision points should be documented in one place in the delivery plan to ease the maintenance, e.g. in the form of tables or diagrams. That is, there should be no schedules in the decision point descriptions.

In the early versions of a delivery plan, the schedules can be stated relatively to the start of the production process.

The guidance on how to define decision points is given in Chapter 6.

Decision point:	<decision point identification>

1.	Purpose

¥	Overall description of the purpose of the decision point.

1.1.		Target domain purpose.

The decisions related to the target domain, e.g. choice of solutions and 	acceptance of IS-descriptions of the existing or a future information 	system.

1.2.		Project domain purpose

The decisions related to the project domain, e.g. decisions regarding 	schedules, budget and allocation of resources.

2.	Deliverables.

¥	Overall description of the exchanged deliverables and how they can 	support the decision making with:

-	References to the deliverable profiles in Annex A.

3.	Roles involved

¥	Overall description of the roles involved in decision making.

¥	For each organisation (customer and supplier) and for each role:

-	Identification of persons allocated to the role.

Annex A.	Required deliverable profile and the related method deliverable profile:

¥	Deliverable profiles with the structure prescribed in the Euromethod
	Method Bridging Guide.

¥	References to the method product profiles in the development plan.

Figure 2: Structure of a decision point description.

## 2.3.	Versions

Within a single IS-adaptation, a delivery plan can evolve through a series of versions. Typically, the customer creates a version as part of the technical specification within the call for tender document; the suppliers create elaborated versions as parts of the technical proposals within their tender response documents; and the customer and the selected supplier create a version as part of the technical annex of the IS-adaptation contract. The delivery plan in the contract is important, because it fixes the initial and final state profiles and it defines the contractual requirements to each delivery within the contract execution. During the production process, the delivery plan will usually remain fixed, but contract change control may result in changes to it.

Figure 3 illustrates the versions of a delivery plan. Euromethod can support different sequences of transactions. This is explained in the Customer and Supplier Guides.

¥	Sequence of transactions

| Transaction type | Delivery plan version |
| --- | --- |
| Call for Tender | Call for tender version |
| Tender Response | Tender response version |
| Supplier selection | Tender response version |
| Contract awarding | Contract version |
| Approval of deliverables | Latest contract version |
| Approval of status and plan | Latest contract version |
| Contract change control | Revised contract version |
| Approval of final deliverables | Latest contract version |
| Contract completion | Last contract version |

Figure 3: Versions of a delivery plan.

# 3.	DeliveryÊPlanning

Using Euromethod, delivery planning is an activity that results in:

¥	either a description of a delivery plan with the contents described in Chapter 2;

¥	or an assessment of the suitability of an existing delivery plan.

The context of the delivery planning activity is described in Section 3.1 and the decomposition of the delivery planning activity is described in Section 3.2.

## 3.1.	Context

The context of delivery planning is illustrated in Figure 4. The delivery planning activity uses input from the following sources, illustrated by the arrows from the sources (boxes) to the delivery planning activity (circle):

¥	Problem situation:

A delivery plan should be tailored to the problem situation. That means, the delivery planning is based on knowledge about the problem situation.

¥	Delivery plan:

Delivery planning can consist of an enhancement or assessment of an existing delivery plan containing a problem situation description (including an initial state profiles and a final state profile), an IS-adaptation strategy and decision point descriptions.

¥	Euromethod:

Delivery planning uses the concepts and guidance described in the Euromethod documents.

¥	Organisational setting:

Delivery planning uses the standards and rules within the organisational setting of the delivery planning activity. The organisation can be either a customer organisation, a supplier organisation or a combination of these.

¥	IS-development methods:

Delivery planning uses the guidance within specific IS-development methods, in particular the process models and the bridges of the method products to the Euromethod concepts (method product profiles).

The result of a delivery planning activity is illustrated by an arrow from the delivery planning (circle) to the result (box). The result is a:

¥	Delivery plan:

As described in Chapter 2, the main contents of a delivery plan is: initial state profiles, final state profiles, an IS-adaptation strategy and decision point descriptions. This is indicated in the text associated with the arrow.

Figure 4: The context of the delivery planning activity.

## 3.2.	ActivitiesÊandÊresults

The decomposition of the delivery planning activity into four activities is illustrated in Figure 5 which presents an overview of the results of each of the activities. The following chapters contain guidance on how to perform the activities.

The assessment of a delivery plan can require an execution of the other activities. That means, the guidance provided for the assessment of a delivery plan makes use of the guidance for the other activities.

| Activities | Results |
| --- | --- |
| Assessment of a problem situation: ¥ Initial and final states. ¥ Situational factors. ¥ Risks. | ¥ Appreciation and description of the problem situation: the initial and final states of the IS-adaptation and important situational factors and risks. |
| Definition of a strategy: ¥ Change of situational factors. ¥ General approaches. ¥ Risk management. | ¥ Description of the choice of IS-adaptation strategy. |
| Definition of decision points: ¥ Sequence of decision points. ¥ Deliverables. ¥ Use of method process models. | ¥ Description of the sequence and contents of the decision points of the IS-adaptation. |
| Assessment of a delivery plan: ¥ Quality of problem situation description. ¥ Suitability of strategy. ¥ Suitability of decision points. | ¥ Assessment of the suitability of a delivery plan. |

Figure 5: The activities and results of delivery planning.

# 4.	HowÊtoÊAssessÊaÊProblemÊSituation

| Purpose: | ¥ To understand the relevant aspects of a problem situation involving IS-adaptation. |
| --- | --- |
| Concepts: | ¥ IS-adaptation (tendering, production and completion processes). ¥ Target domain, project domain. ¥ Initial state, final state, deliverable profile, method product profile. ¥ Information system (operational items). ¥ IS-description (requirements statement, specification, prototype). ¥ Situational factor, complexity, uncertainty, risk. |
| Principles: | ¥ Assess available descriptions (part of the initial state) and requirements on descriptions to be produced (part of the final state). ¥ Use situational factors to understand the situation. |
| Activities: | ¥ Assess initial and final states. ¥ Assess situational factors. ¥ Assess risks. |
| Results: | ¥ Definition of initial state and final state. ¥ Definition of important situational factors. ¥ Identification of critical risks. |
| Checklists: | ¥ Initial state activities. ¥ Final state activities. ¥ Situational factors. ¥ Risks associated to uncertainty. |
| Examples: | ¥ Case study examples, see the following index entries in [EM-2.5-CS]: Initial state profile, final state profile, situational factor (table, complexity, uncertainty), risks. ¥ Annex A-C: Delivery plan examples. |

Both a customer and a supplier can use the guidance in this chapter, but with different backgrounds and different point of views.

At the start of an IS-adaptation, a customer may only have an unclear picture of the kind of problem his organisation is facing. What the customer does know, is that some improvement is required in relation to the current situation.

This chapter of the Delivery Planning Guide helps a customer embark on an IS-adaptation, independent of whether he has a clear picture of where he should eventually take the organisation. Euromethod is used as a tool to record what he does know in a clear and systematic way. The chapter also helps the customer to assess the characteristics and risks of the problem situation.

For a supplier, considering whether to submit a tender response, this chapter provides guidance to enhance his understanding and assessment of the problem situation.

Both the customer and the supplier can use the guidance later in the process when there is a need to change the plans within the production process, or a need to plan for future IS-adaptations.

The purpose of the problem situation assessment is to understand relevant aspects of the situation regarding either an ongoing or a future IS-adaptation in order to be able to act appropriately.

This assessment is supported by the situational factors introduced in the Strategy Model. But first, it is important to have a good understanding of the current expectations for the results and the starting point of the IS-adaptation. This is achieved by undertaking:

¥	Situational factors

¥	An assessment of the initial and final state profiles.

The initial and final state profiles provide important information about the IS-adaptation. This facilitates the determination of the situational factor values and the identification of critical risks, which is performed by undertaking:

¥	An assessment of relevant situational factors, including supporting explanations.

¥	An assessment of critical risks associated with the particular IS-adaptation.

The results gained from this analysis of the problem situation are then input into the definition of the IS-adaptation strategy and the decision points.

## 4.1.	InitialÊandÊfinalÊstates

Euromethod applies to any IS-adaptation effort that can be characterised by a defined initial and a defined final state. As a consequence, the Euromethod concepts can be reapplied at various stages during the life of the same information system as explained in the Transaction Model.

¥	IS-adaptations

The Customer and Supplier Guides give guidance on how to define a feasible IS-adaptation in terms of an initial and a final state. The Customer Guide defines typical initial and final states and discusses which combinations are manageable and which are difficult to manage. The following explains the guidance on how to define the initial and final states in a Euromethod delivery plan.

¥	Typical initial and final states

Remember: The initial state of an IS-adaptation is the state of the information system and the available knowledge on it, at the beginning of the production process. The initial state consists of the existing operational information system, possibly some operational items of a future information system (which are not yet in use), and the IS-adaptation requirements defined in the IS-adaptation contract.

The final state of an IS-adaptation is the state of the information system and the knowledge on it, at the end of the IS-adaptation. This can include plans for future IS-adaptations. A description of a final state should contain the identification of the operational items that shall be replaced and the types of operational items that shall be added to or replace the current ones [EM-4-ED].

The first thing to do is to make an assessment of the contents and quality of the IS-descriptions and operational items that are going to be available to the project actors performing the production process. The IS-descriptions form part of the initial state and can be used to get an understanding of the desired changes of the operational information system and an understanding of the final state information system. Secondly, it should be considered what IS-descriptions and operational items are going to be required and used by the customer after the completion of the IS-adaptation under consideration. These IS-descriptions and operational items are part of the final state.

As part of this assessment, certain weaknesses in the available knowledge will often be identified. It may be the case that it requires effort in order to enhance the existing IS-descriptions.

The following is guidance regarding the activities to be performed in defining the initial and final states of an IS-adaptation. In practice, the sequence of the activities can vary and the definition of the initial and final states is typically done in parallel.

DefinitionÊofÊaÊinitialÊstate

To define the initial state, it is generally necessary to:

×	Assess whether the existing IS-descriptions are sufficient to understand the problem situation, to plan the IS-adaptation and to define which IS-descriptions need to be enhanced or produced. Examples of weaknesses in existing IS-descriptions which may be encountered are:

-	The requirements to the future information system are contradictory or not clarified.

-	The risks, costs or benefits of the change of the information system are not clarified.

-	Specifications of the future information system are not consistent.

×	Decompose the initial state or future information system into sub-systems and, in those situations where it is possible and appropriate, define the initial state for each of the sub-systems.

Sub-systems can be defined by separating the target domain into smaller target domains. The Deliverable Model provides concepts to characterise the processes of a target domain, i.e. the processes of a part of an information system, a sub-system:

¥	Characterisation of a target domain

-	Identification of the considered business areas.

-	Identification of the considered organisational units.

More specifically, regarding the IS-descriptions (requirements statements, specifications and prototypes), it is necessary to:

×	Define which of the available IS-descriptions of the current information system are relevant to use in this IS-adaptation, and define their method deliverable profiles.

×	Define the method deliverable profiles of the IS-descriptions of the future information system which are currently available.

DefinitionÊofÊaÊfinalÊstate

To define the final state, it is generally necessary to:

×	Decompose the final state information system into sub-systems and, in those situations where it is possible and appropriate, define the final state for each of the sub-systems. There may be different types of IS-descriptions related to the sub-systems.

More specifically, in considering the operational items in the final state, it is necessary to:

×	Define the operational items in the initial state information system that are going to be changed, and the new operational items that are going to be constructed and installed.

×	Define the manuals and work instructions that are necessary to ensure a smooth running and efficient new information system.

×	Define which data found in the existing information system needs to be converted into new operational items in the new information system (migration of data).

×	Define the operational items that are going to be constructed, but not installed.

When considering the IS-descriptions of the final state information system, it is necessary to:

×	Define the necessary interfaces between the new operational items, installed as part of this IS-adaptation, and the operational items which are presently in use.

×	Define the IS-descriptions that are necessary in order to maintain the final state information system in an efficient way, and define the policy for the maintenance of these IS-descriptions, e.g. who is responsible for this maintenance.

×	Define the IS-descriptions that are necessary in order to further develop the final state information system in an efficient manner. Available plans regarding the further development should be used wherever possible.

×	Define the requirements statements and prototypes that are going to be used after the termination of this IS-adaptation. (Not used as part of the operational information system, but within a future IS-adaptation).

Finally, considering the IS-descriptions of, and plans for, future information systems it is necessary to:

×	Define the requirements statements, the specifications and the prototypes that are required in order to develop future information systems. Where possible, available plans regarding the further development should be consulted.

×	If this IS-adaptation shall result in proposals for future IS-adaptations, then it is necessary to define the appropriate plans for those future IS-adaptations.

## 4.2.	SituationalÊfactors

Remember: Situational factors are those properties of the problem situation that can be used to determine the most appropriate problem solving strategy. This includes those properties that can have an impact on the type of uncertain events which may occur and their adverse consequences. Therefore, they are used to predict the risks and to determine the most appropriate strategies for their avoidance or containment [EM-4-ED].

The Euromethod situational factors are a checklist for obtaining knowledge about the problem situation. Figures 5 and 6 show the situational factor tables that serve for documenting the situational factor values. The structure of these tables shows the grouping of situational factors within the target and project domain. The values allocated to each factor can be used to characterise the complexity and uncertainty of the organisational situation and the IS-adaptation. The factors are described in detail within the Strategy Model. From this description, the questions that should be asked in order to obtain the knowledge necessary to determine the situational factor values can be derived.

¥	Situational factors

Once the situational factor values are determined, special attention should be given to factors that contribute to either a complex or an uncertain situation. These factors will normally have a big influence on the definition of the appropriate IS-adaptation strategy, as will be explained in the next chapter.

It is recommended that the practitioners record their own experiences about:

¥	How to determine the relevant situational factors, for example in the form of metrics, e.g. project size, adapted to their typical problem situations; and the methods to obtain the necessary knowledge in an organisation.

¥	Which situational factors are the most important, for example in the form of weightings to be applied to the different factors.

¥	Which additional situational factors (not currently defined in Euromethod) are important to take into account, and how they can influence the definition of an IS-adaptation strategy.

The situational factor tables in Figure 6 and 7 can be used to record the situational factors by ticking the values appropriate for the problem situation in question. The situational factor tables give an overview of the problem situation that can be used in the definition of a suitable IS-adaptation strategy, see the examples in the Case Study document. The situational factor tables should be backed up by an explanation of the choice of the situational factor values.

Figures 6 and 7 emphasise the open character of Euromethod by having open rows where additional situational factors can be stated.

Remember: The list of situational factors is neither definitive nor exhaustive. It contains examples that can be used and enhanced based upon personal and organisational experience [EM-3.3-SM].

| Target domain | Complexity | simple | moderate | com-plex | Uncertainty | cer-tain | moderate | uncertain |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Information System | Heterogeneity of actors | low | medium | high | Attitude of actors | posi-tive | neu-tral | negative |
|  | Size of target domain | small | medium | large | Ability of actors | high | medium | low |
|  | Size of distribution | small | medium | large | Stability of environment | high | medium | low |
|  | Complexity of information | low | medium | high | Formality of information | high | medium | low |
|  | Complexity of business processes | low | medium | high | Formality of business processes | high | medium | low |
|  |  |  |  |  | Stability of information and business processes | high | medium | low |
|  |  |  |  |  | Specificity of information system | low | medium | high |
|  |  |  |  |  | Understandability of existing system | high | medium | low |
|  |  |  |  |  | Strategic importance | low | medium | high |
|  |  |  |  |  | Importance of organisational changes | low | medium | high |
|  |  |  |  |  | Availability, clarity & stability of requirements | high | medium | low |
|  |  |  |  |  | Quality of existing specifications | high | medium | low |
| Computer System | Complexity of data | low | medium | high | Importance of technological changes | low | medium | high |
|  | Complexity of functions | low | medium | high |  |  |  |  |
|  | Complexity of non-functional requirements | low | medium | high |  |  |  |  |
|  | Number of replications of computer system | one | few | ma-ny |  |  |  |  |
|  | Complexity of target technology | low | medium | high | Novelty of target technology | low | medium | high |

Figure 6: Situational factor table for the target domain.

| Project domain | Complexity | simple | moderate | com-plex | Uncertainty | cer-tain | moderate | uncertain |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Task | Size of project | small | medium | large | Novelty of IS-adaptation | low | medium | high |
|  | Complexity of migration | low | medium | high | Adequacy of schedules | - | nor-mal | tight |
|  |  |  |  |  | Adequacy of budget | - | nor-mal | tight |
| Project Structure | Number of sub-contractors | none | few | ma-ny | Dependency on sub-contractors | none | low | high |
|  | Number of interfaces to other IS-adaptations | none | few | ma-ny | Dependency on other IS-adaptations | none | low | high |
|  |  |  |  |  | Formality of customer-supplier context | high | medium | low |
| Project Actors | Number of project actors | small | medium | large | Capability of project team | high | medium | low |
| Project Technology | Complexity of develop-ment technology | low | medium | high | Novelty of develop-ment technology | low | medium | high |
|  |  |  |  |  | Availability of appro-priate dev. technology | high | medium | low |

Figure 7: Situational factor table for the project domain.

## 4.3.	Risks

Remember: A risk is a hazard, chance of adverse consequences, losses, etc.; exposure to mischance [EM-4-ED].

The risks which are considered relate to the complexity and uncertainty of the situation. It is important to find resolutions to those risks which relate to the complexity or uncertainty of a situation. The Strategy Model contains examples of risks associated to certain values of the situational factors. These risks are inherent in the problem situation characterised by the situational factor with that value. According to the definition of risk, each risk is described in terms of the adverse consequences that may occur in an IS-adaptation.

The following overview of the risks can be used to predict the risks in a situation characterised by Euromethod situational factors. A definition of the risks is given in the Strategy Model. The degree to which the predicted risks are critical should then be assessed, with respect to the:

¥	Risks

¥	Probability of the occurrence of the possible adverse consequences.

¥	Impact of those consequences on the IS-project, e.g. the impact on costs, schedules and quality of deliverables.

The risks with a high probability of occurrence and high impact on the IS-adaptation are the critical risks. The critical risks should influence the definition of an IS-adaptation strategy and those decision points that are tailored to the specific characteristics of the problem situation. They should be documented in the delivery plan. If appropriate, the other risks should be given attention too, albeit in more detailed plans.

RisksÊassociatedÊtoÊcomplexity

For the complexity situational factors, risks are generally related to the management of the IS-project:

¥	Loss of control of the project,

and to the design of the information system:

¥	Information system is not working or incapable to deal with the complexity of the target domain.

A complex problem situation requires risk resolutions to handle the complexity and thereby reducing the probability of the risks associated to complexity. The criticality of those risks depends on an overall assessment of the problem situation, including both the situational factors that imply complexity and the factors that imply uncertainty.

RisksÊassociatedÊtoÊuncertainty

The following risks are identified and defined in the Strategy Model related to uncertainty situational factors. The risks are defined by the adverse consequences that may occur and they are ordered according to the probability of an early occurrence of the consequences in an IS-adaptation:

¥	Risks

¥	Uncertain or unfeasible requirements.

¥	Uncertain interfaces to other systems.

¥	Evolving requirements.

¥	Unpredictable costs for the organisation.

¥	Unpredictable costs for the project.

¥	Lack of target domain actor participation.

¥	Technical shortfalls in externally performed tasks.

¥	Delays in the delivery of the products.

¥	Poor quality of the products.

¥	Increased costs of the project.

¥	Integration problems.

¥	Shortfalls in non-functional properties.

¥	Straining the computer science capabilities.

¥	Developing a wrong or unfeasible system.

¥	IS-adaptation not accepted by IS-actors.

¥	Business implications of project failure.

The risks can be inherent in a problem situation with certain situational factors as indicated in Figures 8, 9 and 10.

The list of risks is neither definitive nor exhaustive. It contains examples that can be used and enhanced based upon personal and organisational experience.

| Situational factor | Information system factors: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| implying uncertainty | Attitude of actors of the information system is negative |  |  |  |  |  |  |  |  |  |
|  |  | Ability of actors in the information system is low |  |  |  |  |  |  |  |  |
|  |  |  | Stability of environment is low |  |  |  |  |  |  |  |
|  |  |  |  | Formality of information is low |  |  |  |  |  |  |
|  |  |  |  |  | Formality of business processes is low |  |  |  |  |  |
|  |  |  |  |  |  | Stability of inf. & buss. proc. is low |  |  |  |  |
|  |  |  |  |  |  |  | Specificity of IS is high |  |  |  |
| Risk |  |  |  |  |  |  |  | Understandability is low |  |  |
| - chance of adverse consequences |  |  |  |  |  |  |  |  | Strategic import. is high |  |
| Uncertain or unfeasible requirements |  | X |  | X | X |  | X |  |  |  |
| Uncertain interfaces to other systems |  |  |  |  |  |  |  |  |  |  |
| Evolving requirements |  |  | X |  |  | X |  |  |  |  |
| Unpredictable costs for the organisation |  |  |  |  |  |  |  | X | X |  |
| Unpredictable costs for the project |  |  |  |  |  |  |  | X |  |  |
| Lack of target domain actor participation | X |  |  |  |  |  |  |  |  |  |
| Shortfalls in externally performed tasks |  |  |  |  |  |  |  |  |  |  |
| Delays in the delivery of the products |  |  |  |  |  |  |  |  |  |  |
| Poor quality of the products |  |  |  |  |  |  |  |  |  |  |
| Increased costs of the project |  |  |  |  |  |  |  |  |  |  |
| Integration problems |  |  |  |  |  |  |  |  |  |  |
| Shortfalls in non-functional properties |  |  |  |  |  |  |  |  |  |  |
| Straining computer science capabilities |  |  |  |  |  |  |  |  |  |  |
| Developing wrong or unfeasible system | X | X | X | X | X | X |  | X |  |  |
| IS-adaptation not accepted by actors | X |  |  |  |  |  |  |  |  |  |
| Business implications of project failure |  |  |  |  |  |  |  |  | X |  |

Figure 8: Risks associated to target domain uncertainty (1).

| Situational factor | Information system factors: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| implying uncertainty | Importance of organisational changes is high |  |  |  |  |  |  |  |  |  |
|  |  | Availability/clarity/stability of requirements is low |  |  |  |  |  |  |  |  |
|  |  |  | Quality of existing specifications is low |  |  |  |  |  |  |  |
|  |  |  |  | Computer system factors: |  |  |  |  |  |  |
|  |  |  |  | Import. of technological changes is high |  |  |  |  |  |  |
|  |  |  |  |  | Novelty of target technology is high |  |  |  |  |  |
| Risk |  |  |  |  |  |  |  |  |  |  |
| - chance of adverse consequences |  |  |  |  |  |  |  |  |  |  |
| Uncertain or unfeasible requirements |  | X |  |  |  |  |  |  |  |  |
| Uncertain interfaces to other systems |  | X |  |  |  |  |  |  |  |  |
| Evolving requirements |  | X |  |  |  |  |  |  |  |  |
| Unpredictable costs for the organisation | X |  |  | X |  |  |  |  |  |  |
| Unpredictable costs for the project |  |  | X |  | X |  |  |  |  |  |
| Lack of target domain actor participation |  |  |  |  |  |  |  |  |  |  |
| Shortfalls in externally performed tasks |  |  |  |  |  |  |  |  |  |  |
| Delays in the delivery of the products |  |  |  |  |  |  |  |  |  |  |
| Poor quality of the products |  |  |  |  |  |  |  |  |  |  |
| Increased costs of the project |  |  |  |  |  |  |  |  |  |  |
| Integration problems |  |  |  |  |  |  |  |  |  |  |
| Shortfalls in non-functional properties |  |  |  | X | X |  |  |  |  |  |
| Straining computer science capabilities |  |  |  |  |  |  |  |  |  |  |
| Developing wrong or unfeasible system |  |  | X | X | X |  |  |  |  |  |
| IS-adaptation not accepted by actors | X |  |  | X |  |  |  |  |  |  |
| Business implications of project failure | X |  |  |  |  |  |  |  |  |  |

Figure 9: Risks associated to target domain uncertainty (2).

| Situational factor | Project task factors: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| implying uncertainty | Novelty of IS-adaptation is high |  |  |  |  |  |  |  |  |  |
|  |  | Adequacy of schedules is tight |  |  |  |  |  |  |  |  |
|  |  |  | Adequacy of budget is tight |  |  |  |  |  |  |  |
|  |  |  |  | Project structure factors: |  |  |  |  |  |  |
|  |  |  |  | Dependency of sub-contractors is high |  |  |  |  |  |  |
|  |  |  |  |  | Dependency of other IS-adapt. is high |  |  |  |  |  |
|  |  |  |  |  |  | Formal. of cust-supp. context is low |  |  |  |  |
|  |  |  |  |  |  |  | Project actors factor: |  |  |  |
|  |  |  |  |  |  |  | Capability of project team is low |  |  |  |
|  |  |  |  |  |  |  |  | Project technology factors: |  |  |
| Risk |  |  |  |  |  |  |  | Novelty of dev. tech. is high |  |  |
| - chance of adverse consequences |  |  |  |  |  |  |  |  | Avail. of tech. is low |  |
| Uncertain or unfeasible requirements |  |  |  |  |  |  |  |  |  |  |
| Uncertain interfaces to other systems |  |  |  |  |  |  |  |  |  |  |
| Evolving requirements |  |  |  |  | X | X |  |  |  |  |
| Unpredictable costs for the organisation |  |  |  |  |  |  |  |  |  |  |
| Unpredictable costs for the project | X |  |  |  |  |  | X | X | X |  |
| Lack of target domain actor participation |  |  |  |  |  |  |  |  |  |  |
| Shortfalls in externally performed tasks |  |  |  | X |  |  |  |  |  |  |
| Delays in the delivery of the products |  |  | X |  |  |  | X | X | X |  |
| Poor quality of the products |  | X | X |  |  |  | X | X | X |  |
| Increased costs of the project |  | X |  |  |  |  |  |  |  |  |
| Integration problems |  |  |  |  | X |  |  |  |  |  |
| Shortfalls in non-functional properties |  |  |  |  |  |  |  |  |  |  |
| Straining computer science capabilities |  |  |  |  |  |  | X |  |  |  |
| Developing wrong or unfeasible system | X |  |  |  |  |  | X |  |  |  |
| IS-adaptation not accepted by actors |  |  |  |  |  | X | X |  |  |  |
| Business implications of project failure |  |  |  |  |  |  |  |  |  |  |

Figure 10: Risks associated to project domain uncertainty.

# 5.	HowÊtoÊDefineÊaÊStrategy

| Purpose: | ¥ To define a suitable IS-adaptation strategy. |
| --- | --- |
| Concepts: | ¥ Situational factor, complexity, uncertainty, risk. ¥ IS-adaptation strategy, approaches to description, construction, installation and project control, risk management. ¥ Deliverable profile: target domain deliverable (deliverable type, considered system, information system view, computer system view, IS-property, non-functional property, deliverable scope, deliverable state, formality); project domain deliverable (deliverable type, work area, project property). |
| Principles: | ¥ Use a tailored and risk-oriented approach to IS-adaptation. ¥ Define installation approach carefully. ¥ Manage complexity and uncertainty. |
| Activities: | ¥ Define actions to change individual situational factors. ¥ Define suitable approaches to description, construction, installation and project control. ¥ Define risk management of complexity and uncertainty. |
| Results: | ¥ Proposals for actions to change individual situational factors. ¥ Approaches to description, construction, installation and project control. ¥ Proposals for risk management of complexity and uncertainty. |
| Checklists: | ¥ Actions to change individual situational factors. ¥ Suitability of approaches to description, construction, installation and project control. ¥ Management of complexity and uncertainty. |
| Examples: | ¥ Case study examples, see the following index entries in [EM-2.5-CS]: IS-adaptation strategy (approaches to description, construction, installation and project control), deliverable profile, management of risks. ¥ Annex A-C: Delivery plan examples. |

Once the relevant situational factors and the critical risks are defined, as explained in the preceding chapter, they can be analysed and a suitable IS-adaptation strategy can be defined. This chapter contains guidance on how to do that.

Remember: An IS-adaptation strategy is the intended approach to achieve the objectives of an IS-adaptation, i.e. an approach that is appropriate to effectively manage complexity and uncertainty inherent in a certain problem situation [EM-4-ED].

Firstly, there is guidance on how to change individual situational factors that have a critical impact on the uncertainty of the situation.

Secondly, there is guidance on how to define a suitable approach to installation, construction, description and project control. This guidance is structured as a choice between a set of possible options, supported by heuristics based on situational factors and identified critical risks, defined in the Strategy Model.

¥	Strategy options and heuristics

Thirdly, there is more specific guidance on how to manage the complexity and uncertainty in a situation. This guidance consists of proposals for actions to include in the plans. These actions are related to either approaches, decision points or resources.

The resulting IS-adaptation strategy is the basis for the subsequent definition of decision points, as explained in the following chapter. The chosen IS-adaptation strategy provides the justification for the sequence and contents of the decision points. Therefore, the strategy should be documented as part of the delivery plan.

Remember: The IS-adaptation strategy heuristics are neither definitive nor exhaustive. They are examples that can be used and enhanced based upon personal and organisational experience. The heuristics contain no complex relations, e.g. dependencies, between the situational factors. [EM-3.3-SM].

## 5.1.	ApproachÊtoÊchangeÊsituationalÊfactors

The following examples of heuristics provide proposals for actions that can change those situational factors that imply an uncertain situation:

×	When the attitude of actors is negative:

=>	Involve the actors, e.g. increase the information of actors, the actor participation and the actor influence within the IS-adaptation.

=>	Motivate the actors, e.g. by making the benefits understandable and visible.

×	When the ability of actors is low:

=>	Use actor training, e.g. perform a training programme for the people who are actors in the IS-adaptation.

×	When the understandability of the existing system is low:

=>	Use re-engineering, i.e. add decision points to the delivery plan associated with raising the understanding of the existing information system through IS-descriptions of the existing information system.

×	When the availability or clarity of the requirements to the IS-adaptation are low:

=>	Make a stringent requirements analysis, i.e. add decision points to the delivery plan regarding requirements statements of the future information system and traceability of the requirements.

×	When the quality of the existing specifications is low:

=>	Redo the specifications, i.e. add decision points to the delivery plan regarding the approval of the specifications of the future information system.

=>	Review the existing specifications with the actors in the information system, e.g. use a participatory description approach.

×	When the capability of the project team is low:

=>	Use project team training, e.g. perform a training programme for the people who are actors in the IS-adaptation.

=>	Allocate more skilled people to the project team.

## 5.2.	DevelopmentÊapproach

A development approach is a combination of an installation approach, a construction approach and a description approach.

As explained in detail later, the choice of a suitable installation approach is of critical importance to achieving success. The choice of installation approach can put constraints and requirements on the other approaches. Similarly, the construction approach can put constraints on the description approach. Therefore, it is recommended to define the development approach in the following sequence: installation, construction and then description approach.

The guidance on the choice of approaches to installation, construction and description is based on the options defined in the Strategy Model, see Figure 11.

¥	Strategy options

### 5.2.1.	InstallationÊapproach

The determination of an installation approach consists of making decisions regarding the versions of the information system that should be installed in the target domain, and the sequence of these installations.

Remember: The installation of an information system is the process of making the information system operational within the target domain [EM-4-ED].

Making changes to the operational information system through the installation of new or changed operational items are the main objectives of most of the IS-adaptations.

It is the installation of the information system which makes the results of an IS-adaptation usable for the actors of the information system.

The installation is "the moment of truth" regarding the changes to an information system within an IS-adaptation. Therefore, the definition of a suitable installation approach is of critical importance to achieving success.

Due care and attention must be paid in defining the installation approach.

| Development approach | Strategy options |
| --- | --- |
| System installation approach | 1. One shot installation: ¥ a single version installed in one step. 2. Incremental installation: ¥ parts installed in a sequence of steps. ¥ no change of requirements and specifications after first installation. 3. Evolutionary installation: ¥ versions installed in a sequence of steps. ¥ changes of requirements and specifications are possible after learning from usage. Geographical coverage: 1. Full coverage 2. Stepwise coverage |
| System construction approach | 1. One shot construction: ¥ a single version tested in one step. 2. Incremental construction: ¥ parts tested in a sequence of steps. ¥ no change of requirements and specifications after first construction. 3. Evolutionary construction: ¥ versions tested in a sequence of steps. ¥ changes of requirements and specifications are possible after learning from test. |
| System description approach | 1. Mode of operation: ¥ Analytical: use of abstractions and specifications ¥ Experimental: use of experiments and prototypes. 2. Type of co-operation: ¥ Expert-driven: production and assessment separated ¥ Participatory: joint production and assessment. |

Figure 11: Strategy options for a development approach.

It is advised that the installation approach should be influenced by the situational factors for the IS-adaptation under consideration. However, the knowledge about the situation can be insufficient to define an installation approach. In this case, the IS-adaptation should include activities to obtain the knowledge necessary to make decisions regarding a suitable installation approach. The definition of a suitable installation approach can in this way influence the decision points related to the description of the information system.

The choice of installation approach puts some constraints and requirements on the other approaches, for example on the scope and sequence of the deliverables within the description and construction of sub-systems.

InstallationÊapproachÊoptions

The customer and supplier should choose among the following three installation approaches:

¥	Strategy options

1.	One shot installation:

The whole information system is installed (and used) in one version.

2.	Incremental installation:

The information system is installed (and used) in successive parts. Each part contains a sub-set of the information system functionalities. The requirements to the installed information system are fully defined before the first installation and will not be changed afterwards.

3.	Evolutionary installation:

The information system is installed (and used) in successive versions. Between two versions the requirements to the description and construction of the information system can be changed after learning from using the information system. Each version may contain a sub-set or the whole set of functionalities.

Note that the requirements to a version normally have to be fixed in a period of time during construction and installation, but after installation they can be changed and influence the description and construction of the next version.

Orthogonal to those three "system coverage" approaches, the geographical coverage should be considered. Depending on the problem situation, it should be considered whether to have several steps in the installation of a new version of an information system. The first step of an installation of a version would then have a limited geographical coverage, e.g. only one branch, one department or one office. This step can be used as a pilot installation with the purpose of tuning the information system and improving the installation process before the whole target domain is influenced by the changes. The following steps can then increase the geographical coverage, with the last step having a total coverage of the target domain.

That means, a stepwise geographical coverage of installations can be combined with any of the three installation approaches: one shot, incremental or evolutionary.

HeuristicsÊonÊtheÊsuitabilityÊofÊinstallationÊapproaches

The suitability of an installation approach depends on the complexity and uncertainty of the situation:

¥	Strategy heuristics

×	Evolutionary is suitable when the situation is uncertain.

×	Incremental is suitable when the situation is complex, but not uncertain.

Additionally, the suitability of an installation approach depends on some individual situational factors, for example:

×	Incremental or evolutionary is suitable when the schedules are tight,

i.e. install something as fast as possible.

×	One shot is suitable when the schedules are normal and the situation is not complex and not uncertain.

×	Evolutionary is suitable when the importance of the organisational changes is high.

The dependencies on the schedules and the complexity and uncertainty of the situation are illustrated in Figure 12.

There are no general rules on the relative weight of the different situational factors in the assessment of the complexity and uncertainty of the situation. However, the effectiveness of the installation approach to manage complexity or uncertainty depends on the individual situational factors. For example, the heterogeneity of actors is a source of complexity which can hardly be managed through an incremental installation approach; similarly, the novelty of the development technology is a source of uncertainty which best can be managed by an evolutionary installation approach because an evolutionary installation approach implies an evolutionary construction approach.

| Situational Factor |  |  | Installation Approach |  |  |
| --- | --- | --- | --- | --- | --- |
| Schedules | Complexity | Uncertainty | One Shot | Incremental | Evolutionary |
| Normal | Simple | Certain | X |  |  |
|  |  | Moderate | X |  | X |
|  |  | Uncertain |  |  | X |
|  | Moderate | Certain | X |  |  |
|  |  | Moderate | X |  | X |
|  |  | Uncertain |  |  | X |
|  | Complex | Certain |  | X |  |
|  |  | Moderate |  | X | X |
|  |  | Uncertain |  |  | X |
| Tight | Simple | Certain |  | X |  |
|  |  | Moderate |  | X | X |
|  |  | Uncertain |  |  | X |
|  | Moderate | Certain |  | X |  |
|  |  | Moderate |  | X | X |
|  |  | Uncertain |  |  | X |
|  | Complex | Certain |  | X |  |
|  |  | Moderate |  | X | X |
|  |  | Uncertain |  |  | X |
| Heuristics: × Evolutionary is suitable when the situation is uncertain. × Incremental is suitable when the situation is complex, but not uncertain. × Incremental or evolutionary is suitable when the schedules are tight, i.e. install something as fast as possible. × One Shot is suitable when the schedules are normal and the situation is not complex and not uncertain. |  |  |  |  |  |

Figure 12: Examples of heuristics on the suitability of installation approaches.

Heuristics regarding geographicalÊcoverageÊofÊinstallations

A stepwise installation of an information system version can be used to handle the following complexity of a problem situation:

¥	Size of target domain is high.

¥	Size of distribution is high.

¥	Complexity of non-functional properties is high.

¥	Many replications of computer system.

¥	Complexity of target technology is high.

¥	Complexity of migration is high.

¥	Many interfaces to other IS-adaptations.

ExamplesÊofÊriskÊreduction

The evolutionary installation approach can be used to reduce the risk of:

¥	Uncertain or unfeasible requirements to the IS-adaptation.

¥	Uncertain interfaces to other systems.

¥	Evolving requirements.

¥	Unpredictable costs for the organisation.

¥	Unpredictable costs for the project.

¥	Delays in the delivery of products.

¥	Poor quality of the products.

¥	Increased costs of the project.

¥	Integration problems.

¥	Developing a wrong or unfeasible system.

¥	IS-adaptation not accepted by IS-actors.

¥	Business implications of project failure.

The incremental installation approach can be used to reduce the risk of:

¥	Loss of control of the project.

¥	Unpredictable costs for the organisation.

¥	Unpredictable costs for the project.

¥	Poor quality of the products.

¥	Increased costs of the project.

¥	Integration problems.

¥	IS-adaptation not accepted by IS-actors.

The stepwise installation of an information system version can be used to reduce the risk of:

¥	Loss of control of the project.

¥	Unpredictable costs for the organisation.

¥	Unpredictable costs for the project.

¥	Poor quality of the products.

¥	Business implications of project failure.

### 5.2.2.	ConstructionÊapproach

A construction approach defines how the information system is going to be constructed and tested. The choice of a construction approach consists of making decisions regarding the steps in which the information system is constructed and tested, i.e. decisions regarding the sequence and type of parts or versions of the information system that should be constructed, tested and delivered by the supplier to the customer.

ConstructionÊapproachÊoptions

The customer and supplier should choose among the following three construction approaches:

¥	Strategy options

1.	One shot construction:

The whole information system is constructed (and tested) in one version.

2.	Incremental construction:

The information system is constructed (and tested) in successive parts. Each part contains a sub-set of the information system functionalities. The requirements to the installed information system are fully defined before the first construction and will not be changed afterwards.

3.	Evolutionary construction:

The information system is constructed (and tested) in successive versions. Between two versions, the requirements to the description and construction of the information system can be changed after learning from testing the information system. Each version may contain a sub-set or the whole set of functionalities.

From the point of view of the customer-supplier relationship, the installation approach is more important than the construction approach.

In all situations, the installation approach will influence the customer-supplier relationship. The construction approach can have influence on the customer-supplier relationship, but may have influence solely on the internal production process performed within the supplier organisation. It depends on the particular situation.

The following dependencies between installation and construction approaches exist:

¥	The use of a one shot installation approach can be combined with all the construction approaches: Construction can be followed by a final acceptance test of the whole information system and then a one shot installation.

¥	The use of an incremental installation approach can be combined with all the construction approaches:

-	One shot construction can be followed by a final acceptance test of the whole information system and then successive installation of the parts.

-	Incremental construction of each part can be followed by acceptance testing and installation of the part.

-	Evolutionary construction of each part can be followed by acceptance testing and installation of the part.

¥	The use of an evolutionary installation approach implies the use of an evolutionary construction approach, because the requirements to the construction can be changed after learning from using the information system.

HeuristicsÊonÊtheÊsuitabilityÊofÊconstructionÊapproaches

The suitability of a construction approach depends on the complexity and uncertainty of the situation, together with the adequacy of the project schedules defined in the contract. The influence of situational factors on the suitability of construction approaches is very similar to their influence on the suitability of installation approaches. Therefore, the heuristics about the suitability of an installation approach can also be used to access the suitability of a construction approach, see Figure 13.

¥	Strategy heuristics

There are no general rules on the relative weighting of the different situational factors in the assessment of the complexity and the uncertainty of a situation. However, as for the installation approach, the effectiveness of the construction approach to manage complexity or uncertainty depends on the individual situational factors.

This dependency between the effectiveness of an approach and the situational factors is not exactly the same for the construction approach as for the installation approach. For example:

¥	The capability of project team, or the novelty of development technology are sources of uncertainty that can be better managed through using an evolutionary construction approach.

¥	The number of replications of the computer system is a source of complexity that can be managed by an incremental installation approach and not by an incremental construction approach.

| Situational Factor |  |  | Construction Approach |  |  |
| --- | --- | --- | --- | --- | --- |
| Schedules | Complexity | Uncertainty | One Shot | Incremental | Evolutionary |
| Normal | Simple | Certain | X |  |  |
|  |  | Moderate | X |  | X |
|  |  | Uncertain |  |  | X |
|  | Moderate | Certain | X |  |  |
|  |  | Moderate | X |  | X |
|  |  | Uncertain |  |  | X |
|  | Complex | Certain |  | X |  |
|  |  | Moderate |  | X | X |
|  |  | Uncertain |  |  | X |
| Tight | Simple | Certain |  | X |  |
|  |  | Moderate |  | X | X |
|  |  | Uncertain |  |  | X |
|  | Moderate | Certain |  | X |  |
|  |  | Moderate |  | X | X |
|  |  | Uncertain |  |  | X |
|  | Complex | Certain |  | X |  |
|  |  | Moderate |  | X | X |
|  |  | Uncertain |  |  | X |
| Heuristics: × Evolutionary is suitable when the situation is uncertain. × Incremental is suitable when the situation is complex, but not uncertain. × Incremental or evolutionary is suitable when the schedules are tight, i.e. construct something as fast as possible. × One Shot is suitable when the schedules are normal and the situation is not complex and not uncertain. |  |  |  |  |  |

Figure 13: Heuristics on the suitability of construction approaches.

ExamplesÊofÊriskÊreduction

The evolutionary construction approach can be used to reduce the risk of:

¥	Uncertain or unfeasible requirements to the IS-adaptation.

¥	Uncertain interfaces to other systems.

¥	Evolving requirements to the IS-adaptation.

¥	Unpredictable costs for the project.

¥	Delays in the delivery of products.

¥	Poor quality of the products.

¥	Increased costs of the project.

¥	Integration problems.

¥	Shortfalls in non-functional properties.

¥	Straining computer science capabilities.

¥	Developing a wrong or unfeasible information system.

The incremental construction approach can be used to reduce the risk of:

¥	Loss of control of the project.

¥	Unpredictable costs for the organisation.

¥	Unpredictable costs for the project.

¥	Poor quality of the products.

¥	Increased costs of the project.

¥	Integration problems.

¥	Shortfalls in non-functional properties.

### 5.2.3.	DescriptionÊapproach

A system description approach provides the primary mode of operation to be followed in producing a system description, including determination of requirements, and the primary co-operation approach required between the project actors and the actors of the information system. System description includes the determination of requirements.

The  used in producing the system descriptions is the way in which information is processed in order to make the project's design decisions.

The  is the way in which project actors work together with the actors of the information system during the system description task.

The choice of a system description approach always places requirements onto both the deliverables that are exchanged within customer-supplier transactions, and onto the methods and techniques used in the IS-production.

The rest of this chapter explores how a suitable system description approach for an IS-adaptation can be defined.

DescriptionÊapproachÊoptions

The customer and supplier should choose among the four following options for the combination of mode of operation and co-operation approach:

¥	Strategy options

1.	Analytical mode of operation and expert-driven co-operation approach.

2.	Analytical mode of operation and participatory co-operation approach.

3.	Experimental mode of operation and expert-driven co-operation approach.

4.	Experimental mode of operation and participatory co-operation approach.

HeuristicsÊonÊtheÊsuitabilityÊofÊdescriptionÊapproaches

In practice, it will generally not be the case that one of the options alone can be applied. Generally, there are cases where the chosen approach will be combined with one of the others.

¥	Strategy heuristics

It is therefore the primary mode of operation that should be defined as part of the IS-adaptation strategy. The suitability of the primary mode of operation depends on the complexity and uncertainty of the project. In principle:

×	Analytical mode of operation is suitable when the situation is mainly complex.

×	Experimental mode of operation is suitable when the situation is mainly uncertain.

Relying on an analytical mode of operation to reduce complexity will introduce new sources of uncertainty which require experimental countermeasures, e.g. when reducing complexity by dividing into sub-systems, uncertainty is introduced regarding the interfaces between the sub-systems. Correspondingly, relying on an experimental mode of operation to reduce uncertainty will introduce new sources of complexity requiring analytical countermeasures, e.g. knowledge gained from prototyping must be analysed and transformed into requirements or specifications.

The suitability of a primary co-operation approach depends on an overall assessment of a combination of some specific situational factors; no single situational factor can enforce the choice of a particular co-operation approach:

×	An expert-driven approach can be suitable as a primary co-operation approach when the:

-	Heterogeneity of the actors is high.

-	Adequacy of the schedules is tight.

-	Ability of the actors of the information system is low.

In these cases, it may be suitable to keep the actors of the information system outside the project team. The project actors in the project team can then elicit their knowledge through interviews, or equivalent techniques.

×	A participatory approach can be suitable as a primary co-operation approach when the:

-	Ability of the actors of the information system is high.

-	Attitude of the actors towards the IS-adaptation is negative.

-	Formality of the information is low.

-	Formality of the business processes is low.

-	Stability of the information and the business processes is low.

-	Specificity of the information system is high.

-	Complexity of the information is high.

-	Complexity of the business processes is high.

-	Importance of the organisational changes is high.

-	Importance of the technological changes is high.

-	Availability, clarity and stability of the requirements to the IS-adaptation is low.

In these cases, the actors in the information system may be used as project actors in the project team.

In general, it can be concluded that:

×	An analytical and expert-driven description approach can be suitable when the situation is complex, except when the complexity of the information or the business processes is high.

×	An analytical and participatory description approach can be suitable when the complexity of the information or business processes is high.

×	An experimental and expert-driven description approach can be suitable when the situation is uncertain and participatory co-operation is not suitable.

×	An experimental and participatory description approach can be suitable when the situation is uncertain and the ability of the actors of the information system is sufficiently high and the adequacy of the schedules is normal.

×	An expert-driven approach can be more simple to plan and control than a participatory approach. A participatory approach can be easier to control when an evolutionary installation approach is used. That is:

The description, construction, installation, and project control approaches are interdependent.

ExamplesÊofÊriskÊreduction

The analytical  can be used to reduce the risk of:

¥	Uncertain interfaces to other systems.

¥	Delays in the delivery of the products.

¥	Poor quality of the products.

¥	Increased costs of the project.

The experimental mode of operation can be used to reduce the risk of:

¥	Uncertain or unfeasible requirements to the IS-adaptation.

¥	Unpredictable costs for the project.

¥	Shortfalls in non-functional properties.

¥	Straining computer science capabilities.

¥	Developing a wrong or unfeasible information system.

The expert-driven  can be used to reduce the risk of:

¥	Uncertain or unfeasible requirements to the IS-adaptation.

¥	Delays in the delivery of the products.

¥	Poor quality of the products.

¥	Increased costs of the project.

The participatory co-operation approach can be used to reduce the risk of:

¥	Uncertain or unfeasible (conflicting) requirements to the IS-adaptation.

¥	Evolving requirements to the IS-adaptation.

¥	Unpredictable costs for the organisation.

¥	Lack of target domain actor-participation.

¥	Developing a wrong or unfeasible information system.

¥	IS-adaptation not accepted by (some) IS-actors.

## 5.3.	ProjectÊcontrolÊapproach

A project control approach is an approach taken regarding the frequency and formality of the project control measures, and the responsibility for performing them.

Remember: Project control is the set of processes concerned with monitoring the progress of the project, i.e. its direction, quality, and resource utilisation, as compared with project plans [EM-4-ED].

The guidance on the choice of project control approach is based on the options defined in the Strategy Model, see Figure 14.

| Project control approach | Strategy options |
| --- | --- |
| ¥ Development control ¥ Quality control ¥ Configuration control | 1. Frequency: frequent or seldom. 2. Formality: degrees of formality. 3. Customer responsibility: different kinds of responsibility. |

Figure 14: Strategy options for a project control approach.

Project control may be split among the three work areas: IS-development, quality assurance and configuration management, defined by Euromethod. In accordance with this, three project control processes are distinguished:

¥	Work areas

1.	Development control;:

The project management process necessary to control the project tasks performed within the IS-development work area.

2.	Quality control:

The techniques and activities that are used to fulfil the quality requirements. Quality control involves techniques and activities aimed at both monitoring a process and eliminating the causes of unsatisfactory performance at all stages of the quality loop in order to achieve economic effectiveness.

3.	Configuration control:

This is an element of configuration management, which consists of the evaluation and co-ordination, approval or disapproval, and implementation of changes to configuration items after the formal establishment of their configuration item identification.

ProjectÊcontrolÊapproachÊoptions

The customer and supplier should choose among the following options regarding the three aspects of the project control:

¥	Strategy options

¥	Frequency:

The frequency of customer-supplier transactions within the control process.

Options: Frequent or seldom.

¥	Formality:

The degree of formality within organisation, procedures and disciplines used by the control process.

Options: Degrees of formality with the extremes formal and informal.

¥	Customer responsibility:

The definition of customer responsibility within project control. Generally, it is assumed that the supplier is responsible for all aspects of the project control, unless the customer responsibility is explicitly defined in the contract.

Options: Different kinds of customer responsibility.

High degree of formality in project control can contain for example:

¥	Periodical approvals of status and plan.

¥	Well-defined requirements on the content of management reports.

¥	Well-defined target domain deliverables with deadlines and defined approval procedures.

¥	Use of defined metrics for project progress and quality.

¥	Use of a defined inspection technique in quality control of code.

¥	Well-defined configuration control procedures.

The responsibility of the customer can be defined as, for example:

¥	The customer is responsible for the configuration control of requirements.

¥	The customer is responsible for the quality control of descriptions with respect to requirements and business needs.

¥	The customer is responsible for the generation of test cases that cover critical situations from the business process perspective.

¥	The customer is responsible for preparing the organisation for the installation of the new operational information system.

¥	The customer is responsible for obtaining any agreements within the organisation, regarding the adoption of the requirements to the information system.

HeuristicsÊonÊtheÊsuitabilityÊofÊprojectÊcontrolÊapproaches

This checklist provides heuristics regarding which situational factors are addressed by the use of a particular project control approach.

¥	Strategy heuristics

Frequency

×	Frequent development control is suitable when the situation is uncertain, especially when the:

-	Adequacy of schedules is tight.

-	Adequacy of budget is tight.

-	Importance of organisational changes is high.

-	Quality of existing specifications is low.

-	Novelty of IS-adaptation is high.

×	Frequent development and quality control is suitable when the:

-	Strategic importance of the information system is high.

-	Importance of technological changes is high.

-	Dependency of sub-contractors is high.

-	Dependency of other IS-adaptations is high.

-	Capability of the project team is low.

-	Availability of the development technology is low.

-	Novelty of the development technology is high.

-	Complexity of the development technology is high.

×	Frequent development and configuration control is suitable when dependencies are high or the stability is low, i.e. when the:

-	Dependency of sub-contractors is high.

-	Dependency of other IS-adaptations is high.

-	Stability of information and business processes is low.

-	Stability of environment is low.

-	Availability, clarity and stability of requirements to the IS-adaptation is low.

Formality

×	High degree of formality in development control is suitable when the situation is complex or uncertain.

×	High degree of formality in development control is suitable when an evolutionary installation approach is used.

×	High degree of formality in quality control is always suitable, but the procedures that are applied can be more or less complex dependent upon the size of the project.

×	High degree of formality in configuration control is suitable when the stability is low or the situation is complex, i.e. when the:

-	Stability of information and business processes is low.

-	Stability of the environment is low.

-	Availability, clarity and stability of the requirements to the IS-adaptation is low.

-	Size of distribution of the information system is high.

-	Complexity of information or business processes is high.

-	Complexity of computer system factors are high, especially complexity regarding maintainability and many replications of the computer system.

-	Complexity of project actors and project structure is high.

CustomerÊresponsibility

×	It is suitable to define the customer's responsibility in project control, when the target domain factors imply an uncertain situation and the customer ability is sufficiently high. For example regarding the:

-	Handling of attitudes among actors, when the:

¡	Attitude of actors is negative.

-	Provision of knowledge and in decision making, when the:

¡	Formality of information or business processes are low.

¡	Stability of information or business processes are low.

¡	Stability of environment is low.

¡	Specificity of information system is high.

¡	Understandability of existing system is low.

×	It is suitable to define the customer's responsibility in development and quality control regarding the:

-	Handling of conflicts and organisational changes in the target domain, when the:

¡	Heterogeneity of actors is high.

¡	Importance of organisational changes is high.

-	Provision of knowledge and in decision making, when the:

¡	Strategic importance of the information system is high.

¡	Availability, clarity and stability of requirements to the 	IS-adaptation is low.

¡	Novelty of IS-adaptation is high.

×	It is suitable to define the customer's responsibility in configuration control regarding the:

-	Control of changes of requirements, when the:

¡	Stability of information and business processes is low.

¡	Availability, clarity and stability of requirements to the 	IS-adaptation is low.

¡	Size of distribution of information system is high.

-	Provision of knowledge and in decision making, when the:

¡	Stability of environment is low.

ExamplesÊofÊriskÊreduction

The following heuristics provide proposals for project control approaches that will achieve a reduction of the risks associated to the uncertainty of a situation, i.e. a reduction of the probability of the occurrence of any adverse consequences:

×	When there is a risk of uncertain or unfeasible requirements to the IS-adaptation:

=>	Use development and quality control formally with defined customer responsibility, in particular regarding the responsibilities of the customer in handling conflicts or in the description of requirements.

×	When there is a risk of evolving requirements, e.g. there are continuous changes to requirements:

=>	Use development, quality and configuration control which is both frequent and formal with defined customer responsibilities, in particular regarding the responsibilities of the customer in configuration control of requirements descriptions.

×	When there is a risk of lack of target domain actor participation:

=>	Use development and quality control which is both frequent and formal with defined customer responsibilities, in particular regarding the responsibilities of the customer in involving the appropriate actors.

×	When there is a risk of shortfalls in externally performed tasks:

=>	Use development, quality and configuration control which is both frequent and formal. Here, there is no need for the customer responsibility to be defined, because the customer is not involved in the relationships to the supplier's sub-contractors.

×	When there is a risk of system integration problems:

=>	Use development, quality and configuration control which is both frequent and formal with defined customer responsibilities, in particular regarding the responsibilities of the customer in coordination of IS-adaptations.

×	When there is a risk that the IS-adaptation is not accepted by some actors:

=>	Use development and quality control which is both frequent and formal with defined customer responsibilities, in particular regarding the responsibilities of the customer in handling negative attitudes among the actors.

## 5.4.	RiskÊmanagement

In this section, more specific heuristics on how to manage the complexity and uncertainty in a situation are provided. The heuristics make proposals for approaches, decision points and resources that should be considered in the definition of an IS-adaptation strategy.

Typically, the resolution of complexity related risks is concerned with a single situational factor, whereas the resolution of uncertainty related risks consider a combination of situational factors. Therefore, the heuristics for managing complexity are related to individual situational factors whereas the heuristics for managing uncertainty are related to the risks caused by the uncertainty in a particular situation.

### 5.4.1.	Complexity

In the assessment of the problem situation, values have been assigned to the situational factors. The following list of heuristics can be used in the analysis of those complexity factors which have been recognised to imply complexity in the problem situation:

×	When the heterogeneity of actors is high:

=>	Define the customer's responsibility for taking the different interests of the actors into account, e.g. through interviews, questionnaires, meetings and by adopting a participatory description approach.

×	When the size of the target domain is large:

=>	Split the IS-adaptation into IS-adaptations with smaller target domains.

×	When the complexity of information found within the information system is high:

=>	Use the business information view in the IS-descriptions to support early decisions regarding the business information.

=>	Use IS-expertise with a high level of skills in this application domain.

×	When the complexity of business processes in the information system is high:

=>	Use the business process view in IS-descriptions to support early decisions regarding the business processes.

=>	Use IS-expertise with high level of skills in this application domain.

×	When the information system is distributed over a wide geographical area, i.e. the size of distribution is large:

=>	Use an installation approach characterised by progressive steps in the geographical coverage of the resulting information system.

×	When there are many external interfaces to other information systems:

=>	Clarify the interfaces early in the description process and describe them in IS-descriptions.

=>	Test the external interfaces carefully.

=>	Produce plans for the necessary changes to each external information system that is involved in the IS-adaptation.

=>	Plan the construction, test and installation of the interfaces in coordination with the people responsible for the external information systems that are involved in the IS-adaptation.

×	When the complexity of non-functional properties is high:

=>	Approve requirements statements of non-functional properties within early decision points during the IS-production.

=>	Make early decisions on the trade-off between the functional properties and non-functional properties.

×	When there are many replications of the computer system:

=>	Use formal configuration control, e.g. use an automated control system in a disciplined way, using trained resources.

×	When the project size is large, i.e. the amount of development effort required is considerable for the organisations involved:

=>	Split the IS-adaptation into several IS-adaptations, each defined by a contract.

×	When the complexity of the migration is high, i.e. the amount of effort and complexity in migrating from the initial state information system to the final state information system is high:

=>	Manage the migration in steps with defined intermediate interfaces to the existing operational information system.

=>	Use a formal project control approach.

×	When there are many sub-contractors:

=>	Use formal and frequent development and quality control approaches in relation to the sub-contractors.

×	When there are many interfaces to other IS-adaptations:

=>	Plan the IS-adaptation in coordination with the people responsible for these other IS-adaptations.

=>	Clarify the interfaces (external system interfaces, migration interfaces, etc.) early in the IS-adaptation process and describe them in IS-descriptions and plans.

=>	Report on these interfaces at the approval of status and plan transactions.

×	When there are many project actors:

=>	Use formal and frequent project control approaches with a defined project organisation. In particular responsibilities should be defined for each actor.

×	When the complexity of the technology is high:

=>	Use safe, well-known and mature technology,

=>	Use IS-expertise with high level of technical skills.

### 5.4.2.	Uncertainty

The following heuristics provide proposals for approaches that will achieve a reduction of the risks associated to the uncertainty of a situation, i.e. a reduction in the probability of the occurrence of any adverse consequences:

×	When there is a risk of unfeasible requirements to the IS-adaptation:

=>	Create or utilise a good understanding of the existing information system.

=>	Make early decisions on requirements statements, prototypes and specifications of the future information system.

=>	Use a participatory description approach.

=>	Gather experiences obtained from similar information systems.

×	When there is a risk of evolving requirements to the IS-adaptation:

=>	Use frequent and formal development, quality assurance and configuration management approaches.

=>	Pay considerable attention to the design and construction of an adaptable information system, i.e. the quality plan should contain quality criteria on adaptability.

=>	Use an evolutionary approach to construction and installation.

×	When there is a risk of unpredictable costs for the organisation:

=>	Decrease the uncertainty regarding costs by having decision points in the delivery plan concerning the costs early in the IS-adaptation.

×	When there is a risk of poor quality of the products, e.g. which could result in a bad commercial impact:

=>	Use a formal and frequent quality control approach.

×	When there is a risk of shortfalls in the non-functional properties:

=>	Manage the traceability of requirements to non-functional properties.

=>	Use IS-expertise with high level of technical skills.

=>	Make prototypes for the simulation of the non-functional properties.

×	When there is a risk of developing an unfeasible information system:

=>	Verify as soon as possible that the functionality of the future information system will be as good as the functionality of the existing information system, i.e. requirements to the sequence, purposes and deliverables of decision points.

=>	Produce requirements statements, prototypes and specifications of the future information system.

=>	Use a participatory description approach.

=>	Gather experiences obtained from similar information systems.

=>	Make prototypes for simulation of the information system properties.

×	When there is a risk that the IS-adaptation may not be accepted by actors:

=>	Create or maintain a positive attitude of the actors.

=>	Use a participatory description approach.

=>	Use an evolutionary installation approach.

=>	Make prototypes for simulation of work practice properties.

=>	Define customer responsibility within the project control approach.

# 6.	HowÊtoÊDefineÊDecisionÊPoints

| Purpose: | ¥ To establish a sequence of defined decision points at the contractual level. |
| --- | --- |
| Concepts: | ¥ Decision point, customer-supplier transaction, method process model. ¥ Decision point description (decision purpose, deliverable profiles, roles involved). ¥ Deliverable profile: target domain deliverable (deliverable type, considered system, information system view, computer system view, IS-property, non-functional property, deliverable scope, deliverable state, formality); project domain deliverable (deliverable type, work area, project property). |
| Principles: | ¥ Define decision points where deliverables are exchanged. ¥ Tailor the sequence of decision points to the situation. ¥ The sequence and contents of decision points should reflect the chosen IS-adaptation strategy. ¥ Define deliverables in method independent terms, i.e. Euromethod deliverable concepts. |
| Activities: | ¥ Define sequence of decision points. ¥ Define deliverable profiles related to decisions. ¥ Apply IS-development methods. |
| Results: | ¥ Definition of decision points (sequence, decision purpose, deliverable and method product profiles, roles involved). |
| Checklists: | ¥ Heuristics and examples on sequences of decision points. ¥ Heuristics on definition of deliverable profiles related to decisions. ¥ Use of method bridges and method process models. |
| Examples: | ¥ Case study examples, see the following index entries in [EM-2.5-CS]: Decision point (sequence of decision points, decision point description), deliverable profile. ¥ Annex A-C: Delivery plan examples |

Remember: A decision point within an IS-adaptation is a point in time where the customer, possibly together with the supplier, is making decisions on the IS-adaptation. A decision point is characterised by the decisions that are made, the roles involved in these decisions, the customer-supplier transactions that take place and thereby the deliverables that are exchanged. These deliverables serve as a basis for the decisions to be made.

A customer-supplier transaction within an IS-adaptation is an exchange of products (and services) between customer and supplier, in order to achieve a specified purpose, e.g. the making of decisions regarding the IS-adaptation. A customer-supplier transaction is characterised by its purpose and the deliverables that are exchanged [EM-4-ED].

Once the initial state, the final state and the IS-adaptation strategy are defined, it is possible to define a sequence of decision points that is tailored to the problem situation. The sequence and contents of decision points should reflect the chosen IS-adaptation strategy. This chapter provides guidance on how to define such decision points:

¥	Section 6.1 provides heuristics and examples on how to define decision points dependent on the chosen approaches to description, construction, installation and project control.

¥	Section 6.2 provides heuristics on how to define deliverable profiles related to decisions. Three type of decisions on the target domain are distinguished and elaborated further on: investment decisions, design decisions and system acceptance decisions.

¥	Section 6.3 provides an overview on how to use IS-development methods to define the decision points. The detailed guidance on this topic is provided in the Method Bridging Guide.

## 6.1.	SequenceÊofÊdecisionÊpoints

The sequence of decision points should reflect the chosen approaches to description, construction, installation and project control. This section provides heuristics and examples on how to define decision points dependent on the chosen approaches.

In defining a sequence of decision points, it is necessary to:

¥	Define the decision points for the information system or for each of the defined sub-systems (within the definitions of the initial state, the final state and the IS-adaptation strategy) and combine them into a single sequence of decision points addressing the whole IS-adaptation (see the EU-Rent examples in the Case Study document).

¥	Start by using the examples, found in this section, of sequences of decision points related to the chosen approaches for description, construction, installation and project control.

Then go through the detailed aspects of the approaches proposed in the IS-adaptation strategy. For each of the proposals in the IS-adaptation strategy, the decision points may be adapted by one or several of the following changes:

-	Define and add new decision points.

-	Change the sequence of decision points.

-	Change the contents of decision points, i.e. the decision purpose, the deliverable profiles or the roles involved.

### 6.1.1.	DescriptionÊapproach

The assumptions are:

¥	An important part of the IS-adaptation is to develop descriptions of a new or modified information system. The starting situation contains very few descriptions of a future information system.

This is similar to one of the following initial states (see Annex A in the Customer Guide): undocumented information system, documented information system, problem description.

¥	For analytical description approaches, the results should be:

Detailed requirements statements and specifications of all future information system and computer system properties.

This is similar to a combination of the detailed business design and the detailed technical design final states (see Annex A in the Customer Guide).

¥	For experimental description approaches, the results should be:

Prototypes, detailed requirements statements and specifications of the work practice and computer system architecture properties.

When the final state of an IS-adaptation only consists of a system description and doesn't include a new installed information system version, then most probably there will be a subsequent IS-adaptation. In this case, plans for a future IS-adaptation can be part of the final state.

The following guidance provides heuristics on how to define decision points dependent on the chosen description approach. In addition, it provides examples of possible sequences of deliverables for each type of description approach. The examples of decision points illustrate possible sequences of deliverables, defined by use of the deliverable concepts in the Deliverable Model. Figure 14 gives an overview of the heuristics regarding the definition of decision points.

¥	Deliverable concepts

| Description approach |  | Heuristics regarding decision points |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Mode of operation | Type of co-operation | Business setting vs. technical system | Abstract level vs. concrete level | Total solution vs. partial solution | Number of decision points |
| Analytical | Expert-driven | From business setting to technical system | From abstract to concrete | From total to partial | Minimal set |
|  | Participatory | From business setting to technical system | Abstract and concrete in parallel | Mainly from total to partial | Sufficient set |
| Experimental | Expert-driven | Business setting and technical system in parallel | From concrete to abstract | From total to partial | Minimal set |
|  | Participatory | Business setting and technical system in parallel | From concrete to abstract | Total and partial in parallel | Sufficient set |

Figure 14: Heuristics on how to define decision points depending on the description approach.

The examples of decision points are built on the following general heuristics regarding the deliverables that support the decisions:

×	Decisions on the business setting

are supported by the information system views.

×	Decisions on the technical system

are supported by the computer system views.

×	Decisions on an abstract level

are supported by the actor independent information system views (business information and business process views) and the processing unit independent computer system views (computer system data and computer system function views).

×	Decisions on a concrete level

are supported by the work practice and the computer system architecture views.

×	Decisions on a total solution

are supported by a full deliverable scope and a global development state, i.e. neither a high degree of decomposition nor a high degree of specialisation.

×	Decisions on a partial solution

are supported by a partial deliverable scope and a detailed development state, i.e. high degree of decomposition and high degree of specialisation.

AnalyticalÊandÊexpert-drivenÊdescriptionÊapproach

×	When the approach to description is analytical and expert driven, the following heuristics in defining decision points should be applied:

=>	Go from decisions on the business setting to decisions on the technical system.

=>	Go from decisions on an abstract level to decisions on a concrete level.

=>	Go from decisions on total solution to decisions on partial solutions.

=>	Define the minimal set of decision points needed for the customer to make proper decisions.

| Example | Analytical and expert-driven description: 1. Approval of global business requirements statements and specifications. 2. Approval of global work practice requirements statement and specification. 3. Approval of global computer system requirements statements and specifications. 4. Approval of detailed information system requirements statements and specifications. 5. Approval of detailed computer system requirements statements and specifications. |
| --- | --- |

In this example, based on an analytical approach, the focus is on making specifications of a future information system and the decision points are defined:

¥	Starting with the description of business information and business process views (actor independent abstract views) of the future information system, then being more concrete and taking the actors, including the man-machine interfaces, into account through a work practice view, and finally specifying the future computer system through data, function and architecture views.

¥	Information system views and computer system views

¥	Starting with requirements to the total information system and computer system, and ending with requirements to the individual parts of a solution.

¥	Supporting the minimal set of transactions needed to support the customers decision making.

This sequence of decision points requires IS-expertise in the customer organisation with a high level of abstraction skills and with good knowledge regarding the modelling techniques used by the supplier. The customer's IS-expertise is especially necessary to support the customer decisions regarding the information system views.

AnalyticalÊandÊparticipatoryÊdescriptionÊapproach

×	When the approach to description is analytical and participatory, the following heuristics in defining decision points should be applied:

=>	Go from decisions on the business setting to decisions on the technical system.

=>	Make decisions on an abstract level in parallel with decisions on a concrete level.

=>	Go mainly from decisions on a total solution to decisions on partial solutions.

=>	Define sufficient decision points to support continuous customer-supplier interaction.

| Example | Analytical and participatory description: 1. Approval of global work practice requirements statement and specification. 2. Approval of global business requirements statements and specifications. 3. Approval of global computer system requirements statements and specifications. 4. Approval of global computer system data and function requirements statements and specifications. 5. Approval of detailed information system requirements statements and specifications. 6. Approval of detailed computer system requirements statements and specifications. |
| --- | --- |

In this example, the actors in the information system are involved directly in the description process through a participatory approach and the decision points are defined:

¥	Starting with a description of a work practice view (actor dependent concrete view) of the future information system. The production of descriptions can start with a work practice view on the existing information system, but there is not necessarily a decision point at the contractual level related to this part of the production process.

An analytical approach is chosen, which means that the actors are capable of making abstractions, at first through the business information and business process views and, after a computer system architecture view, through the computer system data and function views.

¥	Starting with requirements to the total information system and computer system, and ending with requirements to the individual parts of a solution.

¥	Supporting the sufficient set of transactions needed to support continuous customer-supplier interaction.

It is assumed that the participatory approach requires one more decision point than the expert-driven approach, because it may be more difficult to get consensus regarding the contents of the IS-descriptions. (But the commitment in the customer organisation can be better, which may facilitate the acceptance of the IS-adaptation by the actors in the information system).

ExperimentalÊandÊexpert-drivenÊdescriptionÊapproach

×	When the approach to description is experimental and expert driven, the following heuristics in defining decision points should be applied:

=>	Make decisions on the business setting in parallel with decisions on the technical system.

=>	Go from decisions on a concrete level to decisions on an abstract level.

=>	Go from decisions on a total solution to decisions on partial solutions.

=>	Define the minimal set of decision points needed for the customer to make proper decisions.

| Example | Experimental and expert-driven description: 1. Approval of global work practice prototype. 2. Approval of global work practice requirements statement and specification. 3. Approval of global computer system prototype. 4. Approval of detailed work practice prototype. 5. Approval of detailed computer system prototype. |
| --- | --- |

In this example, based on an experimental approach, the focus is on making prototypes of a future information system, i.e. the focus is on the computer system, the man-machine interfaces and the manual processes supported by the computer system. The decision points are defined:

¥	Starting on a concrete level with decisions related to the work practice view. The properties simulated by the prototype depend on the situation. Not all properties should be simulated in any situation.

The sequence of decision points can be extended with decisions on the basis of more versions of the prototypes. It is recommended to plan the purposes of the prototypes carefully and to limit the prototyping in time, otherwise there is a risk of increased project costs.

¥	Starting with requirements to the total information system and computer system, and ending with requirements of the individual parts of a solution.

It is assumed that the requirements statements are produced in parallel with the production of the prototypes and that some specifications are made. The final result should contain detailed specifications of the work practice and computer system architecture properties, which together with the prototypes are a basis for the construction of a new information system.

¥	Supporting the minimal set of transactions needed to support the customers decision making.

ExperimentalÊandÊparticipatoryÊdescriptionÊapproach

×	When the approach to description is experimental and participatory, the following heuristics in defining decision points should be applied:

=>	Make decisions on the business setting in parallel with decisions on the technical system.

=>	Go from decisions on a concrete level to decisions on an abstract level.

=>	Make decisions on a total solution in parallel with decisions on partial solution.

=>	Define sufficient decision points to support continuous customer-supplier interaction.

| Example | Experimental and participatory description: 1. Approval of global and partly detailed work practice prototype. 2. Approval of global and partly detailed work practice requirements statement and specification. 3. Approval of global and partly detailed computer system prototype. 4. Approval of global and partly detailed computer system requirements statements and specifications. 5. Approval of detailed work practice prototype. 6. Approval of detailed computer system prototype. |
| --- | --- |

In this example based on an experimental approach, the actors in the information system are involved directly in the experiments through a participatory approach. The decision points are defined:

¥	Starting at a concrete level with decisions related to the work practice view.

¥	Starting with requirements to both the total information system and computer system and some individual parts of a solution, and ending with requirements to all the individual parts of a solution.

¥	Supporting the sufficient set of transactions needed to support continuous customer-supplier interaction.

It is assumed that the participatory approach requires one more decision point than the expert-driven approach, because it may be more difficult to get consensus regarding the contents of the IS-descriptions.

### 6.1.2.	ConstructionÊapproach

The assumptions regarding the starting situations are explained in relation to each example. In all the examples, the results should be:

¥	A new information system version which has been tested.

¥	Detailed requirements statements and specifications of the work practice and computer system architecture properties of the tested information system.

These results are similar to a tested information system final state (see Annex A in the Customer Guide).

When the final state of an IS-adaptation only consists of a new information system version which is tested but not yet installed, then most probably there will be a subsequent IS-adaptation. In this case, plans for a future IS-adaptation can be part of the final state.

| Example | One shot construction: The starting situation should be similar to either a detailed technical design state or the end of an experimental production of descriptions. That is, detailed requirements statements of a future information system and detailed specifications of either all the properties of the information system or only the work practice and computer system architecture properties. Decision points after approval of detailed requirements statements and specifications: ¥ Approval of tested information system. |
| --- | --- |

This example of decision points is very simple, because the one shot construction approach is only suitable in situations which are not complex and not uncertain.

In an IS-adaptation, a one shot construction will often be preceded by a production of descriptions with one of the above mentioned sequences of decision points and followed by a one shot or an incremental installation process with the decision points described in the following. The sequence of decision points for the whole production process will be a combination of those sequences of decision points.

| Example | Incremental construction: The starting situation should be similar to either a detailed technical design state or the end of an experimental production of descriptions. Decision points after approval of detailed requirements statements and specifications: ¥ For each part: - Approval of acceptance test of that part. ¥ Approval of tested information system. |
| --- | --- |

| Example | Evolutionary construction: The starting situation should be similar to a global design state or an intermediate decision point of a production of descriptions. Decision points after approval of global requirements statements and specifications: ¥ For each version: 1. Approval of detailed information system and computer system requirements statements and specifications of that version. 2. Approval of acceptance test of that version. ¥ Approval of final acceptance test. |
| --- | --- |

### 6.1.3.	ConstructionÊandÊinstallationÊapproach

It is assumed that the IS-adaptation consists of both construction and installation. It is very seldom to have a separate IS-adaptation (and contract) for an installation without any kind of construction. Therefore, the examples of decision points for installation approaches are combined with the decision points for the relevant construction approaches.

The assumptions regarding the starting situations are explained in relation to each example. In all the examples, the results should be:

¥	A new information system which is installed.

¥	Detailed requirements statements and specifications of the work practice and computer system architecture properties of the installed information system.

| Example | Construction followed by a one shot installation: The starting situation should be similar to either a detailed technical design state or the end of an experimental production of descriptions. The construction can be either a one shot, an incremental or an evolutionary construction. Decision points: ¥ Decision points in the construction process (see above). ¥ Approval of installed information system. |
| --- | --- |

| Example | One shot construction followed by incremental installation: The starting situation is always similar to either a detailed technical design state or the end of an experimental production of descriptions. Decision points after approval of detailed requirements statements and specifications: ¥ Approval of final acceptance test of the total information system. ¥ For each part: - Approval of installation of that part. ¥ Approval of installed information system. |
| --- | --- |

| Example | Incremental construction and installation: The starting situation should be similar to either a detailed technical design state or the end of an experimental production of descriptions. Decision points after approval of detailed requirements statements and specifications: ¥ For each part: 1. Approval of acceptance test of that part. 2. Approval of installation of that part. ¥ Approval of installed information system. |
| --- | --- |

| Example | Evolutionary construction and installation which will include a description of the detailed design of a future information system: The starting situation should be similar to a global design state or an intermediate decision point of a production of descriptions. Decision points after approval of global IS-descriptions: ¥ For each version: 1. Approval of detailed IS-descriptions of that version. 2. Approval of acceptance test of that version. 3. Approval of installation of that version. ¥ Approval of installed information system. |
| --- | --- |

### 6.1.4.	ProjectÊcontrolÊapproach

The decision points derived from the chosen project control approach are related to the approval of project status and plan transactions. The frequency of those transactions and the contents of the plans and reports exchanged depend on the choice of project control approach. Very often those transactions are combined with approval of deliverables and approval of final deliverables transactions. The delivery plan examples in Annex A-C contain examples of such combinations of transactions at a decision point.

### 6.1.5.	CombinedÊapproach

Examples of decision points for the following combined approaches are provided in Annex A-C:

A.	A combined one shot approach from a problem description to an installed information system:

-	Analytical and expert-driven description.

-	One shot construction.

-	One shot installation.

-	Frequent project control and high degree of formality.

B.	A combined incremental approach from a problem description to a tested information system:

-	Experimental and expert-driven description.

-	Incremental construction (three parts).

-	Frequent project control and high degree of formality.

C.	A combined evolutionary approach from a global design to an installed information system:

-	Experimental and participatory description.

-	Evolutionary construction and installation (three versions).

-	Frequent project control and high degree of formality.

## 6.2.	DeliverableÊprofilesÊrelatedÊtoÊdecisions

Several types of decision may be made in an IS-adaptation. In a decision point, several decisions may be taken, each one belonging to a different type.

The types of deliverables which are used in making a decision depend on its type. Therefore, it is useful to characterise a decision purpose in terms of its type because it gives some guidance on which deliverables are necessary to make the decision.

The basic rule to determine what deliverables are required for a decision is the following:

The deliverables must contain the right information to make the decision but no more than that; too much information costs money in its production and overloads the decision makers.

The two major decision types are:

¥	Decisions on the target domain of the IS-adaptation, i.e. on the information system which is subject to the adaptation.

¥	Decisions on the project domain, i.e. on the organisation and the plans to perform the work.

Decisions of the first type mainly require target domain deliverables (requirements statements, specifications, prototypes), although sometimes project domain deliverables may be useful (e.g. delivery plans and development reports allowing to assess costs and risks related to the IS-adaptation).

Decisions of the second type mainly require project domain deliverables (project plans and reports), although sometimes target domain deliverables may also be useful.

The decisions on the target domain may be distinguished in three sub-types:

¥	Investment decisions.

¥	Design decisions.

¥	System acceptance decisions.

These types of decisions are now considered.

### 6.2.1.	InvestmentÊdecisions

An investment decision determines whether to invest or not in a new (or modified) information system. Investment decisions are usually part of the overall decision to go to an IS-adaptation. However, they may also be part of the production process: this means that the initial investment decision is reviewed or refined on the basis of the additional information gained during the production process. Another case is when the IS-adaptation aims at providing the information necessary to make an investment decision (strategic planning, change analysis, etc.).

The key elements input to an investment decision are:

¥	The feasibility:

Is the IS-adaptation organisationally and technically feasible within the technological state-of-the-art?

¥	The benefits:

What is the benefit brought by the new information system?

This may be assessed in terms of new market opportunities, competitive advantage, improved quality of a service or product, better management, more efficient operation, reduced organisational costs, improved working conditions for the actors of the information system, etc.

¥	The costs:

What are the costs of the IS-adaptation, e.g. costs of the hardware and software, construction costs, installation costs, etc.?

¥	The risk:

What are the risks involved in the IS-adaptation (see Section 4.3)?

¥	The delivery plan:

The complete delivery plan is not necessarily required, but some key dates must be known like the date when the major sub-systems become available.

¥	The IS-properties,

which support the assessment of feasibility, benefits, costs, risks and plans.

Typically, the deliverable profile for an investment decision will contain the:

¥	IS-properties,

¥	Views and IS-properties

which support the assessment of feasibility, benefits, costs, risks and plans; these IS-properties must address all the views that have an influence on these elements, namely the views that will show a change between the current and the future information system. Examples:

-	If the business processes are going to change, then the new business processes will likely impact on the benefits, costs, etc. and the business process view must be addressed.

-	If the computer system architecture is going to change, then the computer system architecture will likely impact on the benefits, costs, etc. and the computer system architecture view must be addressed.

In general, the  of the deliverable does not need to be detailed: a global view (low degree of decomposition, low degree of specialisation) is sufficient to assess the benefits, costs, risks, etc. However, in some cases it is needed to have a deeper insight into those parts of the system which are considered critical, complex or uncertain. For those parts, more detail is needed in the IS-descriptions; the right level of detail is the one which makes it possible to make the investment decision.

¥	Deliverable state and deliverable scope

The  must also be tailored to the decision to be made: the ultimate consistency, accuracy or completeness is usually not required for investment decisions. As for the deliverable:~ scope, it must be full scope, unless a representative part of the system can be used to assess the benefits, costs, risks, etc.

¥	Non-functional properties:

¥	Non-functional properties

Costs, benefits, and any other non-functional properties which have a major impact on feasibility, benefits, cost and risk. These can be requirements to efficiency, security, maintainability, etc.

¥	Delivery plan:

The complete delivery plan is often not required; it is often needed to make an overall assessment of risks, to specify the installation approach and to specify some key dates like the dates of availability of the major sub-systems.

The deliverables which are input to investment decisions always address a future information system. However, sometimes deliverables addressing the  may be introduced. These deliverables may be used for the following purpose:

¥	Assessing whether the understanding of the current information system is correct.

¥	Serving as a baseline to express the changes to the information system.

¥	Justifying proposals for changes by a diagnosis of the current information system.

¥	Comparing the future information system with the current one and ensuring that there is an improvement.

Besides these purposes, there is no justification for introducing a deliverable concerning the current system as input to an investment decision, even if its production is planned by a development method.

### 6.2.2.	DesignÊdecisions

A design decision determines whether a new (or modified) information system is acceptable as it is described. The deliverables input to this type of decision are IS-descriptions. The type of IS-description (requirements statement, specification, prototype) depends on the approach as shown in Section 6.1.

These IS-descriptions may potentially address all the views and all the non-functional properties. The ,  and deliverable  depend on the nature of the decision and its position in the sequence of decisions of the delivery plan. The quality procedures to be applied are usually more elaborated than for investment decisions; the final specifications must be correct, accurate, consistent and complete. Project reports can be used to assess this.

Section 6.1. gives heuristics and examples on sequences of decision points. From the characterisation of the decisions made in those decision points, it is possible to derive the required deliverable profile.

Methods also propose standard process models and products to support decisions (see Section 6.3).

The following guidance assists in making the link between a decision and the required deliverable profiles:i.deliverable:~ profile

×	If the decision concerns the changes in the business and the information resources supporting the business,

=>	then the deliverable profile will address the business information and business process views.

×	If the decision concerns the changes in the organisation, the working practices, the roles of the actors, the computerisation of the tasks, the human computer interface,

=>	then the deliverable profile will address the work practice view.

×	If the decision concerns the computerised data (e.g. which part of the information is computerised),

=>	then the deliverable profile will address the computer system data view.

×	If the decision concerns the computerised function (e.g. how are the tasks computerised),

=>	then the deliverable profile will address the computer system function view.

×	If the decision concerns the computer system (e.g. what is the architecture, the hardware, the software),

=>	then the deliverable profile will address the computer system architecture view.

The deliverables which are input to design decisions always address a future information system. However, sometimes deliverables addressing the current information system may be introduced. These deliverables may be used for the following purpose:

¥	Assessing whether the understanding of the current information system is correct.

¥	Serving as a baseline to express the changes to the information system.

¥	Justifying proposals for changes by a diagnosis of the current information system.

¥	Comparing the future information system with the current one and ensuring that there is an improvement.

Besides these purposes, there is no justification for introducing a deliverable concerning the current system as input to a design decision, even if its production is planned by a development method.

In addition to IS-descriptions, it is usual to require quality assurance reports showing the results of the quality control applied to the IS-descriptions. Quality control procedures may control the correctness, accuracy, completeness, consistency, traceability to requirements, etc. according to the plans.

¥	Project domain deliverables

### 6.2.3.	SystemÊacceptanceÊdecisions

There are two types of system acceptance decisions:

¥	Decision to accept a constructed and tested information system.

¥	Decision to accept an installed and operational information system.

These decisions need the operational items that are either tested or installed as input.

In addition, they need quality assurance reports showing the results of the tests of the constructed system or validations of the installed system. Configuration management reports may be required too. An up-to-date specification of the information system may also be required at this point, if it has not been produced and checked earlier.

## 6.3.	ApplyÊIS-developmentÊmethods

IS-development methods can be applied in delivery planning within the two scenarios of usage described in the chapter "What is method bridging" in the Method Bridging Guide:

¥	What is method bridging?

¥	Population of a Delivery Plan.

This scenario assumes that a delivery plan can be defined using the Delivery Planning Guide. The Method Bridging Guide is used to complete this delivery plan; by populating it with those products from the chosen IS-development method that are going to be delivered, as described in Section 6.3.1 "Apply method bridges".

¥	Derivation of decision points.

This scenario assumes that the supplier is in charge of proposing a delivery plan; and that this delivery plan will be based on the supplierÕs favoured IS-development method. The Method Bridging Guide is then used to derive the sequence of the decision points from the method products that the supplier intends to deliver and from the intended sequence of these deliveries using Euromethod concepts, as described in section 6.3.2 "Apply method process models".

A basic prerequisite in both of the scenarios outlined above is a documented bridging of the method products defined by the supplierÕs IS-development method to the concepts furnished by the Deliverable Model. This bridging is documented in method product profiles.

Remember: Using Euromethod, a delivery plan is always expressed in the same terminology. For any method which is applied in a particular IS-adaptation, the delivered method products are mapped to the required deliverable profiles of the delivery plan using method deliverable profiles. This facilitates the analysis of tender responses proposing different methods and also facilitates the expression of the IS-adaptation:~ requirements. [EM-4-ED]

Altogether there are three types of profiles:

¥	How to document method bridges

¥	Method product profiles.

¥	Method deliverable profiles.

¥	Required deliverable profiles.

Their particular purpose and use is described in the Chapter ÒHow to document Method BridgesÓ in the Method Bridging Guide.

### 6.3.1.	ApplyÊmethodÊbridges

The starting point for this method bridging scenario consists of a delivery plan: population of a ~ which contains descriptions of the initial state and the final state of the IS-adaptation and of the required deliverables at each decision point during the production process.

¥	How to populate a Delivery Plan

The Concepts Manuals provide the concepts necessary for describing a delivery plan. Using the Delivery Planning Guide, a delivery plan can be produced, which is adequate for the problem situation being addressed within a particular IS-adaptation.

This delivery plan can be provided by the customer at different levels of detail. However, in this scenario, we imagine that even if the customer provides an incomplete delivery plan within the IS-adaptation requirements of the Call for Tender document, the supplier would complete it using the Delivery Planning Guide.

As mentioned above, the descriptions of the required deliverables are based on the Deliverable Model. This means, the delivery plan contains the required deliverable profiles defining the IS-properties, non-functional properties and project properties which must be described by the method products that are to be exchanged between the customer and supplier during the production process.

Once the delivery plan is established, the required deliverable profiles need to be populated with method deliverables coming from the IS-development method used by the supplier. The supplier should describe the method products that will be delivered at each decision point to meet the requirements described in the required deliverable profiles. This activity can be supported by a method bridging dictionary, i.e. a set of method product profiles describing the products defined in the method manuals. This is described in the Chapter "How to populate a Delivery Plan" in the Method Bridging Guide.

### 6.3.2.	ApplyÊmethodÊprocessÊmodels

A delivery plan may not only be produced by following the guidance given by the Delivery Planning Guide, but the sequence of decision point:derivation of ~ss of a delivery plan might also be derived from the process model of the IS-development method applied by the supplier.

This scenario represents the case where the decision points and thus the deliverable profiles in the delivery plan are not identified on the basis of the Euromethod guidance, but are indeed defined on the basis of an IS-development method.

Remember: A method process model is a description of a class of processes for an IS-project proposed by a method. Commonly, the process model is used for a prescriptive purpose, i.e. to describe "how things must/should/could be done", in contrast to the process itself which is what really happens. Very often a method process model contains recommendations for the sequence of decision points within an IS-project [EM-4-ED].

In this scenario, the Method Bridging Guide is used by the supplier to populate the initial and final state of the IS-adaptation, which are defined in the Call for Tender document. Based on the knowledge of the method deliverables that constitute the initial and final state of the IS-adaptation, and based on the IS-development method used, the supplier can determine:

¥	How to derive decision points

¥	Which intermediate method products has to be produced.

¥	Which of these products constitute method deliverables for which customer approval is required. These will then be the subjects of decision points within the delivery plan.

The supplier can use method bridging to express these method deliverables using the Euromethod concepts and thus establish a complete, populated delivery plan.

Afterwards, with the help of the Delivery Planning Guide, customers, and also suppliers, can review and assess the adequacy of the proposed delivery plan:assessment of a ~ for the problem situation of a particular IS-adaptation.

# 7.	HowÊtoÊAssessÊaÊDeliveryÊPlan

| Purpose: | ¥ To assess whether a delivery plan is appropriate in the current situation. |
| --- | --- |
| Concepts: | ¥ Initial state, initial state profile, final state, final state profile. ¥ Situational factor, complexity, uncertainty, risk. ¥ IS-adaptation strategy, approaches to installation, description, construction and project control, risk management. ¥ Decision point, customer-supplier transaction, decision point description. ¥ Deliverable profile: target domain deliverable (deliverable type, considered system, information system view, computer system view, IS-property, non-functional property, deliverable scope, deliverable state, formality); project domain deliverable (deliverable type, work area, project property). |
| Principles: | ¥ Check that the IS-adaptation strategy applies to the situation. ¥ Check that the delivery plan is consistent with the IS-adaptation strategy. ¥ Check that the delivery plan is realistic and provides the customer with sufficient information to monitor the production process. |
| Activities: | ¥ Assess the quality of the problem situation description. ¥ Assess the suitability of the IS-adaptation strategy. ¥ Assess the suitability of the decision points. |
| Results: | ¥ Assessment of the delivery plan. |
| Checklists: | ¥ Requirements to the quality of the initial and final state profiles. ¥ Requirements to the suitability of the IS-adaptation strategy. ¥ Requirements to the suitability of the decision points. |
| Examples: | ¥ Case study examples, see the following index entries in [EM-2.5-CS]: Delivery plan, initial state, final state, situational factor, risks, IS-adaptation strategy, decision point, deliverable profile. ¥ Annex A-C: Delivery plan examples. |

The guidance on making a delivery plan can be used as guidance on the assessment of a delivery plan as well. In general, an assessment of a delivery plan consists of the same activities as the production of a delivery plan. The only difference is that you have a proposal at the beginning of the activity. For example:

¥	The guidance on the assessment of a problem situation is also relevant as guidance on the assessment of a delivery plan. An understanding of the problem situation is essential for assessing the suitability of a delivery plan and assessing the justification of the IS-adaptation strategy and the decision points.

¥	The heuristics for defining a suitable IS-adaptation strategy can be considered as heuristics for the assessment of the suitability of a chosen IS-adaptation strategy within a delivery plan.

¥	The guidance on checking the consistency of the description of decision points can be used as guidance on the assessment of the decision points within a delivery plan.

The assessment of the context of a delivery plan within an initial state is not covered in this guide.

Remember: The initial state of an IS-adaptation is the state of the information system and the available knowledge on it, at the beginning of the production process, i.e.:

¥	The initial state information system, i.e. the operational items 	contained in the operational information system.

¥	The operational items of a future information system that are available to 	the IS-production process (they have been constructed but are not yet 	installed and part of the operational information system).

¥	And the IS-adaptation requirements, i.e.:

-	The IS-descriptions that are available to the production process; 
		this can include both IS-descriptions of the initial state information 		system and IS-descriptions of a future information system.

-	The delivery plan.

-	Possibly project plans (development plan, quality assurance plan, 		configuration management plan).

An assessment of the context of a delivery plan could include the following assessment of the consistency between the elements of an initial state:

¥	The project plans related to the considered IS-adaptation should be consistent with the delivery plan.

¥	The operational items that are available to the IS-production should be described in the IS-descriptions available for the IS-production. The operational items are either installed in the initial state information system, under construction or ready to be installed.

## 7.1.	QualityÊofÊproblemÊsituationÊdescription

This section provides a checklist for the requirements to the quality of the initial and final state profiles:

×	The IS-descriptions that should be available to the IS-production (part of the initial state) and the IS-descriptions that the customer wants to use after the termination of the IS-adaptation (part of the final state), should be described.

×	The initial state profiles should be in line with the contents and state of the existing IS-descriptions or the expectations to the contents and state of the IS-descriptions available at the start of the production process.

×	The required deliverable profiles within the final state profiles should be in line with the requirements and expectations of the customer.

×	The method deliverable profiles within the final state profiles should be documented and they should match the required deliverable profiles.

## 7.2.	SuitabilityÊofÊstrategy

This section provides a checklist for the requirements regarding the suitability of a chosen IS-adaptation strategy:

×	The IS-adaptation strategy should be adapted to the situation. The justification of the strategy should be described.

×	There should be internal consistency within the IS-adaptation strategy. For example, no contradictions between the approaches for description, construction and installation.

×	The assumptions regarding the initial state should be in line with the available IS-descriptions.

×	The IS-adaptation strategy should result in the required final state.

×	The approaches for description, construction, installation and project control should be suitable. This can be assessed according to the heuristics for defining the approaches, see Section 5.2.

×	The management of risks should be suitable. This can be assessed according to the heuristics for defining the management of risks, see Chapter 5.

## 7.3.	SuitabilityÊofÊdecisionÊpoints

This section provides a checklist for the requirements regarding the suitability of the defined decision points:

×	The decision points should be adapted to the situation and consistent with the described IS-adaptation strategy. A justification of that should be provided. This can be assessed using the heuristics for defining a sequence of decision points, see Section 6.1.

×	The purposes of the decision points should be understandable and adequate.

×	The deliverables that are necessary for making the decisions should be described using required deliverable profiles, i.e. using method independent terms.

×	The basis of the decisions, the deliverables, should be defined and be sufficient for supporting the decisions according to the purposes of the decisions. This can be assessed according to the heuristics for defining the deliverable profiles related to decisions, see Section 6.2.

×	There should be consistency between the purposes of the deliverables, transactions and decisions.

×	The proposed products, described by method deliverable profiles, should be documented and they should match the required deliverable profiles.

×	The proposed roles involved in the decision making should be appropriate, and be allocated to appropriate persons.

# Annexes

# A.	DeliveryÊPlanÊExample: -ÊOneÊshotÊapproach

#### A.1.	ProblemÊsituation

The customer has decided that the installation of a new version of the information system is to be performed by an external information system supplier. The goal of the IS-adaptation and the overall requirements to the schedules and budget for the IS-adaptation are described in a problem statement document.

#### A.1.1.	StartingÊpoint:ÊtheÊinitialÊstateÊofÊtheÊIS-adaptation

Problem description (see Annex A in the Customer Guide).

#### A.1.2.	Goal:ÊtheÊfinalÊstateÊofÊtheÊIS-adaptation

Installed information system (see Annex A in the Customer Guide).

##### A.1.3.	AppreciationÊofÊtheÊproblemÊsituation

¥	Complexity of situation: Moderate, but:

-	Heterogeneity of actors is high.

¥	Uncertainty of situation: Moderate, but:

-	Adequacy of schedules is tight.

-	Budget is tight.

¥	Critical risks of:

-	Delays in the delivery of products.

-	Poor quality of products.

-	Increased costs of the project.

#### A.2.	IS-adaptationÊstrategy

##### A.2.1.	ApproachÊtoÊchangeÊsituationalÊfactors

No specific approach to change situational factors.

##### A.2.2.	DevelopmentÊapproach

¥	Analytical and expert-driven description.

¥	One shot construction.

¥	One shot installation.

##### A.2.3.	ProjectÊcontrolÊapproach

¥	Frequent project control and high degree of formality.

¥	Defined customer responsibility.

The customer is, among other things, responsible for:

-	Clarifying the different interests of actors and for solving any conflicts.

-	Making the user-oriented quality control of IS-descriptions.

-	Producing user manuals, work instructions and job descriptions.

-	Preparing and performing the acceptance test.

-	Performing the migration of data.

-	Managing the installation except the technical implementation of the new computer system.

-	Maintaining the information system after installation.

##### A.2.4.	Risk management

The chosen approaches.

#### A.3.	DecisionÊpoints

The decision points are defined by use of the examples of sequence of decision points related to the chosen approaches. Each decision point contains decisions regarding the progress and direction of the IS-adaptation.

1.	Approval of global business requirements statements and specifications, and project status and plan.

2.	Approval of global work practice requirements statement and specification, and project status and plan.

3.	Approval of global computer system requirements statements and specifications, and project status and plan (re-assess the delivery plan).

4.	Approval of detailed information system requirements statements and specifications, and project status and plan.

5.	Approval of detailed computer system requirements statements and specifications, and project status and plan (re-assess the delivery plan).

6.	Approval of final acceptance test and project status and plan (in particular the plan for the installation).

7.	Approval of installed information system.

8.	Complete the contract.

The schedules of the decision points are illustrated in Figure A.1 relatively to the start of the production process.

| Month from start of the production Decision point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Business req. |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Work practice |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |
| 3. Global CS |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |
| 4. Detailed IS |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |
| 5. Detailed CS |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |
| 6. Acceptance test |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |
| 7. Installation |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |
| 8. Completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |

Figure A.1: The schedules of the decision points.

# B.	DeliveryÊPlanÊExample: -ÊIncrementalÊapproach

#### B.1.	ProblemÊsituation

The customer has decided that the installation of a new version of the information system should be performed by the customer organisation. But the construction of the information system is to be performed by an external information system supplier. That means, the result of the IS-adaptation should be a tested information system, not yet installed. The goal of the IS-adaptation and the overall requirements to the schedules and budget for the IS-adaptation are described in a problem statement document.

#### B.1.1.	StartingÊpoint:ÊtheÊinitialÊstateÊofÊtheÊIS-adaptation

Problem description (see Annex A in the Customer Guide).

#### B.1.2.	Goal:ÊtheÊfinalÊstateÊofÊtheÊIS-adaptation

Tested information system (see Annex A in the Customer Guide).

##### B.1.3.	AppreciationÊofÊtheÊproblemÊsituation

¥	Complexity of situation: Complex, because:

-	Complexity of computerised functions is high (many external interfaces).

-	Complexity of non-functional requirements is high.

-	Complexity of development technology is high.

¥	Uncertainty of situation: Moderate, but:

-	Attitude of actors in the information system is negative.

-	Quality of existing specifications is low.

-	Novelty of the IS-adaptation is high.

¥	Critical risks of:

-	Unpredictable costs for the project.

-	Lack of target domain actor participation.

-	Developing wrong or unfeasible information system.

#### B.2.	IS-adaptationÊstrategy

##### B.2.1.	ApproachÊtoÊchangeÊsituationalÊfactors

¥	Change the attitude of actors by giving more information regarding the benefits of the IS-adaptation.

##### B.2.2.	DevelopmentÊapproach

¥	Experimental and expert-driven description.

¥	Incremental construction (three partial solutions).

##### B.2.3.	ProjectÊcontrolÊapproach

¥	Frequent project control and high degree of formality.

¥	Defined customer responsibility.

The customer is, among other things, responsible for:

-	Changing the attitude of actors by giving more information regarding the IS-project.

-	Making the user-oriented quality control of IS-descriptions (including prototypes).

-	Preparing and performing the acceptance tests.

##### B.2.4.	Risk management

The chosen approaches and:

¥	The project team contains IS-expertise with high level of technical skills.

¥	The project team will gather experience from similar information systems.

¥	The external interfaces of computerised functions are clarified through experiments.

¥	The experiments will be used to test non-functional properties of computer system.

#### B.3.	DecisionÊpoints

The decision points are defined by use of the examples of sequence of decision points related to the chosen approaches. Each decision point contains decisions regarding the progress and direction of the IS-adaptation.

1.	Approval of global work practice prototype and project status and plan.

2.	Approval of global work practice requirements statements and specification and project status and plan.

3.	Approval of global computer system prototype and project status and plan (re-assess the delivery plan).

4.	Approval of detailed work practice requirements statement, specification and prototype and project status and plan.

5.	Approval of detailed computer system requirements statement, specification and prototype and project status and plan (re-assess the delivery plan).

6.1	Approval of acceptance test of part 1 and project status and plan.

6.2	Approval of acceptance test of part 2 and project status and plan.

6.3	Approval of acceptance test of part 3 and project status and plan.

7.	Approval of tested information system.

8.	Complete the contract.

The schedules of the decision points are illustrated in Figure B.1 relatively to the start of the production process.

| Month from start of the production Decision point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. WP prototype |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Global WP req. |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. CS prototype |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Detailed WP |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |
| 5. Detailed CS |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |
| 6.1. Accept. test 1 |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |
| 6.2. Accept. test 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |  |
| 6.3. Accept. test 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |
| 7. Tested IS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |
| 8. Completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |

Figure B.1: The schedules of the decision points
(D = decisions include re-assessment of the delivery plan).

# C.	DeliveryÊPlanÊExample: -ÊEvolutionaryÊapproach

#### C.1.	ProblemÊsituation

The customer has decided that the installation of a new version of the information system is to be performed by an external information system supplier on the basis of the existing global design of a future information system.

#### C.1.1.	StartingÊpoint:ÊtheÊinitialÊstateÊofÊtheÊIS-adaptation

Global design (see Annex A in the Customer Guide).

#### C.1.2.	Goal:ÊtheÊfinalÊstateÊofÊtheÊIS-adaptation

Installed information system (see Annex A in the Customer Guide).

##### C.1.3.	AppreciationÊofÊtheÊproblemÊsituation

¥	Complexity of situation: Complex, because:

-	Complexity of information and business processes is high.

-	Complexity of data and computerised functions is high.

-	Complexity of target technology is high.

-	Complexity of migration is high.

¥	Uncertainty of situation: Uncertain, because:

-	Importance of organisational changes is high.

-	Stability of requirements is low.

But the:

-	Ability of actors in the information system is high.

-	Adequacy of schedules is normal.

¥	Critical risks of:

-	Evolving requirements.

-	Unpredictable costs for the organisation.

-	IS-adaptation not accepted by actors.

-	Business implications of project failure.

#### C.2.	IS-adaptationÊstrategy

##### C.2.1.	ApproachÊtoÊchangeÊsituationalÊfactors

No specific approach to change situational factors.

##### C.2.2.	DevelopmentÊapproach

¥	Experimental and participatory description.

¥	Evolutionary construction and installation (three versions).

##### C.2.3.	ProjectÊcontrolÊapproach

¥	Frequent project control and high degree of formality.

¥	Defined customer responsibility.

The customer is, among other things, responsible for:

-	Participating in the production and evaluation of IS-descriptions, including prototypes.

-	Performing the configuration management of requirements statements and operational items.

-	Managing the installation except the technical implementation of the new computer system.

##### C.2.4.	Risk management

The chosen approaches.

#### C.3.	DecisionÊpoints

The decision points are defined by use of the examples of sequence of decision points related to the chosen approaches. Each decision point contains decisions regarding the progress and direction of the IS-adaptation.

Version 1:

1.	Approval of detailed information system and computer system requirements statements, specifications and prototypes of version 1, and project status and plan, in particular the plan for construction of version 1.

2.	Approval of acceptance test of version 1 and project status and plan, in particular the plan for installation of version 1.

3.	Approval of installation of version 1 and project status and plan (re-assess the delivery plan).

Version 2:

1.	Approval of detailed information system and computer system requirements statements, specifications and prototypes of version 2 and project status and plan, in particular the plan for construction of version 2.

2.	Approval of acceptance test of version 2 and project status and plan, in particular the plan for installation of version 2.

3.	Approval of installation of version 2 and project status and plan (re-assess the delivery plan).

Final version:

1.	Approval of detailed requirements statements, specifications and prototypes of the final version, and project status and plan, in particular the plan for construction of the final version.

2.	Approval of acceptance test of the final version, and project status and plan, in particular the plan for installation of the final version.

3.	Approval of installation of final version.

4.	Complete the contract.

The schedules of the decision points are illustrated in Figure C.1 relatively to the start of the production process.

| Month from start of the production Decision point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1. Spec. of V.1 |  | Æ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2. Test of V.1 |  |  |  | Æ |  |  |  |  |  |  |  |  |  |  |  |
| 1.3. Install. of V.1 |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |
| 2.1. Spec. of V.2 |  |  |  |  |  |  | Æ |  |  |  |  |  |  |  |  |
| 2.2. Test of V.2 |  |  |  |  |  |  |  |  | Æ |  |  |  |  |  |  |
| 2.3. Install. of V.2 |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |
| 3.1. Spec. of V.3 |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |  |
| 3.2. Test of V.3 |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |  |
| 3.3. Install. of V.3 |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |  |
| 3.4. Completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Æ |

Figure C.1: The schedules of the decision points
(D = decisions include re-assessment of the delivery plan).

# References

[EM-1-EO]	Euromethod Overview, 1994

[EM-2.1-CG]	Euromethod Customer Guide, 1994

[EM-2.2-SG]	Euromethod Supplier Guide, 1994

[EM-2.4-MBG]	Euromethod Method Bridging Guide, 1994

[EM-2.5-CS]	Euromethod Case Study, 1994

[EM-3.1-TM]	Euromethod Concepts Manual 1 - Transaction Model, 1994

[EM-3.2-DM]	Euromethod Concepts Manual 2 - Deliverable Model, 1994

[EM-3.3-SM]	Euromethod Concepts Manual 3 - Strategy Model, 1994

[EM-4-ED]	Euromethod Dictionary, 1994

# Index

construction approach 46; 74

~ heuristics 48

evolutionary ~ 46; 74

incremental ~ 46; 73

one shot ~ 46; 73

costs 78

customer-supplier transaction 11; 64

decision 77

project domain ~ 77

target domain ~ 77

design ~ 80

investment ~ 78

system acceptance ~ 82

decision point 11; 13; 16; 64

~ description 17

definition of ~s 64

derivation of ~s 84

sequence of ~s 64

combined approach 76

construction approach 73

description approach 66

installation approach 74

project control approach 76

deliverable 77

~ profile 79

method ~ 84

required ~ 84

~ scope 79; 80

current information system 80

development state 79; 80

method ~ 85

quality state 79; 80

delivery plan 11; 78; 80; 83

~ version 18

assessment of a ~ 85

contents of a ~ 13

population of a ~ 83

delivery planning 19

activities and results of ~ 21

context of ~ 20

description approach 49

~ heuristics 50

analytical ~ 65; 67; 69

co-operation approach 49; 52

experimental ~ 65; 70; 72

expert-driven ~ 67; 70

mode of operation 49; 52

participatory ~ 69; 72

final state 13; 14; 25

definition of a ~ 27

initial state 13; 14; 25; 88

definition of a ~ 26

initial state information system 88

installation 40

installation approach 40

~ heuristics 44

evolutionary ~ 42; 75

geographical coverage 43

incremental ~ 42; 75

one shot ~ 42; 74

IS-adaptation 11

~ contract 18

~ requirements 83

~ strategy 13; 38

~ strategy options 41; 53

IS-adaptation strategy heuristics 43

IS-development method 82

IS-properties 79

management of complexity 59

management of uncertainty 61

method process model 85

method product 84

non-functional properties 79

problem situation 84

how to assess a ~ 23

process model 84

project control 53

project control approach 53

~ heuristics 55; 57

configuration control 54

customer responsibility 54; 56

development control 53

formality 54; 56

frequency 54; 55

quality control 53

prototyping 71

risk 15; 32; 78

complexity ~ 32

critical ~ 32

uncertainty ~ 33

project domain 36

target domain 34; 35

risk management 58

situational factor 15; 28

~ table

project domain 31

target domain 30

approach to change ~s 39

technical annex 12; 18

technical proposal 12; 18

technical specification 12; 17

transaction 11; 64

view

business information ~ 81

business process ~ 79; 81

computer system architecture ~ 79; 81

computer system data ~ 81

computer system function ~ 81

work practice ~ 81

Document history of the Euromethod Delivery Planning Guide

| Version | Status | Author | Comment | Distribution |
| --- | --- | --- | --- | --- |
| 291193 | Being developed | Niels Andersen | A one page overview of the table of contents - presented at the CB meeting at the 30th of November, 1993. | ¥ Control Board ¥ Project Team ¥ GW, LM |
| 120194 | Being developed | Niels Andersen | A presentation of the structure of the guide at the EMPMB meeting the 12th of January, 1994. | ¥ EMPMB ¥ PT, CB, LM |
| 210194, 250194 | Being developed | Niels Andersen | 1. versions of the document with the same layout as the deliverables in WP2 and build on the basis of the contents of the presentation at the EMPMB meeting the 12th of January, 1994. This is input to the enhancements made by MG and to discussions of the style and the structure in the project team. | ¥ Project Team: - MP: part of it - MF: 210194 - MG: 250194 |
| 010294 | Being developed | Niels Andersen, Mark Gibbons | Further development and incorporation of the enhancements from MG (until Section 5.3) and the comments from MF. This is input to the further enhancements made by MG. | ¥ MG |
| 020294 | Being developed | Niels Andersen, Mark Gibbons | Incorporation of very few of the enhancements from MG. This is the 1. draft which is send to some experts for constructive remarks. | ¥ GV, GV, JH, LM ¥ Project Team |
| 110294 | Being developed | Niels Andersen | Incorporation of some remarks from LM. | ¥ Project Team (holiday-diskette) |
| 170294 | Being developed | Niels Andersen | Incorporation of remarks from LM and all the enhancements from MG (010294). Situational factors changed to be in line with the revised strategy model, but the heuristics are not changed. | ¥ GW, LM, MF |
| 020394 | Being developed | Niels Andersen | Incorporation of some remarks from GVs and GW. Enhancements of the typical initial and final states and the examples of decision points. | ¥ MF |
| 070394 | Under L3-review | Niels Andersen | Incorporation of more remarks from GVs, LM and GW. Enhancements of some text. Incorporation of remarks from MF. Layout in line with the guide style. Restructuring of guidance regarding risk management | ¥ Review Group ¥ Project Team ¥ LM (partly) |
| 280394 | Under L3-review | Niels Andersen | Revised on the basis of remarks from the review group, the project team and LM. | ¥ RG (partly), AG ¥ Project Team |
| 050494 | Delivered | Niels Andersen | Revised on the basis of remarks from AG and the project team. New layout standards are implemented. | EC |
| 150694-m | Under L3-review | Niels Andersen | Revised on the basis of EMPMB remarks. | ¥ Review group ¥ GW, MF |
| Version 0, June 1994 | Delivered | Niels Andersen | Revised on the basis of remarks from the review group and GW. Marks are removed. | EC |

The guidance is based on the concepts defined in the Strategy Model. Those concepts support the technical concerns related to delivery planning. Other concerns, e.g. financial and legal concerns, which can be viewed differently by a customer and a supplier are not supported.