Euromethod
Overview

EM-1-EO

___________________________________

Abstract

This document describes the main objectives, the basic principles, and the key documents of Euromethod. Euromethod is designed to assist in managing information system procurement across organisational boundaries.

Euromethod focuses on the dynamic, contractual relationships between a customer and a supplier. A situation driven approach is offered to plan and manage the transactions between the main actors of the customer and the supplier organisations during a project.

___________________________________

© Euromethod Project 1994

This document,

Euromethod Overview,

is a document of the Euromethod Version 0.

In the layered document structure of Euromethod the Overview constitutes the introduction to Euromethod and the other Euromethod documents.

Contents of the Overview

1.	Introduction	4

1.1.	Where can Euromethod be used	4

1.2.	When can Euromethod be used	5

1.3.	How can Euromethod be used	6

2.	Euromethod Project Objectives	7

3	Benefits of using Euromethod	8

4.	Euromethod Principles	10

4.1.	Information System Adaptation	11

4.2.	Variety of Contracts	13

4.3.	Customer-Supplier Relationship	14

4.4.	Situation Driven	15

4.5.	Focus on Decisions	17

4.6.	Focus on Deliverables	18

4.7.	Method Bridging	19

5.	Euromethod Documents	21

5.1.	Guides	22

5.2.	Concepts Manuals	24

Annex: 	Background and history of EM	28

References	30

# 1.	Introduction

The objective of this Overview is to provide an introduction to Euromethod. It focuses on the main objectives underlying the Euromethod project, the basic principles that have guided the design of Euromethod, and the key documents that describe Euromethod at the present stage of development.

This document provides sufficient information to understand what Euromethod is and for what purposes it can be used. At the same time, it serves as an entry point to the information contained within the various documents of Euromethod.

## 1.1.	Where can Euromethod be used

Euromethod can be used in any project regarding an information system, where there is:

¥	A customer.

¥	A supplier (external or internal to the organisation).

¥	A contract (formal or informal) between the customer and the supplier.

The information system is that aspect of the organisation which provides, uses, and distributes the information . It includes the associated organisational resources such as human, technical and financial resources. It is thus effectively a human system, possibly containing a computer system that automates selected elements of the information system.

Euromethod addresses any kind of information system possibly including any kind of computer system (distributed or not, having data bases or not, real time or not, with knowledge base or not, office automation or not, etc.).

Examples of projects regarding the information system:

¥	Business design of a new or modified information system (including the organisational procedures).

¥	Technical design of a new or modified information system.

¥	Development of a new bespoke software.

¥	Development and installation of a new computer system (including new application software).

¥	Installation of a package based system.

¥	Maintenance of application software.

¥	Re-engineering of application software.

¥	Analysis of the changes required to an information system.

¥	Analysis of the changes required to application software.

¥	Documentation of an existing information system.

Euromethod can be used by both the customer organisation and the supplier organisation.

## 1.2.	When can Euromethod be used

Euromethod can be used in the procurement process, once the overall goal of the procurement has been established.

One part of the procurement process is the tendering process.

Euromethod can be used in the preparation of the call for tender and in the tendering process up to the signing of the contract. The determination of the goal of the procurement is not part of Euromethod. Euromethod is assisting in the definition of the requirements to the project. This includes the planning of deliveries.

Euromethod can be used during the project for the interactions existing between the customer and the supplier, such as the approval (or acceptance) of deliverables, the selection of solutions, the approval of project status, etc.

Euromethod can be used in the completion process of the project, e.g. for the approval of final deliverables.

Euromethod gives its full value when it is used consistently throughout the whole process, both by the customer and the supplier.

## 1.3.	How can Euromethod be used

Euromethod is applied by using the Euromethod documents which are shown on page 2, and in Figure 8.

After having read this Overview, the normal entry point is the:

¥	Customer Guide for the customer, or the

¥	Supplier Guide for the supplier.

These two documents refer to the other documents (Delivery Planning Guide, Method Bridging Guide, Concepts Manuals and Case Study) wherever appropriate.

The Case Study document concentrates most of the examples supporting the guides. It should then be read in conjunction with the guides. The Euromethod Dictionary allows access to a concept definition when it is needed by the reader.

# 2.	Euromethod Project Objectives

The open market for information system developments and related services within the European Union requires a good mutual understanding between the customers and the suppliers of information systems from the different EU countries. Currently, difficulties can be encountered within such customer-supplier relationships. The different backgrounds in terms of outlook, culture, training and methodologies lead to a confused and ambiguous relationship between the two groups. These can be serious obstacles for the realisation of the open market within the EU. The first element in the rationale for Euromethod is to facilitate the mutual understanding between customers and suppliers within an open international market for development of information systems.

A second element in the rationale for Euromethod is the provision of a framework in which conceptual harmonisation between different development methods can potentially be achieved. The focus is the customer-supplier relationship. Euromethod provides a common set of concepts and requirements for a potential method harmonisation in this important area without removing the competitive advantage that any particular method may have over other methods within its chosen market place.

The third element is to improve the quality and the efficiency of the information system development process by promoting the flexibility of the methods and their adaptability to the various problem situations that may be encountered.

These objectives support a number of objectives related to the open market. Euromethod is designed as a contribution to a broader process that should improve mobility, better organise international projects, facilitate assessment of tenders, achieve more successful IS developments, improve development processes, and, more generally, improve the competitive position of European industry.

# 3	Benefits of using Euromethod

Customer and supplier organisations are often encountering difficulties when they are working together as part of the procurement of an information system. But what are the main causes for these difficulties?

A commonly expressed view is that customer organisations are unable to express their business needs or requirements clearly. This is classically expressed within the following two situations.

In the first situation, the requirements expressed by the customers are too fuzzy or vague. This makes it impossible for a supplier to identify what the solution to the customer's needs might be. This is clearly expressed by the sentence: "We know we have a problem, but we do not know what that problem is. Please solve it for us!"

In the second situation, customers, possibly contrary to their understanding fail to express their requirements. Rather, the customer presents a solution, which very often does not encapsulate the real requirements, which interested suppliers are then asked to implement. This case is clearly expressed by the sentence: "Here are our requirements. We have done a lot of the technical work already. Please build it for us!". This may be observed as a restrictive tendering practice, in that the customer's choice for obtaining the correct solution to his problem from the best supplier is inhibited.

Another cause of difficulties is the difference in culture which exists within procurement and development organisations. Aspects of this argument include the way in which customers can be frustrated by the complexity of the technical jargon used by the suppliers, and the supplier's failures to understand customer requirements and to effectively manage the implementation of a solution to those requirements.

The problems outlined above consistently lead to a vicious circle, in which suppliers are unable to demonstrate the benefits of their proposals, and in which customer organisations are frustrated in their goals of obtaining the information system required to meet their business needs. Poor requirement elicitation, poor communications, poor decision making and poor matching of customers with suppliers inevitably result in the provision of the wrong information system to the customer.

However, it doesn't have to be like this. Many modern organisations are committed to achieving informed procurement, in which customer organisations aim to develop a partnership with their chosen suppliers. Other customers are aiming to achieve a step-wise improvement in their procurement programmes by utilising more flexible procurement programmes.

Euromethod is an approach to facilitate flexible procurement within the constraints of the European legislation supporting the creation of the European Single Market. That is, Euromethod provides the concepts and guidance needed to perform flexible, open and informed procurement of information systems. By using Euromethod, a virtuous circle is created in which better requirements elicitation, better communications, better decision making and better matching of customers with suppliers, results in the provision of more appropriate information systems to the customer.

An effectively working open European market will enlarge international buying and selling opportunities. Euromethod will facilitate open competition in the single market through improving the relationship between customer and supplier.

Customers buying information systems and enhancements will be able to use Euromethod to define their requirements in a way which is universally understood. This is a major achievement, especially in international tender situations.

The suppliers of information system developments in the international marketplace also will benefit from Euromethod. They will be able to understand better the needs of their customers and to produce better proposals; and they should be increasingly confident that they are developing information systems which meet their customers' needs.

Euromethod makes it easier for customers to evaluate the tenders, therefore helping to obtain value for their money.

Last but not least, Euromethod will facilitate the acceptance of systems by providing the means to better define the requirements of the system development in the contract and to better plan and manage the project and to improve the quality assurance procedures.

# 4.	Euromethod Principles

The design of Euromethod is based on a number of basic principles which have influenced the focus of Euromethod. They have determined the kinds of real life situations to which Euromethod applies. They are expressed more specifically in the key concepts and models included in Euromethod. Lastly, the principles underpin a set of guidelines for effective planning and management of information system development efforts across organisational boundaries.

The basic principles are:

¥	Information system adaptation.

Euromethod addresses a variety of changes to information systems, considering information systems as totalities of organisational, human and technical elements. This variety of changes, which include system development, is captured by the concept of information system adaptation.

¥	Variety of Contracts.

Euromethod applies to any information system adaptation that can be characterised by a well understood initial and final state. As a consequence, Euromethod can be reapplied at various stages during the life of the same information system.

¥	Customer-Supplier Relationship.

Euromethod supports the understanding, planning and management of the contractual relationships between a customer and a supplier of information system adaptations.

¥	Situation Driven.

Euromethod supports the development of a strategy and a plan for information system adaptation that is tailored to the specific characteristics of a problem situation.

¥	Focus on Decisions.

Euromethod focuses on the key decisions to be taken by the customer and the supplier, on their related transactions and on the key roles played by people (organisational actors) during these transactions.

¥	Focus on Deliverables.

Euromethod is focused on the deliverables which are exchanged between the customer and the supplier. The deliverables constitute the key planning elements to support decision making and management of progress.

¥	Method Bridging.

Euromethod provides valuable concepts and guidelines to supplement information system development methods. Guidelines are offered to bridge between Euromethod concepts, on the one hand, and development method concepts on the other.

In the following sections, these principles are discussed in more detail.

## 4.1.	Information System Adaptation

Euromethod addresses procurement and development of information system with a broad view on both the products and processes considered.

Figure 1: The information system.

On the product side, information systems are considered as totalities of organisational, human and technical elements as illustrated on Figure 1. Information systems contain information resources. These resources are used in processes performed by various actors within the organisation. Different kinds of technologies, one of the most important being computer systems, are developed to support the involved actors and to automate part of the processes involved. As a consequence, the scope of Euromethod is wider than software development: it is concerned with improving the information system in all its aspects.

On the process side, Euromethod addresses a variety of information system changes including their modification (correction, enhancement, improvement, etc.) and automation to fulfil the changing needs of the organisation. This variety of changes, for the purpose of Euromethod is captured within the concept of IS-adaptation .

A fundamental distinction is made between two types of activities involved in all these kinds of adaptations:

¥	Production activities: which perform the actual adaptation work through documentation, change study, design, test, installation of the information system.

¥	Management activities: which control the production through project planning and project control. Project planning is concerned with the specification of the components, timing, resources, and procedures of the project. Project control is concerned with monitoring the progress of the project, its direction, quality, and resource utilisation as compared with project plans.

## 4.2.	Variety of Contracts

Euromethod applies to any IS-adaptation that can be characterised by an initial state and a final state. As a consequence, Euromethod can be reapplied at various stages during the life of the same information system as illustrated on Figure 2.

Figure 2: An example of a series of contractual arrangements during the life of an information system.

The life of an information system will typically contain several IS-adaptations regulated by contracts, e.g. one or more change study studies, and one or more system description, construction, installation, or maintenance projects. When any such adaptation contract is established, the information system and the knowledge on the information system are in a certain state, called the initial state of the adaptation. The desired state of the information system and the related products which express the knowledge on the information system at the termination of the contract is called the final state of the adaptation. Euromethod provides the concepts and guidelines to determine both initial and final states of information system adaptations in a flexible way, to better suit each specific situation.

## 4.3.	Customer-Supplier Relationship

Euromethod supports the understanding, planning and management of the contractual relationships between a customer and a supplier of IS-adaptations. Figure 3 summarises this fundamental view on IS-adaptation.

Figure 3: The two levels of a Customer-Supplier Relationship.

A distinction is made between two levels of customer-supplier relations: the relationship at a contractual level and the relationship at a project level. The main focus of Euromethod is on the contractual level starting with the call for tender, proceeding through the signing of a contract, eventually entering into the actual production of a set of deliverables, and finally ending when the contract is terminated. From this point of view Euromethod is designed to:

1.	Enhance the customer-supplier relationships in IS-adaptation contracts (focusing on the relationship at the contractual level).

2.	Bridge the cultural difference between the parties involved in the contractual relationship, e.g. between procurers on the one hand, and project managers and developers on the other (focusing on the relationship between the contractual level and the project level).

This view is further elaborated in terms of the key roles involved as illustrated in Figure 4.

Figure 4: The key roles involved in IS-adaptation.

## 4.4.	Situation Driven

Euromethod supports the development of a strategy and a plan for IS-adaptation that is tailored to the specific characteristics of a problem situation. The problem is the IS-adaptation and the problem situation is its context.

A problem situation is expressed using a set of situational factors, and these properties of the problem situation are used to predict the risks and thus determine the appropriate problem solving strategies for their containment or reduction.

In this sense, Euromethod applies a situation driven approach to IS-adaptation. It does so through guidelines for:

¥	The identification of important situational factors.

¥	The assessment of the complexity, uncertainty and risks.

¥	The definition of a strategy for the IS-adaptation.

This IS-adaptation strategy is designed for the reduction or containment of risks inherent in the problem situation and it places specific requirements on the delivery plan of the contract. This situation driven approach is illustrated on Figure 5.

Figure 5: The context and key results of applying Euromethod.

## 4.5.	Focus on Decisions

In the course of a procurement of an information system, the customer and the supplier execute transactions where they exchange products and take decisions on the basis of the information contained in those products.

The types of transactions between a customer and a supplier are modelled as illustrated on Figure 6. Three processes are considered:

¥	The tendering process which starts with a call for tender and usually ends with the signing of the contract.

¥	The production process where the IS-adaptation is performed, i.e. the deliverables are produced.

¥	The completion process where the contract is technically and commercially terminated.

During the tendering and the completion processes a set of specific types of transactions are used to provide a simple and general model. In contrast, during the production process a set of general types of transactions are used to provide the means to create, in each specific application of Euromethod, a tailored model of the production process. This model focuses on key decisions to be taken by the customer. These decisions are crucial for the customer since they will determine the properties of the new information system. They are as important for the supplier insofar as they are shaping the objectives of the project, its costs and chances of success.

Figure 6: The types of customer-supplier transactions in IS-adaptations.

The process followed by the customer and the supplier during the production process will consist of transactions in which decisions about the information system and the way it is produced are approved or made. The main decision points have to be approved by the customer or made in co-operation with them, and the sequence of the related transactions is specified in the delivery plan.

Euromethod is providing assistance in planning these decision points and customer-supplier transactions. It also gives some help in determining the right products that must be delivered to support a certain decision.

## 4.6.	Focus on Deliverables

Euromethod focuses on deliverables with less concern for the supplier's activities in which they are produced. The deliverables constitute the key planning elements to support decision making and management of progress.

For the customer, the deliverables are more important than the way in which they are produced by the supplier. ÒWhatÓ is more important than ÒHowÓ. Some of these deliverables are stated as the objective of the contract. It is crucial that there is a mutual understanding between the customer and supplier regarding the goal, and the meaning of these deliverables. In addition, other deliverables need to be included to provide the customer with sufficient information on intermediate results, plans, and progress made.

Figure 7: The principal deliverable types.

For the supplier, both deliverables and activities are important. Nevertheless, the activities are subordinate to the deliverables because a project is defined through the dynamic contractual relationship with the customer.

The classification of deliverables is based on the distinction between target domain and project domain. The target domain is that part of an organisation for which an IS-adaptation should be performed. The project domain is the temporary organisation, sometimes called project, which has been set up with the goal of adapting an information system of an organisation.

Euromethod includes three types of deliverables as illustrated in Figure 7. Target domain deliverables relate to the information system to be adapted and they include descriptions as well as operational items of the information system. The delivery plan contains a description of the approach to the production process as agreed between the customer and the supplier. Finally, project domain deliverables relate to the process of production including more detailed plans, as well as reports on progress and problems. Plans for future IS-adaptations can also be produced during an IS-adaptation.

## 4.7.	Method Bridging

As illustrated by Figure 5, the actual design of an appropriate development approach is not only to be guided by Euromethod. The organisational setting will contain standards and rules that have to be followed, and the development methods to be applied in the production process will guide the actions through specific process models and product profiles. In this sense, Euromethod provides valuable concepts and guidelines to supplement information system development methods and local standards and rules.

Euromethod offers guidelines to bridge between its own concepts, on the one hand, and the concepts of development methods on the other. These guidelines can be used in applications of Euromethod to specific IS-adaptations. In a different context, these guidelines can serve as a framework to achieve some level of conceptual harmonisation between different development methods.

# 5.	Euromethod Documents

Euromethod is designed to help practitioners analyse, plan, and manage customer-supplier relationships at a contractual level in a single IS-adaptation. The abstract principles underlying the design of Euromethod express the approach taken to provide this support. On a more concrete level, Euromethod provides concepts and models to help understand the dynamics of a customer-supplier relationship together with guidelines to help plan and manage the transactions involved in an IS-adaptation. As a consequence, Euromethod has been structured into four layers as illustrated on Figure 8:

Figure 8: The layered Euromethod document structure.

This layered structure of the Euromethod documents has been designed to facilitate easy access to the information. Each of the layers makes references to, and uses, elements defined in the lower layers.

¥	Euromethod Overview:

A general introduction to the principles underlying the design of Euromethod. This overview serves as a guide to the other documents on Euromethod. It is the first document to be read.

¥	Euromethod Guides:

A set of guides and a Case study document that facilitate and explain the use of Euromethod to plan and manage development efforts across organisational boundaries.

¥	Euromethod Concepts Manuals:

A set of concepts and models that provides a coherent and in depth understanding of the dynamics of a customer-supplier relationship during an IS-adaptation.

¥	Euromethod Dictionary:

A summary of the terms defined in Euromethod, classified in alphabetical order. Whenever possible, the ISO standards have been selected as sources.

The following sections provide a brief introduction to the Guides and the Concepts Manuals.

## 5.1.	Guides

The Euromethod Guides consists of four different guides and a case study document. Each guide has its own focus and key audience.

Case Study

The Case Study document presents examples of practical applications of the Euromethod guides and concepts. The purpose of the document is to demonstrate how the various Euromethod elements apply to real life situations. It also provides a context for a complete and consistent set of examples that serve to illustrate the guides.

It should be read in conjunction with the guides.

It is an important document for the understanding of Euromethod.

Customer and Supplier Guides

The Customer and Supplier Guides provide role specific guidance to the application of Euromethod. The guides explain the usage of the Delivery Planning Guide, the Method Bridging Guide and the Concepts Manuals by the customer and supplier roles.

The two role guides are very similar in structure, but they give guidelines from two different points of view.

The objectives of the Customer Guide are to:

¥	Provide guidance on how to apply the Euromethod concepts in order to effectively support the customer within the customer-supplier relationship found within an IS-adaptation. In this way the guide aims to support the customer in bridging the cultural difference which frequently exists as part of this relationship. In particular, guidance is provided to support the roles of customer contract authority and customer project authority.

¥	Provide guidance on applying the Euromethod concepts in order to express, interpret and assess the main contractual products produced and received by the customer. That is, the provision of guidance on how the concepts can be used by a customer to augment those parts of the IS-adaptation requirements which are supported by Euromethod.

¥	Provide guidance on how the customer should use the Euromethod concepts to support their work within each transaction, with particular emphasis on the deliverables to be exchanged and the decisions to be made.

The objectives of the Supplier Guide are very similar in nature but they address the needs and point of view of the supplier instead of the customer.

Delivery Planning Guide

The Delivery Planning Guide supports the customer and the supplier in the design and assessment of a delivery plan. The delivery plan defines the customer-supplier transactions during the production process. Based on a common terminology, this delivery plan can be understood by both the customer and the supplier.

The Delivery Planning Guide helps the customer and supplier:

¥	Describe the initial state and the final state of an IS-adaptation in terms of the concepts in the Deliverable Model.

¥	Determine the contents and scheduling of decision points based on a chosen strategy. Each decision point is related to one or more customer-supplier transactions, e.g. the approval of deliverables and the approval of status and plan.

¥	Define the exchanged deliverables needed to make the scheduled decisions.

Method Bridging Guide

The Method Bridging Guide serves a triple purpose. First, it allows method owners and suppliers to bridge their method to the Euromethod concepts. Second, given a Euromethod delivery plan, it helps populating this plan with products from a chosen IS-development method. Third, given a specific IS-development method, it demonstrates how to express the process model of the method as a Euromethod delivery plan.

A Euromethod delivery plan is expressed in a terminology that is independent of IS-development methods. This facilitates:

¥	The comparison of proposed delivery plans with bridges to different methods.

¥	The assessment of the suitability of a proposed delivery plan.

¥	The assessment of the suitability of IS-development methods for a delivery plan.

## 5.2.	Concepts Manuals

The basic principles of Euromethod are expressed by a set of concepts related to three fundamental models of the customer-supplier relationship during IS-adaptation. These are the Transaction Model, the Deliverable Model, and the Strategy Model.

Transaction Model

The Euromethod Transaction Model is developed as a vehicle to understand, manage and facilitate customer-supplier interactions across organisational boundaries during an IS-adaptation. The model serves two purposes:

¥	It defines the kinds of real life situations to which Euromethod can be applied.

¥	It provides the conceptual means to understand, plan, and manage a customer-supplier relationship during IS-adaptation.

Deliverable Model

The Euromethod Deliverable Model is designed to facilitate the understanding and definition of deliverables utilised within an IS-adaptation. In order to characterise the deliverables, the Deliverable Model defines:

¥	what a target domain of an IS-adaptation is,

¥	what an information system is,

¥	what the scope of an IS-adaptation is, and

¥	what the essential properties of an information system are.

The essential properties of an information system are expressed as a set of views related to the information resource, the processes, and the actors of the information system in question. These views define the concepts and the terminology used to characterise essential knowledge about an information system:

¥	The business information view:

This view defines relevant knowledge about the information resource of the target domain.

¥	The business process view:

This view defines relevant knowledge about processes and their general usage of the information resource.

¥	The work practice view:

This view defines relevant knowledge about individual actors, their organisation, their locations, the tasks by which they achieve the business processes and their specific usage of the information resource.

These views are complemented by more specific views on how computer systems support the usage of the information resource. Three views are provided:

¥	The computer system data view:

This view defines relevant knowledge about the computerised data of the target domain.

¥	The computer system function view:

This view defines relevant knowledge about the computerised processes (functions) and their usage of the data.

¥	The computer system architecture view:

This view defines relevant knowledge about the processing units of the computer system, their structure, their locations, and the distribution of data and functions to them.

These computer system views correspond to the three information system views above, but the focus has changed from organisational information processing to computer-based data processing.

Strategy Model

The Euromethod Strategy Model provides a situation driven approach to the planning of IS-adaptation projects. The situation is expressed using a set of situational factors (relevant properties of the situation), and these properties of the problem situation are used to predict the risks and then determine the appropriate strategy for their containment or reduction.

A situation driven approach is a response to the need of tailoring development approaches to problem situations. This need has been expressed by practitioners in the field of information system development and situation driven approaches are considered as an area for potential improvement of current development methods.

An IS-adaptation strategy defines the intended approach to achieve the objectives of a project, i.e. an approach that meets the requirements and needs of a customer and which is appropriate for the reduction or containment of risks inherent in a certain problem situation. The IS-adaptation strategy places requirements on the delivery plan, which on a more specific level describes the structure and content of decision points and deliverables.

The definition and assessment of an appropriate IS-adaptation strategy is supported by a set of strategy options. These options are expressed in relation to four concerns that are important from the point of view of the customer-supplier relationship:

¥	System installation,

defining how the system is going to be brought into service in the target domain.

¥	System construction,

defining how the system is going to be constructed and tested.

¥	System description,

defining how the system is going to be modelled and described.

¥	Project control,

defining how the project is going to be planned and controlled.

The Strategy Model provides a description of the situational factors that allow an assessment of the problem situation, a description of the available strategy options, and a set of heuristics for the selection of those options on the basis of the problem situation.

# Annex: Background and history of EM

Project history

The Euromethod project has been running since November 1989. This was the start of Phase 1 where the European Member States got together with the European Commission and agreed on the essential requirements. This provided the basis for Phase 2, a Euromethod feasibility study, funded by the European Community, which ran from May 1990 for about 8 months. The study concluded that the need for Euromethod was a real one and recommended a high level structural model on which the development of Euromethod should be based.

The Euromethod Phase 3 which started in the summer of 1992, was a very large step and to control it better, it was split into Phase EM 3a and a possible further phase. Phase 3a is now completed with the initial version of Euromethod as a result.

Project Organisation

The Euromethod project is funded by the European Commission on behalf of the European Member States under the sponsorship of the Public Procurement Group (PPG), a pan-European grouping of public procurement bodies. The project has been performed by the Eurogroup consortium, consisting of 10 partners from 8 different Member states: Sema Group, which was the main contractor (France), BT (UK), Cap-Volmac (Netherlands), CGI (France), Datacentralen (Denmark), EMSC, formed by Bull (France), Olivetti (Italy) and Siemens-Nixdorf (Germany), Eritel (Spain), Finsiel (Italy), Instituto Nacional de Administrao (Portugal), and Softlab (Germany).

There are other companies which are associated partners to this consortium: Commission Nationale d'Informatique (Romania), Center for Software Engineering (Ireland), IABG (Germany), MTA Information Technology Foundation (Hungary) and PLANET (Greece).

A multi-national project team, drawn from the members of the consortium, has produced the initial version of Euromethod. In doing so, the project team called upon a pool of expertise made up of specialist consultants and people from the academic community.

Prior to the release of the project deliverables, they have been subjected to a quality assurance process. This has been undertaken both from within the consortium and from a board representing the European Commission and Member States (Euromethod Programme Management Board, EMPMB) established by the PPG. The European Commission controlled whether the deliverables and progress were according to the contract.

Last but not least, in some countries National Euromethod Fora have been set up, made up of representatives of users, software industry, government and universities, to judge the deliverables of Euromethod from a national point of view.

# References

[EM-1-EO]	Euromethod Overview, 1994

[EM-2.1-CG]	Euromethod Customer Guide, 1994

[EM-2.2-SG]	Euromethod Supplier Guide, 1994

[EM-2.3-DPG]	Euromethod Delivery Planning Guide, 1994

[EM-2.4-MBG]	Euromethod Method Bridging Guide, 1994

[EM-2.5-CS]	Euromethod Case Study, 1994

[EM-3.1-TM]	Euromethod Concepts Manual 1 - Transaction Model, 1994

[EM-3.2-DM]	Euromethod Concepts Manual 2 - Deliverable Model, 1994

[EM-3.3-SM]	Euromethod Concepts Manual 3 - Strategy Model, 1994

[EM-4-ED]	Euromethod Dictionary, 1994

---------

[87/95/EEC]	The EEC Standards Decision.

[92/50/EEC]	The EEC Service Directive.

Document history of the Euromethod Overview

| Version | Status | Author | Comment | Distribution |
| --- | --- | --- | --- | --- |
| 180294 | Being developed | LM, NA | An overall design based on outline provided by MF | Project team |
| 250294 | Being developed | LM | A complete version. A few minor elements have to be inserted at places indicated by (*Specification of insertion*). | Project team |
| 020394 | Being developed | MF | This version has been updated with remarks from NEA and MF To be included: Project organisation and benefits | NA |
| 070394 | Under L3-review | NA | Small changes of figures and inclusion of description of benefits and project organisation based upon PPG DOC: 323. | ¥ Review group ¥ Project team |
| 250394 | Under L3-review | MF | Updated according to remarks from Review Group and Project Team | ¥ Review group ¥ Project team |
| 050494 | Delivered | MF |  | EC |
| 150694 | Ready for review | MF | EMPMB remarks taken into account | Review Group |
| 300694 | Delivered | MF |  | EC |

IS-adaptation includes all kinds of project such as system development, maintenance, design, reverse engineering, various sorts of study, system installation, etc.

However, it is recognised that the production process is also important insofar as it has an impact on the quality of the deliverables.