Euromethod
Supplier Guide

EM-2.2-SG

__________________________________

Abstract

This Guide provides the guidance for Euromethod practitioners undertaking IS-adaptations from a Supplier perspective.

It explains how the Euromethod concepts defined in the EuromethodÊConcepts Manuals have to be used in order to support suppliers in performing the tendering process and the activities related to the production and completion processes of an IS-adaptation.

__________________________________

© Euromethod Project 1994

This document,

Euromethod Supplier Guide,

is a document of the Euromethod Version 0.

In the layered document structure of Euromethod it constitutes a part of the Guides Level. It makes use of the definitions in the Method Bridging Guide, the Delivery Planning Guide and Concepts Manuals and the Dictionary.

Contents of the Supplier Guide

1.	Introduction	5

1.1.	Objectives	5

1.2.	Target Audience	5

1.3.	Scope	6

1.4.	Style Considerations	6

1.5.	Entry Points	9

2.	What is an IS-Adaptation	11

2.1.	IS-Adaptations and the Services Directive	11

2.2.	How are the SupplierÕs Responsibilities described	15

2.3.	How is the CustomerÕs Involvement to the Production Process described	16

2.4.	How is the Customer-Supplier Relationship described	19

2.5	Role Assignment in an IS-adaptation	21

3.	How to use Euromethod in the Tendering Process?	27

3.1	How to participate in the Call for Tender	29

3.2.	How to prepare the Tender Response Transaction	30

3.2.1.	How should you interpret the IS-adaptation Requirements	32

3.2.1.1.	Identification of the Products to be delivered	32

3.2.1.2.	Analysis of the Initial State Products	33

3.2.2.	How should you produce an IS-Adaptation Proposal	34

3.2.3.	What should you do if no Delivery Plan can be produced	36

3.2.3.1.	Amendment of the Final State	37

3.2.3.2.	Amendment of the Initial State	37

3.2.3.3.	Change the Situational Factors	38

3.3.	How to prepare the Supplier Selection Transaction	39

3.4.	How to prepare the Contract Awarding Transaction	41

4.	How do you use Euromethod in the Production Process	44

4.1.	Approval of Deliverables	45

4.2.	Approval of Project Status and Plan	51

4.3.	Contract Change Control	53

4.4.	IS-adaptation Role Assignments in the Production Process	57

5.	How do you use Euromethod in the Completion Process	58

5.1.	Approval of Final Deliverables	59

5.2.	Contract Completion	61

References	64

Index	65

# 1.	Introduction

## 1.1.	Objectives

The objectives of this Supplier Guide are to:

¥	Provide guidance on how to apply the Euromethod concepts as a supplier within the customer-supplier relationship during an IS-adaptation. The guide supports the supplier in bridging the cultural gap which frequently exists as part of this relationship. In particular, guidance is provided to support the roles of supplier contract authority and supplier project authority.

¥	Provide guidance to the supplier on applying the Euromethod concepts to produce and interpret the main contractual products. That is, provide guidance on how the concepts can be used by a supplier during an IS-adaptation.

¥	Provide general guidance on how Euromethod interfaces with the day to day tendering and production process management activities performed by the supplier.

¥	Provide guidance on how the supplier should use the Euromethod concepts to support their work within each transaction, with particular emphasis on the deliverables to be exchanged and the decisions which must be made.

## 1.2.	Target Audience

This guide is intended to be used by a supplier's contract authority and project authority for IS-adaptations. These are the person or group of persons:

¥	Holding the authority to make contractually binding arrangements with a customer for a given IS-adaptation;

¥	Having the responsibility for managing the supplier organisationÕs activities related to this IS-adaptation.

## 1.3.	Scope

The basic assumption for this guide is:

The goals of the IS-adaptation are defined within a call for tender document.

Thus, this guide assumes a context in which:

¥	The Initial and Final States of the IS-adaptation and the documentation available to this IS-adaptation are defined within the call for tender.

The scope of this guide is the appropriate level of Euromethod guidance that must be provided to a supplier. It is assumed that the supplier is experienced in the processes involved in an IS-adaptation and will principally be interested in the Method Bridging and Delivery Planning Guides.

That is, the guide aims to describe the context of a supplier's usage of Euromethod during an IS-adaptation and in particular, introduce the entry points into the detailed guidance of the topic guides. This guide therefore provides guidance on:

¥	The planning of an individual IS-adaptation (with cross-references to the Delivery Planning Guide [EM-2.3-DPG]).

¥	The relationship between Euromethod deliverables and method products within an individual IS-adaptation (with cross-references to the Method Bridging Guide [EM-2.4-MBG]).

¥	The use of the Euromethod concepts in defining tender response documents, contracts, deliverables, etc.

¥	The preparation of the individual transactions in an IS-adaptation.

## 1.4.	Style Considerations

Careful consideration has been given to the style of this guide to ensure that it makes reading easy, and thus has the ability to support the activities that Euromethod proposes. Each of the documentation features employed by this guide is now considered briefly.

Based on the documentation content and the supporting document features described here, the guidance provided in this document aims to help users of the guide quickly locate the problem they are currently addressing. In this way, the guide intends to help that person determine which step to take next, in order to facilitate a decision to be taken, or in progressing some task during the course of the Euromethod activity being performed.

Layout and Symbols

Throughout the text of this guide a number of symbols are used that ease reading by giving graphical help for recognising the purpose of particular paragraphs.

Bullet Point Lists

These are used to emphasise enumerations. This can be used for several purposes:

¥	To highlight important terms; rather than hiding them in the text.

¥	To attribute additional information to terms; thus avoiding sentences that are too long and not well structured.

¥	To list topics that will be dealt with in subsequent sections.

Checklists

These are used to give direct support to the users of Euromethod.

There are some question-answer checklists:

×	Are you just reading this guide to learn about the supplier role?

=>	 If so, the checklists provide you with some information.

×	Are you using this guide while performing a supplier's activity?

=>	 If so, you should work through the checklists in order to achieve the correct results.

There are also checklist items that do not have a part prefixed with the arrow symbol. These just give you information on things to be considered in the supplier's activities.

Some of the tables and matrices provided in the guide also serve as checklists. These are provided when they are more useful than the mechanism described above.

Reference Arrows

These appear in the left margin and indicate in which Euromethod Document and under which key words additional information and definitions on the topic discussed there can be found.

¥	Key word

¥	Key word

Reference to the other Euromethod Documents is also provided by using the document name in the text. This is especially the case, when the document as a whole is mentioned without reference to particular key words, e.g. method bridging is based on the concepts defined in the Deliverable Model.

Reminder Notes

These are used to emphasise what should be kept in mind when reading the subsequent sections.

Remember: This section only gives a quick overview of the symbols used, not a detailed definition of a semantic of these symbols.

In Reminder Notes that recall definitions the reference to the document that contains the definition is provided.

Chapter Overview Sections

Special headers for the chapters which describe the preparation of customer-supplier transactions give a quick overview of the contents of the particular chapter. The contents of an overview section in this guide is:

| Purpose: | The objective of activities described in the chapter. |
| --- | --- |
| Activities: | List of the activities described in the chapter. |
| Results: | List of the results from the activities. |
| Concepts: | List of the Euromethod concepts used in the activities. |
| Checklists: | List of the checklists provided to support the activities. |
| Examples: | List of related Case Study examples. |

The example entry in each chapter overview section points to the appropriate chapters and sections in the Case Study document, where examples related to the presented guidance can be found.

Highlight Boxes

Highlight boxes draw the readers attention to statements which are of general importance.

Knowing the symbols used eases using the guide.

Examples

Besides the case study examples that are references in the Chapter Headers, more general examples which are independent from the case study are used.

| Example | These example boxes are used for: ¥ Providing example information additional to the case studies. ¥ Small examples which serve to clarify points in the text. |
| --- | --- |

## 1.5.	Entry Points

This guide is intended to be used by both the contract authority and the project authority in the sense that the guidance provided is relevant to both of them. However, the perspective of the two roles is different:

¥	The point of view of the contract authority is:

ÒI have to ensure that the tendering process results in a sound contract and that the contract is effectively managed".

¥	The point of view of the project authority is:

ÒI have to ensure that the products are delivered to the required quality and within budget and timescalesÓ.

When reading the guides for the first time, it is advised that all the sections are read in the sequence in which they are presented.

Readers familiar with the guide can enter it from several points dependent upon their working situation within an IS-adaptation, i.e., depending upon the transaction that they are preparing for.

Thus their entry point to this guide can be:

¥	Chapter 3, to prepare for the transactions of the tendering process.

-	Preparing for the Tender Response transaction.

-	Preparing for the Supplier Selection transaction.

-	Preparing for the Contract Awarding transaction.

¥	Chapter 4, to prepare for the transactions of the production process.

-	Preparing an approval of deliverables transaction.

-	Preparing a approval of project status and plan transaction.

-	Preparing a contract change control transaction.

¥	Chapter 5, to prepare for the transactions of the completion process.

-	Preparing an approval of final deliverables transaction.

-	Preparing a contract completion transaction.

# 2.	What is an IS-Adaptation

This chapter shows which parts of an IS-adaptation:~ contract can be formulated using Euromethod; and which Euromethod concepts are relevant for that purpose.

Remember: An IS-adaptation is any kind of modification (correction, enhancement, improvement, etc.) and automation of an information system; that is performed by a supplier for a customer in a contractual relationship 
[EM-4-ED].

A contract for an IS-adaptation must contain a precise description of the IS-adaptation in terms of what has to be delivered. Furthermore, it must define what the contribution of the contractual parties should be in the production of the delivered products.

Guidance on how to produce and execute an IS-adaptation contract and use the definitions is given to you in the following chapters. They describe how to use Euromethod in the tendering, production and completion processes respectively.

## 2.1.	IS-Adaptations and the Services Directive

Remember: According to the Council Directive 92/50/EEC of 18 June 1992 (the Services Directive) a technical specification is defined as Òthe totality of the technical prescriptions contained in particular in the tender documents, defining the characteristics of a work, material, product or supply, which permits a work, a material, a product or a supply to be described in a manner that it fulfils the use for which it is intended by the contracting authority. [...]Ó [92/50/EEC]

The use of the term technical specification was first defined in the original Supplies Directive, 70/32/EEC. However, information systems were not covered until 1981. Consequently the term, technical specification was included within 92/50/EEC principally for historical reasons. The implication of this is that the term is not appropriate to completely address the need to define the requirements of IS-adaptations within tendering documentation. Indeed, the use of the term technical specification could create the wrong impression with Euromethod practitioners, since customers of IS-adaptations wish to provide requirements to suppliers which will eventually be met by solution proposals, and the use of the term specification may suggest a solution. For this reason, although Euromethod supports the objectives of 92/50/EEC, Euromethod has defined its own terminology to support the technical prescriptions required by 92/50/EEC.

Euromethod supports the definition of an IS-adaptationÕs results and the planning of the IS-adaptation in terms of the deliveries to the customer which in the Euromethod terminology are called the IS-adaptation:~ requirements.

IS-adaptation requirements are part of all the documents exchanged in the tendering process.

Remember: In the Euromethod documents these are referred to as:

¥	The technical specification, in the call for tender of the customer;

¥	The technical proposal, in the tender response of the supplier;

¥	The technical annex, in the IS-adaptation:~ contract between the customer and supplier.

However, it should be noted that, in addition to the IS-adaptation requirements there is additional technical documentation required as part of a call for tender. For example, in addition to the IS-adaptation requirements, you may receive information regarding the evaluation criteria which will be used in assessing your tender responses. Although this is referenced at the appropriate points within the Euromethod documentation, it is not currently supported in detail within Euromethod.

Euromethod facilitates a unified formulation of the IS-adaptation requirements in the tender documentation.

It does not address any other issues to be defined in IS-adaptation contracts; especially the financial and legal commitments.

Within this context, Euromethod defines the means to describe an IS-adaptation from the customer-supplier relationship point of view; and in particular provides the concepts and terminology needed to formulate IS-adaptation requirements (see Figure 2).

| Services Directive Technical prescriptions (i.e. IS-adaptation:~ requirements) | Supporting Euromethod concepts |
| --- | --- |
| Defining the characteristics of a material, product or supply in a manner that it fulfils the use for which it is intended by the contracting authority. | This is supported by the concept of the final state of an IS-adaptation; which is based on the idea of characterising the result to be achieved through selecting properties of information systems that have to be specified or implemented. |
| Defining the characteristics of the work | This is supported by the concept of the delivery plan |

Figure 2: Euromethod support in formulating requirements for IS-adaptations.

The definition of technical specification in the Council Directive 92/50/EEC provides further detail in defining what the content of the technical prescriptions should be.

Remember: The Council Directive 92/50/EEC states:

ÒThese technical prescriptions shall include levels of quality, performance, safety or dimensions, including the requirements applicable to the material, the product or to the supply as regards quality assurance, terminology, symbols, testing and test methods, packaging, marking or labelling.Ó

The formulation of these issues is supported by the concepts defined in the Deliverable Model. Figure 3 provides an overview mapping of the relevant deliverable model concepts.

¥	Deliverable concepts

| Services Directive Technical prescription issues (i.e. IS-adaptation:~ requirements) | Supporting Euromethod concepts |
| --- | --- |
| Levels of quality, performance, safety or dimensions. | These are captured by the non-functional properties that can be defined as requirements of an information systems. |
| Requirements as regards quality assurance. | These are captured by the quality assurance plans and reports |
| Requirements as regards terminology. | This is supported through Euromethod as a whole as it defines a terminology for the tender documents. |
| Requirements as regards symbols. | The use and explanation of symbols and notations is supported through the method bridging capabilities of Euromethod |
| Requirements as regards testing and test methods | These are captured by the quality assurance plans and reports |

Figure 3: Euromethod support in formulating requirements for IS-adaptations.

Three types of procurement procedure are permitted within the Services Directive. These are the open, restricted and negotiated procedures.

From Figure 3, it can be seen that the definition of technical specification can be interpreted to permit the description of IS-adaptation requirements.

All three procedures defined within the Services Directive may be undertaken using the Euromethod concepts.

The following sections consider how the three main issues of defining the IS-adaptation:~ requirements are addressed by the Euromethod concepts:

¥	Definition of the IS-adaptation result to be produced by the supplier,

¥	Definition of the customer involvement in terms of products to be supplied,

¥	Definition of the working relationship during the production of the IS-adaptation results.

This section has concentrated on the legal requirements which are applied to public procurement of information systems under the auspices of the Services Directive.

Remember: The Euromethod concepts and guidance are equally applicable within IS-adaptations:

¥	When the customer is in the private sector, as well as in the public sector.

¥	Performed within a single organisation and defined by an informal rather than formal contract (e.g. a Memorandum of Understanding).

## 2.2.	How are the SupplierÕs Responsibilities described

The IS-adaptation results that have to be produced are defined by the final state of the IS-adaptation within the technical annex of an IS-adaptation contract. The final state of an IS-adaptation contains:

¥	The final state:~ information system (That is, a set of operational items providing enhanced functionality or performance)

¥	The operational items of a future information system that are produced as a result of this IS-adaptation, but which are not yet installed as part of the operational information system.

¥	The IS-descriptions that are produced as a result of this IS-adaptation and which the customer wants to use after the conclusion of this IS-adaptation. These IS-descriptions will address either:

-	The final state information system.

-	A future information system version.

¥	Plans for future IS-adaptations that are produced as part of this IS-adaptation.

It is this description of the final state that contains the core of the supplier's responsibilities within a proposed IS-adaptation.

| Example | The Euromethod definition of the final state of an IS-adaptation allows you to define any kind of IS-adaptation. Examples of frequently encountered kinds IS-adaptation are: - Development projects, which are mainly concerned with adding new operational items rather than replacing existing ones. - Maintenance projects, which are mainly concerned with the replacement of operational items rather than adding new ones. - Design projects, which are not changing the operational items installed in the information system, but produce IS-descriptions of a future information system. - Reverse engineering projects, which are not changing the operational items installed in the information system, but produce IS-descriptions of this information system. - Study projects like information system change study project. |
| --- | --- |

In some circumstances, a supplier may perform more than one IS-adaptation on behalf of a customer. In this instance, the supplier may help the customer to identify and plan for the technical dependencies within the project plans; and then manage these dependencies during the production and completion processes.

## 2.3.	How is the CustomerÕs Involvement to the Production Process described

The customer's involvement in an IS-adaptation depends on the nature of a particular IS-adaptation, and the activities involved in both contracting that IS-adaptation out to a supplier, and then participating in the customer-supplier transactions defined within the delivery plan. In addition, the customer may well participate in more informal relationships, such as providing operational expertise to the supplier's project authority.

In this way, the customerÕs involvement in the tendering process depends on:

¥	The IS-descriptions and operational items that must be made available to the supplier in order to facilitate the production of the desired results, as defined by the final state description.

¥	IS-descriptions

¥	Operational items

The customer's involvement in the production and completion processes is described in terms of:

¥	The products (e.g. packages, or existing data) that have to be fed into the production process

¥	Managing the dependencies between all the IS-adaptations that are currently proceeding,

¥	Planning the customer's involvement in terms of the human resources and materials that are required.

And last, but not least, the customer has to participate in the production process by:

¥	Taking their responsibility within the customer-supplier relationship and the decisions on the direction of the IS-adaptation being made. This responsibility may vary from an IS-adaptation to another: the customer may wish to take the overall control of the project or to give more or less control to the supplier.

That is, the customer's involvement is not limited to the provision of the initial state products.
The customer also participates in the production process by providing people and materials to the production process.

The decisions that the customer has to take, and thus their relationship with the supplier in terms of the customer-supplier transactions to be performed, is defined within the delivery plan, which is described in the following section.

These last points are very important within the context of Euromethod.
This is because Euromethod assumes that a customer makes informed decisions on the direction of the IS-adaptation.

However, it is recognised that there are other conceivable models of customer-supplier relationships!

| Example | In practice, a customer may avoid any responsibility for the technical direction taken by the IS-adaptation, thereby placing the entire risk for the ISÊadaptation in your hands. |
| --- | --- |

This is the customer's choice and you must define how you intend to handle these differences to Euromethod proposed approach.

The initial state of an IS-adaptation and thus the products that have to be fed into and considered during the production process are defined in terms of:

¥	The initial state:~ information system, i.e. the operational items contained in the operational information system at the beginning of the production process;

¥	The operational items of the future information system version that are available to the production process (they are constructed but not yet installed as part of the operational information system).

¥	And the IS-adaptation requirements i.e.

-	The IS-descriptions that are available and relevant to the IS-production process. These can include both IS-descriptions of the initial state information system and IS-descriptions of the future information system version;

-	The delivery plan;

-	Possibly project plans (development plan, quality assurance plan, configuration management plan) for the IS-adaptation.

| Example | Examples of documentation related to the information system that can be input to an IS-adaptation are: - The design of the currently operational information system - The design of a planned successor version of the information system - Manuals (of application software, system software, hardware) - Documented observations of problems with the currently operating information system - Statements of business goals the successor version must support - The IS-strategy definition of the customer organisation etc. |
| --- | --- |

## 2.4.	How is the Customer-Supplier Relationship described

As mentioned above, the customer-supplier relationship with your customer during the production process of the IS-adaptation is described within the delivery plan.

¥	The contents of a delivery plan

This relationship is described by means of the following concepts:

¥	The decisions that must be made throughout the production, and completion processes including:

-	The target domain deliverables that are required to support each of the decisions to be taken.

-	The project domain deliverables that are required to support each of the decisions to be taken.

¥	The decision points sequence.

¥	The planning of the project domain issues for the phases between the decision points.

Customer-supplier transactions take place at decision points during an IS-adaptationÕs production and completion processes. In the course of these transactions the supplier delivers the deliverables, as defined in the delivery plan. The customer must subsequently make the required decision on them.

The deliverables required for each of the transactions defined at the decision points, the initial state and the final state of an IS-adaptation have to be characterised by required deliverable profiles which are based upon deliverable model.

Guidance on the interpretation of the different types of Euromethod profiles is found within the Method Bridging Guide.

¥	Method
Product
Profiles

¥	Method Deliverable Profiles

¥	Required Deliverable Profiles

Deliverables are described by required deliverable profiles or method deliverable profiles.

A required deliverable profile defines the properties 
that have to be covered by a deliverable.

At the beginning of the production process (or when required during the production process), the products that constitute the initial state of the IS-adaptation have to be provided (that is, the existing products that match the profiles of the initial state definition) by the customer.

Figure 4: Euromethod support for tendering documents.

The deliverables which match the required deliverable profiles are produced during the production process. These are then delivered, as defined by the delivery plan, in order for the customer to make the decision within the appropriate customer-supplier transaction at a decision point.

## 2.5	Role Assignment in an IS-adaptation

It is important to appreciate the conceptual difference that exists between these IS-adaptation roles and the organisational roles found within your organisation, when using the Euromethod role concepts within an IS-adaptation. That is, unlike organisational roles which are usually long in duration, stable for some time, and applied to everything that role does within the organisation; IS-adaptation roles only exist within the context of a single IS-adaptation.

The IS-adaptation roles defined in Euromethod are:

¥	Contract Authority;

¥	Role Concepts

¥	Project Authority;

¥	Operational Expertise;

¥	Organisational Authority.

IS-adaptation roles represent authorities and responsibilities, and
the skills and knowledge provided to a single IS-adaptation.

In an IS-adaptation, each role may be performed by a single person or a group of people. A single person can also perform several roles.

| Example | ¥ A "project director" managing the supplier's work may perform the project authority role and at the same time provide operational expertise to the work. .¥ Operational expertise is generally provided by a group of people e.g. the project team. |
| --- | --- |

Lastly, it should be noted that IS-adaptation roles are not directly comparable to the role definitions found within development methods.

In defining an IS-adaptation and in performing the customer-supplier transactions, it is necessary to assign the IS-adaptation roles to people in your organisation. The rest of this section provides guidance on how this can be achieved and then monitored within an IS-adaptation.

IS-adaptation roles place requirements upon the organisational roles and the skill set of the people they are assigned to. In deciding whether a person within your organisation is appropriate  for a certain IS-adaptation role the following checklists should be followed.

General issues to be resolved for every role assignment is:

×	Should the role assignment be for the whole IS-adaptation or should it change at defined points?

-	Does the move from the tendering process to the production process require a change in the role assignments?

-	Should the role assignments be the same for every decision point or are changes necessary due to the decisions that have to be made?

×	Are the selected persons available to perform all the activities related to their involvement in the IS-adaptation?

Assigning the Contract Authority

Remember: A contract authority  is the person, or persons with the power to resolve or conclude an open issue with regard to a specific IS-adaptation contract. 
It is not necessary, or necessarily desirable that the same person acts as the contracting authority for every transaction within a given IS-adaptation.

A person is normally assigned the role of contract authority by a member of the organisation's senior management.

When assigning the contract authority role to a person the following apply:

×	The person must have the necessary authority within the organisation for signing contractual documents.

×	The person must have the necessary budgetary authority to manage a contract.

Besides these prerequisites, some questions concerning the skills of the person be nominated for contract authority may be asked, e.g.:

×	Is the person suitably skilled in customer-supplier relationships?

×	Is the person a skilled and experienced negotiator?

When using the checklists, it is important to recall that the customer is managing the business risk associated with the IS-adaptation, while the supplier is managing the technical risk.

Assigning the Project Authority

Remember: A project authority  is the person, or persons with the power to resolve or conclude an open issue with regard to a specific IS-adaptation project. 
It is not necessary, or necessarily desirable that the same person acts as the project authority for every transaction within a given IS-adaptation.

The constraint placed upon the organisational role of the person being assigned to the project authority role is:

×	Does the person have a proven record of managing projects within the supplier organisation?

Furthermore, when assigning the project authority role to a person the following questions apply:

×	Is the person suitably skilled in customer-supplier relationships?

×	Does the person have the necessary leadership skills to perform the project authority role?

×	Does the person have the necessary technical skills to perform the project authority role?

-	for the tendering process?

-	for the production and completion processes?

×	Does the person have the necessary bid management skills?

Selecting People to provide Operational Expertise

Remember: An operational expertise role is the role of a person or persons performing a development task or acting as an opinion maker based upon their expertise, skills or knowledge with regard to a specific IS-adaptation topic.

A person is normally assigned to provide operational expertise by the project authority in performing the delivery planning for an IS-adaptation.

In selecting the project actors that will perform the activities required from the supplier under the management of the project authority, the following question should be answered:

×	Does the person have the necessary business or technical skills to perform the tasks required of the operational expertise role as required by the IS-adaptation requirements?

At the end of this exercise, you will have established who in your organisation has the required expertise to undertake particular responsibilities within the IS-adaptation and is currently available.

Identifying the Organisational Authorities

Remember: An organisational authority is the role of a person or persons with the power to resolve or conclude an open issue with regard to the strategic requirements of the organisation.

Decisions made by a contract authority may be influenced by an organisational authority within the organisation, such as the senior supplier , the financial authority or legal authority , etc. The implication of this is that, in some circumstances, a decision can be imposed upon the contract authority by one of these organisational authorities.

In identifying the organisation authorities which have a stake in the progress of the IS-adaptation, the following should be considered:

×	Is the IS-adaptation important on a strategic point of view ?

=> If the answer is yes, then your senior management's view is important.

×	Is the IS-adaptation important on a financial point of view ?

=> If the answer is yes, then your financial authority's view is important.

×	Is the IS-adaptation affected by legal arrangements such as the EU directives or EU/GATT trade agreements ?

=> If the answer is yes, then your legal authority's view is important.

×	Are certain legal aspects of the contract regarding this IS-adaptation critical ?

=> In this situation, your legal authority's view is important.

×	Are the quality management requirements defined and being adhered to?

=> If this is the issue, your QM-Authority's view is important.

Completing the mapping of the IS-adaptation roles

Once the IS-adaptation assignments have been established you are in a position to complete the mapping to the decision point descriptions found within the delivery plan of the technical proposal. The following checklist is an aid to ensuring that all the decision point descriptions are complete from the IS-adaptation roles perspective :

Document delivery plan

×	Have you decided what IS-adaptation roles are required for all the decision point descriptions?

×	Have you decided what level of resourcing will be required for each IS-adaptation role in each transaction within the decision point descriptions?

# 3.	How to use Euromethod in the Tendering Process?

| Purpose | This chapter shows how the Euromethod concepts can be support the different activities you have to perform when participation in the tendering process of an IS-adaptation. |
| --- | --- |
| Activities | Your involvement in the preparation of, and subsequent participation in the different transactions of the tendering process. In particular, your usage of Euromethod in preparing a tender response regarding: ¥ The interpretation of the IS-adaptation requirements described in the call for tender document. ¥ The use of delivery planning, described in the Delivery Planning Guide, in the assessment of risks and some options for reducing risks. ¥ The use of method bridging, described in the Method Bridging Guide, in identifying and describing the deliverables that have to be produced. |
| Results | The results of these activities are the operational items and other deliverables that will constitute the supplier's technical proposal in response to the IS-adaptation requirements specified in the call for tender. |
| Concepts | ¥ customer-supplier transactions, ¥ delivery plan, ¥ initial and final state, ¥ IS-adaptation requirements, problem situation, situational factors, ¥ IS-development method, method product, ¥ method deliverable, and required deliverable profiles, ¥ IS-properties. |
| Examples | For examples, you are referred to the following Case Study chapters [EM-2.5-CS]: ¥ Chapter 4 - Preparation of a Tender Response (for NAS). ¥ Chapter 11 - Preparation of a Tender Response (for Eu-Rent). |

In the previous chapter you have seen which elements of an IS-adaptation contract are supported by Euromethod.

Remember: The tendering process of an IS-adaptation starts with the issuing of a call for tender and lasts until the signing of the contract for this IS-adaptation with the chosen supplier. [EM-3.1-TM]

If the IS-adaptation:~ requirements have been defined using Euromethod within either a call for tender, tender response or IS-adaptation contract's technical annex, they consist of:

¥	The IS-descriptions that are available and relevant to the production process. These can include both IS-descriptions of the initial state information system and IS-descriptions of the future information system version;

¥	The delivery plan;

¥	The project plans (development plan, quality assurance plan, configuration management plan) for the IS-adaptation, if applicable.

Document evolution

These definitions are not produced in a single step, but undergo an evolution during the preparation for the IS-adaptation and the IS-adaptationÕs tendering process.

The description of the delivery plan for the production process including the description of the initial and final state of the IS-adaptation evolves throughout the tendering process and is finally fixed in the IS-adaptation contract.

Once the decision to participate in a tender is made, your organisation has to perform a set of activities within the tendering process of the proposed IS-adaptation which will result in new versions of the IS-adaptation:~ requirements being produced. These are:

¥	Establishing an understanding of the customerÕs situation and the problems associated with the envisaged IS-adaptation.

¥	Developing a technical proposal containing the elements listed above These activities involve the production of documents which will either be exchanged in customer-supplier transactions, or used internally as part of the on going decision making process.

The remainder of this chapter focuses on the Euromethod supported aspects of the tendering process. Nevertheless, you should not forget that common business practices associated with the tendering process will continue. For example, questioning the customer and receiving the replies regarding the IS-adaptation requirements described within the call for tender document will continue to be undertaken in the normal way.

## 3.1	How to participate in the Call for Tender

As mentioned above, the Euromethod supported deliverables progress through a number of versions during the tendering process. These versions are produced either by the customer and documented in the IS-adaptation:~ requirements of the call for tender; or by your organisation in producing your tender response.

However, in some IS-adaptation situations, suppliers may have the opportunity to participate with the customer organisation during the preparation of the Call for Tender. This may simply be by responding to a request for information, or it could involve significant technical work in establishing the IS-adaptation:~ requirements.These can be viewed as iterations of the Euromethod tendering transactions. For example, where:

Tendering Process

¥	Suppliers are contacted by a customer with a "request for information" prior to the issue of call for tender, this request can be treated as an informal call for tender transaction; and the response to the request regarded as an informal tender response transaction.

¥	Suppliers, in response to a request from the customer for outline technical proposals, can be regarded as providing a provisional tender response in reply to a provisional call for tender.

Furthermore, if a supplier or suppliers are shortlisted on the basis of an evaluation of these outline technical proposals, a provisional supplier selection transaction has also been performed.

Remember: The use of the tendering transactions as they are described in this section is always to clarify the IS-adaptation requirements to the point where they are mature enough to be included within a formal call for tender, advertised for example, within the European Journal. Even when these more complex relationships occur, they are always followed by a formal call for tender transaction, as it is described in Euromethod, which initiates the IS-adaptation.

The involvement of a supplier within the preparation for the call for tender is very much controlled by the nature of the demand from the potential customer. However, the following checklist can be used:

×	If you receive a request for information:

=> Your response will be determined by the nature of the request. However, in most situations, it is unlikely that you will be required to produce detailed documents using the Euromethod concepts. However, you may choose to respond to the request using Euromethod common terminology.

×	If you receive a request for an outline technical proposal:

=> You should decide whether your response should provide an outline delivery plan, descriptions of the final and initial states and supporting initial products. Where they are necessary, it is recommended that Euromethod concepts are used where possible to provide this documentation.

## 3.2.	How to prepare the Tender Response Transaction

Goal:

To propose a feasible technical proposal addressing the customer's IS-adaptation requirements as stated in the call for tender document, in order to meet the customer organisation's strategic goals.

Remember: That the supplier:

¥	Decides whether the supplier organisation should participate in the tendering process by submitting a technical proposal to the customer organisation.

¥	Provides the complete technical proposal, including the proposed delivery plan.

¥	Provides terms and conditions or comments to the customer's proposed terms and conditions. [EM-3.1-TM]

As the name of the transaction suggests, in the preparation of a tender response transaction, you have to produce a tender containing the IS-adaptation requirements in the technical proposal, which will be submitted to the customer when the transaction takes place.

Euromethod provides you with the means to create the technical proposal in a terminology that assists the understanding of the technical proposal by the customer; simply because all the suppliers participating in a particular tendering process will use the same Euromethod concepts and terminology.

It is important to notice that

The .IS-adaptation:~ requirements in the technical proposal
must completely define the customer-supplier relationships in 
the production and completion processes of the IS-adaptation.

This means, you have to produce:

¥	A delivery plan that establishes in detail the sequence of the decision points, and thus of the customer-supplier transactions in the production and completion processes.

¥	 Products e.g. specifications describing the solution you propose to produce for the final state defined in the IS-adaptation requirements of the call for tender.

In order to be able to produce a technical proposal, you must also be able to understand the customerÕs problem situation described in the IS-adaptation requirements described in the technical specification.

Here Euromethod provides some assistance in analysing the problem situation and also the provided products; independently of the IS-Development method and notation used.

### 3.2.1.	How should you interpret the IS-adaptation Requirements

#### 3.2.1.1.	Identification of the Products to be delivered

The first thing you have to determine is what the final state, defined in the .IS-adaptation:~ requirements, means in terms of products you have to deliver. This means that you have to find out which of the products, found in the IS-development method that you intend to use, will have to be produced as a result of the envisaged IS-adaptation.

¥	Method product

¥	Product profile

The key to that question lies in the bridging of your method products to the deliverable model of Euromethod.

The required state of deliverables is defined in terms of required deliverable profiles that are based on the deliverable model of Euromethod. With the content of your methodÕs products characterised with the same set of concepts, you can establish a mapping of:

¥	The definition of your IS-development methodÕs products; in terms of the IS-properties each product is able to define.

This is documented in the method product profiles.

¥	The definition of the final state; i.e. the IS-properties for which products have to be produced (with the required state and scope of these products)

This is defined in the required deliverable profiles of the final state.

The mapping between the required deliverable profiles and the method product profiles is contained within the method deliverable profiles. These consist of the method product profile information augmented by the state and scope information needed to address the requirements of the required deliverable profiles of the final state.

The way that the method product profiles for your IS-development method can be produced is described in the Method Bridging Guide. This guide provides the guidance on the structure of the method product profiles and the procedure to follow when bridging the method products, i.e. describing the method products in Euromethod terminology.

¥	Method product

¥	Method Product profile

The concepts for characterising deliverables in an IS-adaptation and also the products of an IS-development method are defined in the Euromethod deliverable model.

¥	Views

¥	IS-properties

The set of products you have to deliver as the result of the envisaged IS-adaptation are established when all the IS-properties needed in the required deliverable profile of the final state are matched by the method deliverable profiles; i.e. when the final state can be reached by producing the products you have chosen.

#### 3.2.1.2.	Analysis of the Initial State Products

The initial state of the envisaged IS-adaptation is the next thing to be considered. In the contract, the initial state is defined by the method deliverable profiles for the products which the customer provides as the starting point of the intended IS-adaptation.

This description of the initial state by method deliverable profiles helps you in the following ways.

Performing product correlation

As with the final state, you can use the IS-properties to obtain a correlation between the products provided by the customer to products that are developed when using your method ; and thus determine the starting point of the IS-adaptation in terms of your own IS-development method.

This will provide you with a baseline, from which you can determine the required activities, resources and the associated costs needed to perform the IS-adaptation; based on your experience in applying your method.

Interpreting method products

Depending on the nature of the products provided by the customer (i.e.where they have been produced in a language and notation with which you are conversant), you may have the opportunity to filter the information provided by them into your production activities, without having to transform them physically. This is because it is possible to interpret both the initial state products and the product definitions of your method, in terms of the Euromethod concepts and consequently establish links between the concepts and information that they are addressing. Conversely, it also provides you with the means to identify what information must be re-engineered using your own method.

Assessing the quality of the initial state products

With the definition of the initial state provided, it is possible to assess whether the initial state products actually define the IS-properties of the initial state (again, where they have been produced in a language and notation with which you are conversant). In this instance, you can have a measure of the quality of the initial state products provided .

Making the decision to participate

Based on the analysis of what the initial and final state of the envisaged IS-adaptation mean in terms of your IS-development method, and knowing what activities you have to perform, you can now consider the actual production of the technical proposal. This is provided that the previously identified benefit in undertaking the IS-adaptation still exists and that you still intend to participate in the tendering process.

### 3.2.2.	How should you produce an IS-Adaptation Proposal

Delivery planning

In your tender response document you have to include a delivery plan which identifies all the decision points you intend to have, and thus all the deliverables you intend to deliver to the customer.

The Customer Guide provides some advice on the risks associated with the envisaged IS-adaptation; for example:

¥	Risks

¥	Your delivery planning may reveal that the initial state is not sufficient for the production of a tender response.

¥	The description of the problem situation might reveal that it bears risks that you do not want to take.

In each of these cases you can propose actions in your tender response that allow you to improve the situation. It should be remembered that the list of risks identified in the analysis of the problem situation can be revisited at other decision points during the IS-adaptation to assess whether the likelihood or consequences have changed.

¥	Assess problem situation

The inputs necessary to begin your delivery planning are:

¥	The description of the initial state of the IS-adaptation, documented in a required deliverable profile.

¥	The description of the desired final state of the IS-adaptation, documented in a required deliverable profile.

¥	The description of the problem situation, in terms of situational factors.

The way of actually performing delivery planning is defined in the Delivery Planning Guide [EM-2.3-DPG]. This contains the information provided on how to use the strategy model [EM-3.3-SM] to determine a strategy for the production process of the IS-adaptation and how to use the deliverable [EM-3.2-DM] and transaction models [EM-3.1-TM] to produce a delivery plan that implements that strategy.

¥	Define strategy and decision points

In addition, the description of a project situation in terms of situational factors is defined in the Delivery Planning Guide.

The review of an IS-adaptation by situation analysis and delivery planning assumes that

If you cannot plan a project now

you may not be able to control it in the future.

Assessment of delivery planning results

Thus, the exercise of producing a delivery plan can have two results:

1.	It can succeed, in the sense that it results in a delivery plan that is defined in enough detail to identify the necessary deliveries throughout the whole production process including the final delivery.

This is an indicator that the envisaged IS-adaptation is of a manageable size and can be performed without extra risk.

In this case a tender response can be produced and returned to the customer based on the existing documentation.

2.	It can fail, in the sense that it results in a delivery plan that is not able to define the deliveries up to the end of the production process. Rather, it goes as far as defining a contract change control transaction, after which no further deliveries are planned.

This is an indicator that the IS-adaptation is not of a manageable size and that there is a major risk in issuing a tender response based on the existing information. That is, the contract change control transaction is normally placed at the point where the risk associated with the ISÊadaptation becomes excessive, and a review of the .IS-adaptation:~ requirements within the contract is vital prior to the continuation of the ISÊadaptation.

A second difficult situation which can result in the production of a deficient delivery plan is where it is technically possible to proceed to the final state from the provided initial state, but where the size of the identified risk associated with the project situation is so large that it would not permit you to manage the IS-adaptation effectively. In this situation, corrective action should again be considered in order to minimise the risks associated to the characteristics of the IS-adaptation wherever possible.

Examples of risks that are associated with tendering for an IS-adaptation, for which the production process cannot be planned are:

¥	The price for your solution proposed in the tender response could be higher than that of other suppliers because you have to calculate a high contingency to cover the financial risk.

¥	The production process of the IS-adaptation could result in a failure because the IS-adaptation was not feasible.

¥	The cost of the IS-adaptation may not be controllable.

### 3.2.3.	What should you do if no Delivery Plan can be produced

As there are three parameters that determine the characteristics of an IS-adaptation i.e. the initial state, the final state and the situational factors, each of these parameters offers the potential of improving the characteristics of an IS-adaptation.

Thus, the basic options for corrective action are:

¥	The expectations of the final state are reduced.

¥	The initial state is amended.

¥	The situational factors are altered.

#### 3.2.3.1.	Amendment of the Final State

A supplier may make a proposal in which the expectations of the final state are reduced, in situations where it is possible to address most of the IS-adaptation:~ requirements, by producing some part of the final state only. Particular scope for this exists where a customer has defined the requirements in terms of those which are mandatory and those which are desirable.

However, reducing the expectations of the final state may not always be an option available to the supplier. The IS-adaptation was launched in order to achieve a certain business goal by the customer, which may well not be met if the final state is reduced or changed. This means that if the supplier considers that all other means of reducing the risk or uncertainty of the IS-adaptation would fail, he should either withdraw from the tendering process, or make a proposal to the customer recommending that the current problem situation requires a review of their information system strategy. In this instance, the objective would be to obtain a decision at the customer senior management level to revise the goals of the proposed procurement.

#### 3.2.3.2.	Amendment of the Initial State

If it is considered that the initial state, as it is currently defined, is not sufficient to perform the IS-adaptation because it introduces unmanageable uncertainties into the process, the supplier can consider how to improve the initial state to an extent where these uncertainties are resolved and the IS-adaptation becomes feasible and manageable.

There are different ways in which this amendment to the initial state can be achieved:

¥	The supplier can be provided with additional existing documentation by the customer, which could serve as an input to the IS-adaptation.

¥	If no suitable documentation exists the supplier may, in some circumstances (with the agreement of the customer), be able to produce the documentation that is required to create an acceptable initial state. In this case the supplier is effectively splitting the envisaged IS-adaptation into sequential IS-adaptations, which are:

-	One that establishes the required initial state based on the documentation which currently constitutes the initial state. This may be either funded as a separate IS-adaptation by the customer or may be performed by the supplier at their own expense in an effort to secure the IS-adaptation.

-	A second (which was the originally envisaged IS-adaptation), that produces the final state based on the, then available, required initial state.

This example actually shows a way of breaking down a procurement into a series of IS-adaptations. The typical initial and final states can be used to define the interfaces between the different IS-adaptations.

#### 3.2.3.3.	Change the Situational Factors

If it is considered that the risks associated with the currently envisaged IS-adaptation are not the result of an insufficient initial state, but are caused by the problem situation of the envisaged IS-adaptation, the decision can be made by the supplier to improve this situation.

To define the necessary corrective action an analysis of the problem situation, documented in a situational factor:~s table, is required.

In the situational analysis you will find situational factors whose s indicate a high uncertainty or complexity in your envisaged IS-adaptation.

You will not be able to change some of these factors, because they are inherent to the problem situation that the customer wants to solve within the envisaged IS-adaptation. Nevertheless, for some of them , you may have the opportunity of changing them for the better.

¥	Change individual situational factors

The explanations that support the values given to the situational factors can indicate such opportunities of improvement.

| Example: | ¥ Training of the persons that will be involved in the IS-adaptation as information system actors, if their capability or motivation is considered to be low. ¥ Use of external consultancy, if the information system actorÕs capability is considered to be low, and improvement cannot be achieved. |
| --- | --- |

## 3.3.	How to prepare the Supplier Selection Transaction

Goal:

Responding to customer's questions concerning the tender response.

Remember: That the supplier:

¥	Responds to any questions by the customer organisation regarding the tender response.[EM-3.1-TM]

The call for tender document issued by the customer will always provide a closing date for the receipt of your technical proposals. This date corresponds with the initiation of the tender evaluation activity, which will result in the supplier selection transaction, and thus the notification of your selection or rejection within this tendering process.

The transaction itself therefore requires the decision as to which technical proposal has been selected on the basis of the tender evaluations (a process which is mostly performed internally to the customer's organisation). The transaction is concluded by awarding the IS-adaptation to one or more of the participating supplier organisations in the tendering process and terminating this relationship with those supplier organisations that have not been chosen on this occasion.

Responding to customer's questions during tender evaluation

In more complex tendering processes, the supplier selection transaction is the point at which a number of suppliers might be short listed, based on their initial technical proposals.

The evaluation of a tender response involves an evaluation of the:

¥	content of the tender response itself and
¥	responding supplier organisation.

In this process though, you may have only a passive role to play. Normally, this will involve responding to any questions by the customer regarding your tender response.

Receiving the notification of selection or rejection

At the end of the tender evaluation procedure, you will be informed as to whether you have been selected for the IS-adaptation. If you have been selected you will then proceed to the contract awarding transaction with your customer.

If you have not been short listed or selected, you have a choice to make. You can either accept the decision of the tender evaluation, or you can investigate what aspects of your proposals were regarded as weak by the tender evaluation team. Where the customer organisation is subject to the rules contained within the Services Directive (92/50/EEC), the customer is obliged to provide you with a debriefing explaining why you were not short-listed or selected. This will normally be provided within a report giving the reasons for rejecting your tender response. In some situations, this report may provide you with the scores given to your tender response for each of the evaluation criteria. The lessons learnt from this can then be used in future technical proposals submitted by your organisation.

## 3.4.	How to prepare the Contract Awarding Transaction

Goal:

To obtain a contract in line with the negotiated customer IS-adaptation requirements while ensuring that the commercial benefits identified within the original IS-adaptation solution remain.

Remember: That the supplier:

¥	Introduces the supplier organisation's contractual concerns into the negotiation procedure.

¥	Obtains the best profit margin possible from the project.

¥	Decides if the supplier organisation's interests are still met by the proposed contract.

¥	Undertakes an impact analysis with respect to a proposed change and produces the amended delivery and project plans. [EM-3.1-TM]

In the preparation of the contract awarding transaction nothing new, in terms of Euromethod support, happens. Contract awarding involves the customer and yourself negotiating on what the final form of the technical annex shall be and is concluded either with the formal signing of the contract or with the withdrawal by either party from the contractual process. The negotiations are characterised by the consideration of the known technical, financial, management and quality issues, and is performed within the legal contract framework.

In some IS-adaptation situations, draft contracts will have been prepared and discussed with each shortlisted supplier at an earlier stage within the tendering process, for example prior to the supplier selection transaction. However, contract awarding corresponds to the time when the complete technical annex, containing the contract version of the delivery plan is finalised.

Refinement of the IS-adaptation requirements

Each negotiation undertaken is characterised by the need for clarification of, or requests for change to, the technical proposal. In practice, most requests for change come from the customer, but they can also come from yourself.

In some legal environments any negotiations after supplier selection may be completely forbidden.
In this situation, ; the delivery plan including the final and initial state descriptions in the technical proposal become part of the IS-adaptation:~ contract directly.

Where it is appropriate, the refined technical proposal can be augmented in all or some of the following ways:

¥	By incorporating the results of the contractual negotiations regarding the technical annex.

¥	By undertaking detailed delivery and project planning activities such as:

-	Refining the sequence of decision points.

-	Identifying deliverables and detailed bridging to an IS-development method.

-	Performing any relevant additional mappings to further methods or techniques.

-	Defining the interface between the IS-development method and the additional mappings to further methods or techniques.

-	IS-project resourcing.

¥	By including details of any corrective actions required within the process to be used in the IS-adaptation.

That is, during the detailed tender evaluation process, the customer organisation identified a list of issues regarding the proposed processes of the selected or shortlisted suppliers. Each of these issues may now be considered for inclusion within the technical annex.

Signing of the contract

By the end of contract awarding the version of the delivery plan proposed in the selected technical proposal has become the contract version of the delivery plan, and is included within the technical annex of the contract. On reaching this point, the transaction is formally concluded with the signing of the contract by the contractual parties.

# 4.	How do you use Euromethod in the Production Process

| Purpose | This chapter shows how the Euromethod concepts can support the different activities you have to perform related to customer-supplier transactions of the production process of an IS-adaptation. |
| --- | --- |
| Activities | Your involvement in the preparation of, and subsequent participation in the different transactions of the production process. |
| Results | The target domain deliverables defined by the within the technical annex of the contract are produced, along with the project domain deliverables required for the monitoring and control of the IS-production are produced. |
| Concepts | ¥ consistency, ¥ contract change control, ¥ delivery plan, decision point description ¥ development state, IS-properties ¥ final state, ¥ IS-adaptation requirements, problem situation, situational factor values, ¥ IS-development method, method product, ¥ method deliverable, and required deliverable profiles, product glossary. |
| Checklists | ¥ Preparation for delivery checklist. ¥ Recording experiences checklist. ¥ Need for contract change control checklist. |
| Examples | For examples, you are referred to the following Case Study chapters [EM-2.5-CS]: ¥ Chapter 8 - Detailed NAS Requirements Specifications |

Remember: The production and completion processes of an IS-adaptation are defined by an IS-adaptation contract.

All the customer-supplier transactions of the production and completion processes are scheduled and defined within the delivery plan of the IS-adaptation. [EM-3.1-TM]

In passing from the tendering process to the production process your responsibility as a supplier in the IS-adaptation are altered, so that it is now you who is driving the process. The interface to your customer is now expressed through two very different means. At the project level, resources are supplied by the customer to provide informal feedback into the production process. At the contractual level, you interface formally with the customer at the decision points containing the transactions defined within the delivery plan.

That is, during the production and completion processes, you are very often ÒactivelyÓ pushing forward the process. The customer interfaces to you through the delivery plan requirements and the provision of appropriate operational expertise to the project.

In the production process, transactions are started by the exchange of products between the customer and supplier (which may be target domain deliverables, project domain deliverables or change control requests), and are terminated when the required decision has been made.

This chapter looks at the support that Euromethod can provide within the preparation of the deliverables in the transaction.

## 4.1.	Approval of Deliverables

Goal:

To deliver the deliverables that meet the customer expectations, to receive approval for those deliverables and hence permission to proceed with the IS-adaptation.

Remember: That the supplier:

¥	Delivers the deliverables to the customer.

¥	Decides whether the deliverables meet the IS-adaptation requirements within the technical annex within the contract and are ready for delivery to the customer organisation. [EM-3.1-TM]

Euromethod supports the description of decision points , and in particular, the purpose of a decision point. Consequently, when a set of deliverables is delivered, it has already been clearly defined within the delivery plan what the technical and managerial purposes are for the relevant decision point, what roles are required and thus what the goals of the customer-supplier interaction within a transaction are. In this way, far greater visibility of the decision involved in the approval of deliverables is achieved.

¥	Define decision points

More information on decision point descriptions can be found in the Delivery Planning Guide.

¥	Define decision points

Each decision point has been identified and jointly agreed by the customer and yourself as part of the preparation of the delivery plan. In addition, you identified which i.method product;s were required in order to meet the requirements of each decision point within the production and completion processes.

This was achieved by matching the method product profiles of the IS-development method with the required deliverable profile until all of the aspects required had been completely addressed i.e. its purpose, the appropriate development and quality states needed, the IS-properties covered etc.. This was recorded within method deliverable profiles.

Method product profiles

Product glossary

It is the decision point description; within the delivery plan which now defines what must be done at an approval of deliverables decision point.

The decision made by your customer on receipt of some deliverables is split into two parts. Firstly, the customer decides, on the basis of the deliverables, whether the IS-adaptation is still on course, and therefore whether the IS-adaptation is still on target to reach the required final state. Secondly, the technical content of the method products is assessed to judge their accuracy in this business context.

| Example: | A customer approves a data model of the future computer system: ¥ If, based on this data model, the customer is confident that the IS-adaptation is still on target. ¥ If it is felt that data model contains all of the data which must be included within the future computer system to satisfy the business need. That is, the customer is deciding on the completeness of the method product [EM-3.2-DM]. |
| --- | --- |

Checking the deliverables before delivery

As the conclusion of a production phase leading to the delivery of some deliverables at a decision point, it must be decided if the method products are in a state which is good enough to be delivered. You must therefore review:

¥	The associated decision point description,

¥	The method deliverable profiles,

¥	And in particular, review the state of each method products to see whether they address the IS-adaptation:~ requirements for this decision point and thus satisfactorily support the decision to be made.

The control of the content of the method products and hence the decision to deliver should be based on your completion of the following checklist:

×	Has the purpose of the method product been fully achieved to meet the requirements of this decision point?

×	Is the system (either the current or future) considered by the method products consistent with that specified in the decision point description?

×	Do the method products to be delivered cover all of the views required to satisfy the requirements of the decision point description?

×	Do the method products consider all of the properties (IS-properties, project properties and non-functional properties) required to satisfy the requirements of the decision point description?

×	Is the development state of the method products consistent with that specified in the decision point description?

×	Is the quality state of the method products consistent with that specified in the decision point description?

×	Is the deliverable scope of the method products consistent with that specified in the decision point description?

×	Does the method product developed correspond with the product glossary specified in the supplier's method product profile for the decision point?

¥	Method product profiles

Product glossary

×	Have all the rules for internal consistency of the method product been observed?

×	Has the method product developed demonstrated your claims about its suitability in this situation?

In the situation where the decision point description includes operational items, you should check the following:

×	Do all the operational items have the required functionality?

×	Does the system fulfil the IS-adaptation requirements?

These last two items should have been tested prior to delivery.

Within your method deliverable profiles, it will have been specified what internal consistency rules are required for each product to address the decision point description.

Where appropriate, these consistency rules should now form part of the quality review criteria prior to the delivery of the method products to the customer. That is, the method products should be reviewed for consistency in those circumstances where they are needed to support the decision to be met using these deliverables.

¥	Consistency rules

| Example: | One of the Euromethod consistency rules is that every data item within a data model should appear in at least one computerised function. One of the consistency checks within the quality review for the data model of the future system considered earlier could be to see if every data item is considered within at least one computerised function. [EM-3.2-DM] |
| --- | --- |

Delivering to the customer

When the deliverables have been checked, they must be delivered to the customer, as specified in the contract.

Customer Deliveries

Occasionally, there will be a need for the customer to make a delivery to the supplier. Examples of this are the provision of the target domain hardware, or the packages upon which the IS-adaptation will be based. In these circumstances, an approval of deliverables transaction can be planned. In the situation where the delivery is not made to the suppliers satisfaction, and this has implications on the project's progress, the supplier may call for a contract change control transaction to take place.

In this instance, the Euromethod concepts regard the supplier as a customer and vice versa.

Rework of Deliverables

Normally, the supplier submits the deliverables at a decision point for approval by the customer, expecting them to be approved. However, this may not happen! Indeed, in the real world of live projects, the reasons are myriad why a deliverable may not be delivered entirely in line with its intended requirement. It may result from shortfalls in either the customer or supplier organisations. Examples which would result in rework are:

¥	The deliverables did not conform with the IS-adaptation requirements.

¥	Rapidly changing circumstances within the customer organisation were insufficiently taken into account and resulted in the deliverables reflecting an obsolete problem situation.

The Delivery Planning Guide explains how you can avoid the risk of this occurring by developing delivery plans which are sensitive to a given project situation and which are therefore adaptable to the production situations that will be encountered. For example, a problem situation in which the requirements are evolving rapidly can be handled by the use of a delivery plan developed upon an experimental description approach and an evolutionary construction approach.

¥	General approaches

Unfortunately, while it is best avoided, deliverable rework is going to be unavoidable in some circumstances and new approval of deliverables and approval of project status and plan transactions will have to be introduced into the delivery plan. This requires that you:

¥	Assess, with your customer, the impact of delays and resourcing problems on the production process.

¥	Make changes to the project plans.

¥	Ensure the delivery of the deliverables that the customer wants.

The control of the content of the reworked method products and hence the decision to re-deliver should be based on the same checklist used in your preparation in originally submitting the deliverables.

Where appropriate, the consistency rules should be reconsidered where they are needed to support the decision to be made.

Rework Acceptance

The decision made by your customer in this instance is, as with the original submission of the deliverables, split into two parts:

¥	Firstly, whether the IS-adaptation is back on course, and whether you are back on target to deliver the required final state system.

¥	Secondly, the customer is assessing the technical content of the reworked method products.

From our earlier example, does the customer now believe that the data model of the future computer system contains all of the business information which must be included within the future computer system.

Recording experiences for use in future ISÊadaptations

Since Euromethod offers the means to clarify the decision process, and therefore the decision making associated with each delivery, it provides a framework in which to capture project experiences. In particular, it facilitates the recording of what is necessary in a method product to support a particular decision, and conversely what is not necessary. You therefore have the means to use your own observations to help tailor the production process to meet the demands of the decision making process within future IS-adaptations better. Consequently, the over-engineering of certain method products within your production process may be avoided !

For each approval of deliverables decision point, you should consider the following checklist:

×	What parts of the deliverable (and thus its constituent method products) were observed as facilitating the customer's decision making process?

×	Were any concepts in the deliverable not observed as facilitating the customer's decision making process?

×	Were all of the requirements of the decision point description equally well supported by the deliverable?

×	For those aspects of the decision point description which were not well supported by the deliverable, what must be done in future to provide a better quality product ?

As stated earlier, rework is expensive. It eats into project schedules, your budget and finally your profit. This review approach can be applied to reworked deliverables in the same way as it was to the originally submitted deliverables.

## 4.2.	Approval of Project Status and Plan

Goal:

To ensure the IS-adaptation feasibility by uncovering risks and defining actions to prevent them i.e. to protect the benefit to be gained from the project.

Remember: That the supplier:

¥	Delivers the necessary project status and plan deliverables to the customer.

¥	Represents the supplier organisation at the project status and plan review.

¥	Proposes appropriate solutions to problems and risks.

¥	Determines whether a contract change control transaction is necessary from the supplier point of view.

¥	Triggers any contract change control activities within the supplier organisation.

¥	Determines the technical implications to the supplier organisation within any contract change control activities.[EM-3.1-TM]

An approval of project status and plan transaction is performed with the customer but is approved by the customer alone. In this transaction, project domain deliverables covering topics such as management reporting, assessments of project risks, feasibility and quality and proposals for risk resolution, re-planning and resource allocation are evaluated. Based on the evaluation of the reports, contract change control may be triggered if necessary.

¥	Project Domain Deliverables

The purpose of introducing a transaction of this type into the delivery plan is to:

¥	Make an assessment of the impact of delays and resourcing problems in the production process.

¥	Make a co-operative decision with respect to corrective actions, i.e.

-	Changes to the delivery plan.

-	Changes to the project plans.

Remember: The planning of the IS-adaptation is determined by the sequence and schedule of the customer-supplier transactions.[EM-3.1-TM]

Therefore, the decision to be made in transactions of this type is whether to:

¥	Continue the production process with the existing plans,

¥	Approve changed plans for the further production process,

¥	Trigger a contract change control transaction.

The Delivery Planning Guide can be used in the assessment of the impact of particular problems.

¥	Assess Delivery plan

Assessing the problem situation

As a supplier, you may be requested to analyse the problems in the IS-adaptation by assessing the problem situation.

Based on the new analysis of the problem situation, the initial conclusions about the IS-adaptation can then be checked to see whether the strategy chosen remains valid; and thus whether it is safe to tackle the problems with slight changes to plans. For example:

¥	Postponing of deliveries.

¥	Changes to the project plans; e.g.

-	New resource planning,

-	Changes in management procedures,

etc.

Performing corrective actions and complementary initiatives

A further characteristic of this transaction is that, on the basis of the project reports, the customer can identify a number of corrective actions which could be performed by your organisation in order to improve your processes. In this way, the approval of the project status and plan transaction may lead to the instigation of a process improvement programme to run in parallel with the IS-adaptation. However, all process improvement issues will be handled outside of the Euromethod concepts.

## 4.3.	Contract Change Control

Goal:

Where requirements to the IS-adaptation have developed from those defined within the contract, they need to be documented within the project process as part of a controlled change process to ensure an up to date technical annex in the contract.

Remember: That the supplier:

¥	Decides if the supplier organisation's interests are still met by the contract.

¥	Identifies the technical implications caused by the gap between the customer's stated and actual IS-adaptation requirements which must be resolved by contract change control .

¥	Represents the supplier organisation within the triggered contract change control activity.

¥	Obtains the best profit margin possible from the project.

¥	Decides if the supplier organisation's interests are still met by the contract and whether this needs to be followed up in contract re-negotiations by senior management.[EM-3.1-TM]

The contract change control transaction addresses the situation in which changes to the technical annex of the contract are identified and processed.

In some legal environments no re-negotiation of the contract is permitted.
In this situation, the contractual descriptions of the final and initial state and the delivery plan are fixed for the duration of the IS-adaptation.

The transaction is concluded when the new version of the technical annex containing the changes is approved. Changes to the body of the contract, which contains the legal and financial provisions of the contract are not addressed by this transaction.

The contractual change control process
must be outlined within the contract.

General usage of contract change control

Contract change control may be either planned within the delivery plan, or be triggered during the production or completion processes. It may be triggered by either the customer, or by yourself when technical or planning risks that are not handled clearly within the technical annex of the existing contract are detected. Contract change control often follows an assessment of either some deliverables, or of the project itself, in which changes to the technical annex are identified which reduce a threat to the project's outcome.

As mentioned above, contract change control consists of the agreement of both contractual parties to changes to the technical annex. The nature of these changes is such that, they act as a minor amendment or clarification of a previously stated requirement. In the large majority of cases the changes made as part of the contract change control do not have a substantial impact upon the content and intention of the contract. It simply records the advances in the understanding of the contractual goals and requirements.

The following checklist identifies situations in which a contract change control transaction may be needed:

×	Does some aspect of the technical annex require some further clarification?

×	Has part of the production process resulted in the need for some enhancement or updating of the IS-adaptation requirements?

×	Are some of the specifications provided in the technical annex no longer applicable to the IS-adaptation and should they be removed to avoid confusion?

Based on your experience, further examples are likely to be identified.

Examples of the changes that can be made are:

¥	Perform a new analysis of the problem situation and check whether the initial conclusions about the IS-adaptation strategy are still valid.

Based on this analysis, you should make changes to the plans. For example:

¥	Postpone some of the deliveries defined within the delivery plan.

¥	Redefine responsibilities within the delivery plan.

¥	Introduce additional decision points.

¥	Make changes to the project plans; e.g.

-	New resource planning,

-	Changes in management procedures, etc.

Contract change control and re-negotiation of the contract

In some circumstances, major technical changes may be involved which require radical changes to the plans and the contract itself. In this circumstance, the contract change control transaction is used to manage the technical changes to the technical annex. However, all re-negotiation of contract issues will be handled outside of the Euromethod concepts, using normal business practices.

Remember: The Services Directive states that if a customer fundamentally changes their requirement, then they must re-advertise. [92/50/EEC]

The likely scenarios in which this may occur are:

¥	The customer detects that the IS-adaptation requirements stated in the technical annex are no longer in line with the business objectives, and thus wants to change the technical annex in order to ensure the system needed is obtained.

¥	The customer detects that the IS-adaptation requirements are not being met by the supplier.

¥	The supplier detects that the real customer expectations are not consistent with the stated IS-adaptation requirements, and thus wants a significant change of the technical annex in order to avoid risks to the acceptance of the work.

¥	The supplier discovers that the system development is not feasible.

Contract change control and contract completion

In each of the following situations the performance of one of the contractual partners is found to be damaging to the progress of the IS-adaptation:

¥	Your performance is thought to be partially or wholly unsatisfactory in meeting the objectives of the IS-adaptation. Consequently, the customer may require that the supplier is removed from the IS-adaptation.

¥	One of the contractual parties is found to be in breach of the contract.

In these circumstances, which are comparatively rare, contract change control allied to a re-negotiation of the contract may not be enough to salvage the project, and contract completion; could be invoked as part of the cancellation of the IS-adaptation.

From this it can be seen that in the terms of the Euromethod support provided to the IS-adaptation nothing new happens as part of the contract change control transaction. Contract change control is simply a review of the existing Euromethod supported products to obtain a better functioning project, and consequently an improvement in the customer-supplier relationship. More information can be found in the Delivery Planning Guide.

¥	Assess Delivery plan

## 4.4.	IS-adaptation Role Assignments in the Production Process

Once the delivery plan has been incorporated within the technical annex of the contract, you must monitor whether the IS-adaptation role requirements are being adhered to as defined within the delivery plan , both in terms of the people that you are able to assign to the production and completion processes at a particular time, but also in terms of what resources the customer is assigning to the appropriate parts of the IS-adaptation.

Further information on this can be found within the Delivery Planning Guide.

# 5.	How do you use Euromethod in the Completion Process

| Purpose | This chapter shows how the Euromethod concepts can support the different activities you have to perform related to customer-supplier transactions of the completion process of an IS-adaptation. |
| --- | --- |
| Activities | Your involvement in the preparation of, and subsequent participation in the different transactions of the completion process. |
| Results | The final deliverables defined within the technical annex of the contract are produced, along with any project domain deliverables required for the monitoring and control of the IS-production. As a result, the IS-adaptation terminates with the supplier having met the IS-adaptation requirements. |
| Concepts | ¥ contract change control, ¥ decision point, decision point description, ¥ IS-properties ¥ final state profiles, ¥ IS-adaptation requirements, problem situation, ¥ method product, method deliverable, and required deliverable profiles. |
| Checklists | ¥ Preparation for delivery checklist. ¥ Recording experiences checklist. |

## 5.1.	Approval of Final Deliverables

Goal:

To provide the final deliverables in line with the contractual IS-adaptation requirements and satisfying the customer expectations as close as possible; in order to permit the successful termination of the contract.

Remember: That the supplier:

¥	Decides whether the proposed final deliverables meet the requirements of the technical annex of the contract and are ready for delivery to the customer organisation.

¥	Delivers the proposed final deliverables to the customer.[EM-3.1-TM]

From Section 4.1, it is known that Euromethod supports the description of a decision point, and in particular, the purpose of a decision point. In this way, there really is no distinction between the final delivery and those which have preceded it in the production process. That is, the technical support to the decision point concerning the approval of final deliverables is defined within the final state:~ profiles within the delivery plan. Thus, when the final deliverables are delivered, it has already been defined within the delivery plan what the technical and managerial objectives are, and thus what the goals of the customer-supplier interaction are. In this way, greater visibility of the decision to be taken is achieved.

More information on decision point descriptions can be found in the Delivery Planning Guide.

¥	Define decision points

The decision made by the customer on receipt of the final deliverables is split into the following parts. Firstly, the customer is deciding, on the basis of your deliverables, whether the IS-adaptation:~ requirements in terms of the required information system or the IS-descriptions have been achieved. Secondly, the customer is assessing the technical content of the delivered method products.

Deliverable non-acceptance can be caused either because of the poor specification of the requirements in the first instance, the poor quality of the deliverables, or by the expectation gap that can exist between customers and suppliers in general.

As part of the preparation of the delivery plan, you identified which of your method products were required in order to meet the requirements of the final state of the IS-adaptation by producing the method deliverable profile. This was achieved by matching the method product profiles until they had completely addressed all of the aspects required by the final state required deliverable profile i.e. its purpose, the appropriate production and quality states needed, scope, the IS-properties covered etc.

Checking the deliverables before delivery

On deciding when to deliver the final deliverables, you must decide if they are in a state, which is sufficiently good to be accepted, and in the case of operational items successfully tested and installed within the target domain. You must therefore review:

×	The final state profile,

×	The method deliverable profiles,

×	And in particular, the development state and quality state of the method products to see whether they address your requirements for final state and thus satisfactorily support the final state decision process,

×	The results of the tests on the operational items.

The control of the content of the method products and hence the decision to deliver should be based on the completion of the same checklist as was used in the Approval of Deliverables transactions, with the following minor changes:

×	The term decision point description should always be read as final state within the checklist items.

×	All the IS-adaptation deliverables must be viewed in the context of the final state.

Consistency checking is identical for the final deliverables as for any other delivery within the production process.

Delivering to the customer

When the deliverables have been checked, they must be delivered to the customer, as specified in the contract.

Recording project experiences

As mentioned in earlier sections, Euromethod provides a framework to capture project experiences and record what is necessary in a method product to support the decision making process. This framework can be applied to final deliverables in the same way as it was applied to any other deliverables. However, it is most common that this review is incorporated within the end-project review performed as part of the contract completion.

## 5.2.	Contract Completion

Goal:

To ensure that all outstanding technical and commercial transactions regarding this IS-adaptation contract have been satisfactorily concluded.

Remember: That the supplier:

¥	Ensures the timely closure of the IS-adaptation, while keeping in mind the possibility of further business opportunities.[EM-3.1-TM]

As the supplier, the contract completion transaction is essentially an administrative transaction, in which you ensure that all the transactions regarding the IS-adaptation have been satisfactorily completed. However, it may also contain residual technical tasks.

Scheduled Completion

You should aim to work co-operatively with your customer, in order to phase out all the technical, management and financial aspects of the IS-adaptation in a controlled manner.

When contract completion occurs after the acceptance of the final deliverables, it is performed in the scheduled manner, 
which represents the normal termination sequence for an IS-adaptation.

Unscheduled Completion

As mentioned in the section regarding contract change control, contract completion can also occur in an unplanned fashion.

When contract completion occurs in an unplanned fashion, 
it is performed in a triggered manner. 
It thus represents the abnormal termination sequence for an IS-adaptation.

Technical and commercial aspects of completion

In completing the contract completion, you should check that all the following checklist items have been satisfactorily concluded:

¥	Technical aspects:

Examples of the outstanding results are:

-	Have all the operational items been amended in line with the results of the acceptance test suite to ensure the smooth running of the operational system ?

-	Has any previously produced planning information regarding future IS-adaptations under consideration been made available to both parties?

-	Has all the quality review documentation been completed and provided by you?

-	Has all the user documentation been finalised and delivered to the customer?

¥	Commercial aspects:

Examples of possible outstanding commercial aspects are:

-	Have all the sub-contracts been honoured?

-	Have all the invoices been issued to the appropriate organisations?

-	Have all the cost statements been submitted?

Managing dependencies with other transactions

It is common that the contract completion can run in parallel with one or more transactions. For example, the customer may choose to initiate further contractual negotiations (or perhaps issue a new call for tender document) to address the post-contractual relationship i.e. the undertaking of a new IS-adaptation or finalising the maintenance agreement. A second example is the case of an abnormal termination to an IS-adaptation. In this instance, the execution of this transaction may occur in parallel with that of contract change control.

You should pay attention to managing these interfaces to provide a consistent and manageable relationship with the customer.

Recording experiences for use in future IS-adaptations.

What are the lessons from this IS-adaptation that must be absorbed in future IS-adaptations?

Euromethod provides a framework to capture project experiences for both the target and project domains and subsequently record what is necessary in order to support the decision making process demanded by complex customer-supplier relationships.

This framework can be applied within contract completion to address the entire IS-adaptation, in the same way as it has been applied individually to the target and project domain transactions. Once again, you have the means to use your own observations to help you develop future production processes to meet better the demands of the decision making process within future IS-adaptations.

Lastly, you have the additional opportunity within the contract completion transaction to perform a synthesis of the entire customer-supplier relationship, and thus build up a feeling for what constitutes best practice in this complex area.

Your objective is to learn from your experiences.
Support the decision process in future IS-adaptations.
Avoid the risk of delivering either the wrong, or poor quality adapted information systems!

In performing this end-project review you can reuse the earlier lessons checklist to consider the lessons to be learnt (See Section 4.1) for each decision point and production phase within the production process.

# References

[EM-1-EO]	Euromethod Overview, 1994

[EM-2.1-CG]	Euromethod Customer Guide, 1994

[EM-2.2-SG]	Euromethod Supplier Guide, 1994

[EM-2.3-DPG]	Euromethod Delivery Planning Guide, 1994

[EM-2.4-MBG]	Euromethod Method Bridging Guide, 1994

[EM-2.5-CS]	Euromethod Case Study, 1994

[EM-3.1-TM]	Euromethod Concepts Manual 1 - Transaction Model, 1994

[EM-3.2-DM]	Euromethod Concepts Manual 2 - Deliverable Model, 1994

[EM-3.3-SM]	Euromethod Concepts Manual 3 - Strategy Model, 1994

[EM-4-ED]	Euromethod Dictionary, 1994

---------

[87/95/EEC]	Standards Decision

[92/50/EEC]	Council Directive 92/50/EEC of 18 June 1992 relating to the co-ordination of procedures for the award of public service contracts

# Index

application software 19

approval of deliverables 46, 49, 50, 60

approval of final deliverables 59

approval of project status and plan 49, 52

authority 23

call for tender 12, 27, 28, 29, 39, 62

completion process 17, 31, 45, 46, 58

computerised function 48

configuration management plan 28

consistency 48, 50, 60

construction approach 49

contract authority 23

contract awarding 40, 41

contract change control 35, 51, 52, 55, 62, 63

contract completion 61

customer organisation 19, 39, 40

customer-supplier transactions 31

decision point 19, 23, 31, 34, 45, 48

decision point description 26, 46, 47, 51, 60

deliverable model 20, 32

deliverable scope 48

delivery plan 19, 28, 31, 34, 35, 45, 46, 52, 60

description approach 49

development plan 28

development state 47, 60

Euromethod concepts 11

final state 15, 19, 32, 35, 36, 60

~ information system 15

~ profiles 59

financial authority 25

for a certain IS-adaptation role the following checklists should be followed. 22

initial state 19, 33, 35, 36, 37

~ information system 18

initial state information system 28

IS-adaptation 11, 52

~ contract 11, 12, 42

~ requirements 12, 13, 14, 28, 29, 31, 32, 36, 37, 47, 59

IS-adaptation strategy 55

IS-description 17, 18, 28, 59

IS-development method 32, 46

IS-properties 32, 33, 34, 47, 60

IS-adaptation contract 45

key role

contract authority 22, 23

operational expertise 22

organisational authority 22

project authority 22, 24

legal authority 25

method deliverable profile 32, 33, 46, 48, 60

method product 32, 47, 50, 59, 60

method product profile 32, 46, 48, 60

non-functional properties 47

Operational expertise 22, 24, 45

operational item 17, 18, 48, 60, 62

organisational authority 25

problem situation 31, 35, 38, 52, 55

product glossary 48

production process 17, 28, 31, 45, 46

project authority 24

project domain deliverables 19, 52

project plan 28

project properties 47

project report 53

quality assurance plan 28

quality state 46, 47, 60

relevant deliverable model 13

required deliverable profile 20, 32, 33, 35, 46

responsibility 17

risk 35

role concepts 21

senior management 25, 37

Services Directive 11, 40, 56

situational factor 35, 36

~ value 38

~s table 38

specification 55

supplier selection 39

system software 19

target domain 60

target domain deliverables 19

technical annex 12, 15, 28, 43, 46, 57

technical proposal 12, 29, 31, 34, 39, 42

technical specification 11, 12

tender response 12, 28, 29, 31, 35, 40

tendering process 12, 28

typical final state 38

typical initial state 38

Supplier Guide Document history

| Version | Status | Author | Comment | Distribution |
| --- | --- | --- | --- | --- |
| 221193 | Being developed | MG | Initial draft of D.3.2 | MF, MG, MP, NA |
| 261193 | Being developed | MP | Update of the table of contents for control-board review. | MF, MG, MP, NA |
| 291193 | Being developed | MP | Update of the table of contents for control-board review. | MF, MG, MP, NA, control-board |
| 011293 | Being developed | MP | First version of the chapter ÒHow to use Euromethod in the tendering process?Ó | NA, MP |
| 081293 | Being developed | MP | First step towards an integration of the use of the role concepts | MF, MG, MP, NA, LM |
| 200194 | Being developed | MP | Further development based on the EMPMB presentation |  |
| 110294 | Being developed | MP, MG | Revised introduction Section 2 copied from Customer guide. Guidance on Tender Response provided. |  |
| 070394 | Under L3 review | MP, MG | ¥ Rewritten the first two chapters in line with the Customer Guide ¥ Produced the Tender Response section ¥ Transaction guidance section completed, with special emphasis on Tender Response and Approval of Deliverables. |  |
| 230394 | Under L3 review | MG, MP | Post L3 and project team review version incorporating all review changes. |  |
| 050494 | Delivered | MG | Final changes taken from second L3 reading. All layout standards incorporated | CEC |
| 170694 | Under L3 review | MG, MP | EMPMB comments taken into consideration | Review Group |
| 300694 | Delivered | MF |  | CEC |

The operational items of a future information system which have not been installed as part of the operational information system at this time, may then be subject to a separate IS-adaptation covering the transition from the Tested Information System typical state to the Installed Information System typical state. This may be appropriate in the situation, for example, where the services of a separate supplier skilled in managing organisational change may be required.

In this section, the word person may mean individual or group of individuals.

However, in some legal environments it has to be fixed in the Call for Tender or in the Tender Response.

In restricted and negotiated tendering procedures, the supplier organisations may already have been evaluated. In this case, that evaluation will simply be refined now. In open tendering procedures, this will be the first opportunity to evaluate a supplier.

In those contractual situations in which no negotiation is allowed, and in which the tender response can not be adopted as the basis of a contract, the only option available is to redo the entire tendering process.